## Dev Tracker
Project Name | Website Url | Task | Priority | Assign | S Date | E Date | As Per WO | Status | Env | Efforts | Actual Effort | Informed | Support Needed / Blocker | Dependency Detail | Page Url | Mail Subject | Internal Mail Subject | Functionality | Gmail Thread ID | Google Task ID
Adfactors PR Private Limited | intranet.adfactorspr.com | Demo Page | Low | Parthiban | 2026-04-29 | 2026-05-04 |  | Under Review & Testing | Staging | 5 | 4.5 |  | All the changes have been completed. We are waiting for approval to go live | Awaiting for approval to go live |  |  | [Dev Tracker] TASK UPDATE: Demo Page |  | 19ec0731129c8883
Adfactors PR Private Limited | intranet.adfactorspr.com | Intranet Tech Queries | Low | Sowndar | 2026-04-30 | 2026-05-07 |  | Under Review & Testing | Production | 6.5 | 6.5 |  | Vishal Said He will come back to us |  |  |  | [Dev Tracker] TASK UPDATE: Intranet Tech Queries |  | 19ec52bb83377384
Adfactors PR Private Limited | intranet.adfactorspr.com | Content Update June | Low |  | 2026-06-01 | 2026-06-13 |  | In Progress | Staging | 5 | 4.5 |  | Update the content in awards page Create a new Casestydy In live sort and update the Leadership team members Update content in Cross sell inivative winner list |  |  |  | TASK UPDATE: Content Update June |  | 19ed29ab81158007
Adfactors PR Private Limited | intranet.adfactorspr.com | Adfactor Admin Dashboard | Low | Parthiban |  |  | 2026-02-24 | On Hold / Blocked | Staging | ⚠ Missing Effort | 3.5 |  | Following the Adfactor dashboard submission, we have finalized the functional requirements and staging updates. Although changes were ready by March 24th, the site has been offline since March 26th due to server instability. We provided the database to the server team on April 9th. To resolve the remaining issues, we must create a new image directory with the correct write permissions; this is essential for posts to be saved and displayed correctly. We also require a WAF permission update |  |  |  | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard |  | 19ec6ac88dbc8391
Adfactors PR Private Limited | intranet.adfactorspr.com | Dev Update June | Low | Parthiban |  |  |  | In Progress | Staging | 32.5 | 15.5 |  | Update the content in awards page Create a new Casestydy In live sort and update the Leadership team members Update content in Cross sell inivative winner list Update and fix the issue in SQL for restore Database List the Case study with published and Article date "change name Adfactors PR 1/3 carosel badge Remove bold for value in current affairs System generated post Text changes Enable the Auto post generation Fix the EmployeeID in Post moderation Add AE AM decathlon in utilities page" Left align the text in system generated post |  |  |  | TASK UPDATE: Dev Update June |  | 19ed29ae59265021
Adfactors PR Private Limited | intranet.adfactorspr.com | Case Study Page May 2026 | Medium |  |  |  |  | Pipeline / To Do | Local | 0 | 0 |  |  | Need to develop new Case Study page template. Client logos/design assets if required. |  |  | TASK UPDATE: Case Study Page May 2026 |  | 19ed1518e71e4cb5
Adfactors PR Private Limited | work.adfactorspr.com | Restore Work.Adfactor | Low |  |  |  |  | Pipeline / To Do | Local | No Subtasks | No Subtasks | [5 empty] | [Dev Tracker] TASK UPDATE: Restore Work.Adfactor |  | 19e3488183ba4491
Diriyah Gate Development Authority | www.dgda.gov.sa | Raise Concern | Medium |  | 2026-05-13 | 2026-05-18 | 2026-05-18 | Under Review & Testing | Production | 9 | 9.5 |  | Shared with Client Waiting for approval | Need Approval From Saad | https://release-dgda.d1pchk3m069rke.amplifyapp.com/en/contact-us/general-inquiries | Open Data Form - DGDA | TASK UPDATE: Open data form Phase - 2 |  | 19ec976388afdc2e
Diriyah Gate Development Authority | www.dgda.gov.sa | Events Application and Diriyah Horizon | Low |  | 2026-05-14 |  |  | In Progress |  | 48.5 | 39.5 | [5 empty] | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon |  | 19ed0e33d52ddeef
Diriyah Gate Development Authority | www.dgda.gov.sa | DGDA Maintenance June 2026 | Low |  | 2026-05-01 |  |  | In Progress |  | ⚠ Missing Effort | 29.95 | [5 empty] | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 |  | 19ed0e4ad0604eff
Diriyah Gate Development Authority | www.dgda.gov.sa | National Design System (DGA) | Medium | Abhicheke | 2026-01-03 | 2026-02-25 | 2026-02-25 | Under Review & Testing | UAT | 202.5 | 184.5 |  | Main project development has been underway since February 25th. Although the National Design phase was on hold as of February 12th, we received confirmation to initiate work on April 7th. The team was requested to share a first draft by April 15th, and a preview link was sent to the DGDA team on April 16th. We reshared the homepage with them on April 17th and are currently awaiting feedback to proceed with the remaining pages. A review meeting was scheduled for April 28th, and we are now awaiting a post-meeting update from the DGDA. We have received the approve the other page 07 May the team will start working on rest of the page Based on Saad He Approved and proceed with everything. Regarding the quality assurance phase, a new joiner from Saad's team will be responsible for cross-checking the work once development is complete (11 May), | Send the email to Saad and get the clarification for the icon | https://feat-national-design-system-v16-main.d38541r9nlp4br.amplifyapp.com/ | DGA timeline Development for DGA guidelines and Website Content | [Dev Tracker] TASK UPDATE: National Design System (DGA) |  | 19ed187f836ec16f
Diriyah Gate Development Authority | www.dgda.gov.sa | Quamatic Integration | Low |  | 2026-03-16 |  |  | On Hold / Blocked |  | 9 | 3 |  | Following our March 16th call, we requested the UAT URL for testing. Although we suggested a single endpoint on April 2nd, the team confirmed this was not feasible. On April 8th, we followed up regarding current access restrictions and are awaiting Dayel’s guidance on Qmatic access. Per yesterday's meeting, Saad needs to provide confirmation; until then, API integration is on hold while we focus on other changes and the NDS. The API integration is currently blocked by IP restrictions. We are also awaiting the Qmatic API documents, as the previous files were inaccessible. Finally, we requested VPN access on March 31st and are waiting for the necessary APIs from the Qmatic team | API integration paused due to access constraints. Saad to advise once sorted. 503 Service Unavailable SMS API Working Good Waiting for Production URL The production URL auth is failed |  |  | [Dev Tracker] TASK UPDATE: Quamatic Integration |  | 19e3488d3a8b0c0a
Diriyah Gate Development Authority | www.dgda.gov.sa | Emergency services form | Low | Abhicheke | 2026-03-12 |  |  | On Hold / Blocked |  | 8.75 | 8.75 |  | Since completing the form and OTP integration on March 12th, we have been working through several integration blockers. The current SMS API is restricted to Arabic numbers, which prevents us from finalizing the global OTP functionality. Additionally, while GIS token generation is successful, we are encountering an 'Invalid URL' error when testing KMZ files. We held a technical call on April 28th to address why the third API remains non-functional. We are currently awaiting follow-up responses from Waleed and Kamran regarding the GIS fix and the SMS production credentials, respectively. | 3rd Api not working 1st and 2nd Api Working For SMS API Production URL I tried both No Auth and Basic Auth username - ffffa747-d38b-3971-83e5-facd68d4fd40 Password - SAPCPI_SMS__API_OAUTH_e650058 but it show unauthorized_client |  |  | [Dev Tracker] TASK UPDATE: Emergency services form | SMS Api Need to Implement | 19e3488fe21c9b07
Diriyah Gate Development Authority | www.dgda.gov.sa | Eservices and Qmatic Webpages | Low |  |  |  |  | In Progress | Local | 0.25 | 0.25 |  | Team has reviewed the websites and shared the estimation with Saad on 19/04. AW backend access to review in detail, request raised with Saad. Need to schedule a call with Qmatic team 29/04 |  |  |  | [Dev Tracker] TASK UPDATE: Eservices and Qmatic Webpages |  | 19ddd4c15de487fd
Diriyah Gate Development Authority | www.dgda.gov.sa | Research Inquiry Forms | Low |  | 2026-04-21 | 2026-04-22 |  | Waiting for Client Input | Staging | 9.25 | 8.75 |  | Team has initiated the work on the form; preview link will be shared on 22/04. Preview link shared with Dayel on 23/04. CRM integration pending with DGDA. | Need Arabic content and Description Form need to map on c4c | https://main.d3jcmxm4xwijj.amplifyapp.com/en/contact-us/research-inquiry |  | [Dev Tracker] TASK UPDATE: Research Inquiry Forms |  | 19dbe08a710e8032
Diriyah Gate Development Authority | www.dgda.gov.sa | DGDA Application PT Finding | Low |  |  |  |  | Local |  | 0.25 | 0.25 |  | Email received from Faisal on 21/04 to update the Next.js version of the DGDA website. AW confirmation from Saad to proceed further. |  |  |  | [Dev Tracker] TASK UPDATE: DGDA Application PT Finding |  | 19ddd4bbfdf4fdb8
Diriyah Gate Development Authority | www.dgda.gov.sa | EMS Project | Low |  |  |  |  | In Progress
Diriyah Gate Development Authority | www.dgda.gov.sa | DGDA EMS Infra set up | Low | Moswin |  |  |  | Pipeline / To Do | Local | No Subtasks | No Subtasks | [5 empty] | TASK UPDATE: DGDA EMS Infra set up |  | 19ec4f56005ae817
FIA | farnboroughairshow.com | Expo Platform Changes | Low | Sowndar | 2026-04-07 | 2026-04-10 |  | Under Review & Testing | Staging | 50 | 23.95 |  | The Expo platform team's questions have been clarified and shared. We are currently awaiting a response. |  |  | 1) Request for Timeline – FIA Application API Requirement 2) FIA Application - API Process & Data Flow Documentation – Review and Feedback Requested | [Dev Tracker] TASK UPDATE: Expo Platform Changes |  | 19ecc0b18b5671d1
FIA | farnboroughairshow.com | FIA Website – VAPT Assessment Timeline | Low |  |  |  |  | Pipeline / To Do | Local | No Subtasks | No Subtasks |  |  |  |  | FIA Website – VAPT Assessment Timeline | [Dev Tracker] TASK UPDATE: FIA Website – VAPT Assessment Timeline |  | 19e348987fbfe133
FIA | events.farnboroughinternational.org | Update 8.18.5 to Umbraco 13 | Low | Sai |  |  |  | Pipeline / To Do | Local | No Subtasks | No Subtasks |  | Awating Client Input |  |  |  | [Dev Tracker] TASK UPDATE: Update 8.18.5 to Umbraco 13 |  | 19e3489b196ae0f1
FIA | farnboroughairshow.com | FIA Maintenance June 2026 | Low |  | 2026-05-01 |  |  | In Progress | Local | 8 | 8 | [5 empty] | [Dev Tracker] TASK UPDATE: FIA Maintenance May 2026 |  | 19e7db8b3ccc4784
FIA | farnboroughairshow.com | Umbraco Update 13 to 17 | Low |  |  |  | 2026-09-01 | Pipeline / To Do | Local | No Subtasks | No Subtasks | [5 empty] | TASK UPDATE: Umbraco Update 13 to 17
Vajra Global | vajraglobal.com | Updated SEO Automation BRD | Low | Sowndar |  |  |  | In Progress | Local | No Subtasks | No Subtasks |  | Indexing, Keyword research, Competitor Analysis API Credits, Techinical Feasbility Token Common feature |  |  |  | [Dev Tracker] TASK UPDATE: Updated SEO Automation BRD |  | 19df666b384b7115
Vajra Global | vajraglobal.com | Seo Automation Tool | Low | Rackesh Kumaran |  |  |  | In Progress | Local | 148 | 150 | [5 empty] | TASK UPDATE: Seo Automation Tool
Vajra Global | vajraglobal.com | Server Monitoring Implementation Plan | Low | Moswin |  |  |  | In Progress | Local | [7 empty] | TASK UPDATE: Server Monitoring Implementation Plan

## Pending Changes (hidden)
Timestamp | Subject | MainRowIndex
2026-05-15 13:48 | Project Update: Open data form Phase - 2 | 22
2026-05-15 13:48 | Project Update: Open data form Phase - 2 | 22
2026-05-15 14:08 | National Design System (DGA) | 10
2026-05-15 14:08 | National Design System (DGA) | 10
2026-05-15 14:21 | Project Update: Open data form Phase - 2 | 10
2026-05-15 14:21 | Project Update: Open data form Phase - 2 | 10
2026-05-15 14:21 | Project Update: Open data form Phase - 2 | 10
2026-05-15 14:21 | Project Update: Open data form Phase - 2 | 10
2026-05-15 15:03 | National Design System (DGA) | 11
2026-05-15 15:03 | National Design System (DGA) | 11
2026-05-15 15:03 | National Design System (DGA) | 11
2026-05-15 15:03 | National Design System (DGA) | 11
2026-05-15 15:05 | National Design System (DGA) | 11
2026-05-15 15:05 | National Design System (DGA) | 11
2026-05-15 16:40 | Project Update: Image and Video Edit On Post | 7
2026-05-15 16:40 | Project Update: Image and Video Edit On Post | 7
2026-05-15 16:40 | National Design System (DGA) | 11
2026-05-15 16:40 | National Design System (DGA) | 11
2026-05-15 16:40 | National Design System (DGA) | 11
2026-05-15 16:40 | National Design System (DGA) | 11
2026-05-15 16:40 | National Design System (DGA) | 11
2026-05-15 16:40 | National Design System (DGA) | 11
2026-05-15 16:41 | National Design System (DGA) | 11
2026-05-15 16:41 | National Design System (DGA) | 11
2026-05-15 16:41 | National Design System (DGA) | 11
2026-05-15 16:41 | National Design System (DGA) | 11
2026-05-15 16:41 | National Design System (DGA) | 11
2026-05-15 16:41 | National Design System (DGA) | 11
2026-05-15 16:42 | National Design System (DGA) | 11
2026-05-15 16:42 | National Design System (DGA) | 11
2026-05-15 17:34 | National Design System (DGA) | 11
2026-05-15 17:34 | National Design System (DGA) | 11
2026-05-15 17:41 | National Design System (DGA) | 11
2026-05-15 17:41 | National Design System (DGA) | 11
2026-05-15 18:06 | National Design System (DGA) | 11
2026-05-15 18:06 | National Design System (DGA) | 11
2026-05-16 07:23 | Project Update: Demo Page | 2
2026-05-16 07:23 | Project Update: Demo Page | 2
2026-05-16 07:27 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:27 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:27 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:27 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:28 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:28 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:28 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:28 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:28 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:28 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:28 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 07:28 | Project Update: Events Application and Diriyah Horizon | 11
2026-05-16 10:51 | Project Update: Adobe Experence Manger and workflow | 24
2026-05-16 10:51 | Project Update: Adobe Experence Manger and workflow | 24
2026-05-16 23:24 | National Design System (DGA) | 13
2026-05-16 23:24 | National Design System (DGA) | 13
2026-05-16 23:26 | National Design System (DGA) | 13
2026-05-16 23:26 | National Design System (DGA) | 13
2026-05-16 23:26 | National Design System (DGA) | 13
2026-05-16 23:26 | National Design System (DGA) | 13
2026-05-17 09:38 | Project Update: Demo Page | 2
2026-05-17 09:39 | Project Update: Demo Page | 2
2026-05-17 09:42
2026-05-17 10:51 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-17 11:14 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-17 11:14 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-17 11:37 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-17 11:37 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-18 09:36 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 09:36 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 17:43 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:23 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-18 19:23 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-18 19:30 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:30 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:31 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:31 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:31 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:40 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:40 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:41 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:41 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:41 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:41 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:41 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-18 19:42 | [Dev Tracker] TASK UPDATE: Open data form Phase - 2 | 10
2026-05-20 10:08 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-20 10:10 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-20 10:10 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-20 10:10 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-20 10:12 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-20 10:12 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-05-20 10:12 | [Dev Tracker] TASK UPDATE: Intranet Tech Queries | 3
2026-05-20 15:29 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 10
2026-05-20 15:29 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 10
2026-05-20 19:10 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 16:25 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 16:25 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 16:25 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 18:21 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 19:22 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 19:22 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 19:23 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 19:23 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 19:23 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 19:23 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-22 19:23 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 14:22 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 18:49 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 19:37 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 19:37 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 19:37 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 19:37 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 19:37 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 21:08 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-25 21:08 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-26 09:47 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-26 09:47 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-05-26 10:27 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 7
2026-05-26 11:21 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 11
2026-05-26 11:21 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 11
2026-05-26 11:23 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 11
2026-05-26 12:15 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 11
2026-05-26 12:15 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 11
2026-05-26 12:44 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 11
2026-05-26 18:16 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-05-26 22:25 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-05-27 10:05 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-05-27 17:02 | [Dev Tracker] TASK UPDATE: Events Application and Diriyah Horizon | 11
2026-05-29 12:11 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-05-29 12:13 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-05-29 17:11 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-05-29 17:12 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-06-01 17:13 | TASK UPDATE: Case Study Page May 2026 | 10
2026-06-01 17:13 | TASK UPDATE: Case Study Page May 2026 | 10
2026-06-01 20:18 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 7
2026-06-01 20:18 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 7
2026-06-01 20:18 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 7
2026-06-01 20:18 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 7
2026-06-01 20:20 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-01 20:20 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-02 10:04 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-02 14:09 | TASK UPDATE: DGDA EMS Infra set up | 23
2026-06-02 14:51 | TASK UPDATE: Case Study Page May 2026 | 10
2026-06-02 14:51 | TASK UPDATE: Case Study Page May 2026 | 10
2026-06-02 17:22 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-06-02 17:22 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-06-02 17:23 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-06-02 19:16 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-02 19:16 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-02 19:17 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 7
2026-06-02 19:19 | TASK UPDATE: Seo Automation Tool | 30
2026-06-02 19:19 | TASK UPDATE: Seo Automation Tool | 30
2026-06-02 19:20 | TASK UPDATE: Seo Automation Tool | 30
2026-06-02 19:20 | TASK UPDATE: Seo Automation Tool | 30
2026-06-03 19:28 | TASK UPDATE: Seo Automation Tool | 30
2026-06-03 19:28 | TASK UPDATE: Seo Automation Tool | 30
2026-06-03 19:31 | TASK UPDATE: Seo Automation Tool | 30
2026-06-03 19:31 | TASK UPDATE: Seo Automation Tool | 30
2026-06-03 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-03 19:34 | TASK UPDATE: Seo Automation Tool | 30
2026-06-03 19:34 | TASK UPDATE: Seo Automation Tool | 30
2026-06-04 10:13 | TASK UPDATE: Content Update June | 5
2026-06-04 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-04 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-04 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-04 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-04 19:34 | TASK UPDATE: Seo Automation Tool | 30
2026-06-04 19:34 | TASK UPDATE: Seo Automation Tool | 30
2026-06-04 20:05 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-05 10:00 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-05 14:04 | TASK UPDATE: Content Update June | 5
2026-06-05 16:51 | TASK UPDATE: Content Update June | 5
2026-06-05 16:52 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-05 17:27 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-05 19:28 | TASK UPDATE: Seo Automation Tool | 30
2026-06-05 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-05 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-05 19:34 | TASK UPDATE: Seo Automation Tool | 30
2026-06-05 19:34 | TASK UPDATE: Seo Automation Tool | 30
2026-06-05 19:34 | TASK UPDATE: Seo Automation Tool | 30
2026-06-05 19:35 | TASK UPDATE: Seo Automation Tool | 30
2026-06-09 09:45 | TASK UPDATE: Seo Automation Tool | 30
2026-06-09 09:45 | TASK UPDATE: Seo Automation Tool | 30
2026-06-09 09:46 | TASK UPDATE: Seo Automation Tool | 30
2026-06-09 09:46 | TASK UPDATE: Seo Automation Tool | 30
2026-06-09 10:07 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-09 10:07 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-09 19:32 | TASK UPDATE: Seo Automation Tool | 30
2026-06-09 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-09 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-09 19:33 | TASK UPDATE: Seo Automation Tool | 30
2026-06-10 14:39 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-10 14:39 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-10 14:39 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-10 14:39 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-10 18:20 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 17
2026-06-11 09:49 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 09:51 | TASK UPDATE: Content Update June | 4
2026-06-11 09:51 | TASK UPDATE: Content Update June | 4
2026-06-11 09:51 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 09:51 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 09:51 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 09:51 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:52 | TASK UPDATE: Dev Update June | 6
2026-06-11 09:54 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 09:59 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-06-11 10:01 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 23
2026-06-11 10:01 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 23
2026-06-11 18:02 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 23
2026-06-11 18:02 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 23
2026-06-11 18:02 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-11 18:02 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-12 09:46 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:46 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:46 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:46 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:46 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:47 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:47 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:47 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:47 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:50 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:50 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:50 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:50 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:53 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:53 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:54 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 09:54 | TASK UPDATE: Seo Automation Tool | 28
2026-06-12 10:21 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-12 10:21 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 16
2026-06-12 10:21 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 23
2026-06-12 10:26 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 23
2026-06-12 10:33 | TASK UPDATE: Case Study Page May 2026 | 7
2026-06-12 10:39 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 21
2026-06-12 10:39 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 21
2026-06-12 10:40 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 21
2026-06-12 10:40 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 21
2026-06-12 10:45 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 21
2026-06-13 06:14 | TASK UPDATE: Content Update June | 4
2026-06-13 06:16 | TASK UPDATE: Dev Update June | 6
2026-06-13 06:17 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 14
2026-06-15 09:31 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-15 09:32 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-15 09:34 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:34 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:34 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:34 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:34 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:34 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:34 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:35 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:36 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 09:36 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 10:18 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-15 10:18 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-15 10:19 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-15 18:15 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-06-15 18:15 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-15 18:15 | TASK UPDATE: Dev Update June | 6
2026-06-15 19:25 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-15 19:25 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-15 19:28 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 19:28 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 19:28 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 19:28 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 19:28 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 19:28 | TASK UPDATE: Seo Automation Tool | 26
2026-06-15 19:34 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-16 18:11 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-06-16 18:11 | [Dev Tracker] TASK UPDATE: Demo Page | 2
2026-06-16 18:34 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-06-16 18:35 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-06-16 18:35 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-06-16 19:08 | TASK UPDATE: Seo Automation Tool | 27
2026-06-16 19:08 | TASK UPDATE: Seo Automation Tool | 27
2026-06-16 19:11 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-06-16 19:11 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-06-16 19:12 | TASK UPDATE: Dev Update June | 6
2026-06-16 19:12 | TASK UPDATE: Dev Update June | 6
2026-06-16 19:12 | TASK UPDATE: Seo Automation Tool | 27
2026-06-16 19:12 | TASK UPDATE: Seo Automation Tool | 27
2026-06-16 19:13 | TASK UPDATE: Seo Automation Tool | 27
2026-06-16 19:13 | TASK UPDATE: Seo Automation Tool | 27
2026-06-16 19:14 | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 | 12
2026-06-16 19:28 | TASK UPDATE: Seo Automation Tool | 27
2026-06-16 19:28 | TASK UPDATE: Seo Automation Tool | 27
2026-06-17 10:13 | TASK UPDATE: Seo Automation Tool | 27
2026-06-17 10:13 | TASK UPDATE: Seo Automation Tool | 27
2026-06-17 10:13 | TASK UPDATE: Seo Automation Tool | 27
2026-06-17 10:52 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 13
2026-06-17 10:58 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 10:59 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 10:59 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 10:59 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 10:59 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 10:59 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:00 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:01 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:01 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:01 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:01 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:01 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:02 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:02 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:02 | [Dev Tracker] TASK UPDATE: Adfactor Admin Dashboard | 5
2026-06-17 11:12 | TASK UPDATE: Seo Automation Tool | 27
2026-06-17 11:12 | TASK UPDATE: Seo Automation Tool | 27
2026-06-17 11:12 | TASK UPDATE: Seo Automation Tool | 27
2026-06-17 12:59 | [Dev Tracker] TASK UPDATE: Restore Work.Adfactor | 8
2026-06-17 13:00 | [Dev Tracker] TASK UPDATE: Expo Platform Changes | 21
2026-06-17 13:00 | [Dev Tracker] TASK UPDATE: FIA Website – VAPT Assessment Timeline | 22
2026-06-17 13:00 | [Dev Tracker] TASK UPDATE: Update 8.18.5 to Umbraco 13 | 23
2026-06-17 13:00 | [Dev Tracker] TASK UPDATE: FIA Maintenance May 2026 | 24
2026-06-17 13:00 | TASK UPDATE: Umbraco Update 13 to 17 | 25
2026-06-17 13:01 | [Dev Tracker] TASK UPDATE: FIA Website – VAPT Assessment Timeline | 22
2026-06-17 13:01 | [Dev Tracker] TASK UPDATE: Updated SEO Automation BRD | 26
2026-06-17 13:01 | TASK UPDATE: Seo Automation Tool | 27
2026-06-17 13:01 | TASK UPDATE: Server Monitoring Implementation Plan | 28
2026-06-17 13:08 | TASK UPDATE: Open data form Phase - 2 | 9
2026-06-17 13:13 | [Dev Tracker] TASK UPDATE: National Design System (DGA) | 12
2026-06-17 13:14 | [Dev Tracker] TASK UPDATE: Emergency services form | 14
2026-06-17 13:14 | [Dev Tracker] TASK UPDATE: Research Inquiry Forms | 16
2026-06-17 19:16 | TASK UPDATE: Seo Automation Tool | 26
2026-06-17 19:16 | TASK UPDATE: Seo Automation Tool | 26
2026-06-18 10:44 | [Dev Tracker] TASK UPDATE: FIA Maintenance May 2026 | 23
2026-06-19 09:35 | [Dev Tracker] TASK UPDATE: Eservices and Qmatic Webpages | 15
2026-06-19 10:04 | TASK UPDATE: Seo Automation Tool | 26
2026-06-19 10:04 | TASK UPDATE: Seo Automation Tool | 26
2026-06-19 10:04 | TASK UPDATE: Seo Automation Tool | 26
2026-06-19 10:04 | TASK UPDATE: Seo Automation Tool | 26
2026-06-19 10:04 | TASK UPDATE: Seo Automation Tool | 26

## Completed Tracker
Project Name | Website Url | Task | Priority | Assign | S Date | E Date | As Per WO | Status | Env | Efforts | Actual Effort | Informed | Comment | Dependency Detail | Page Url | Mail Subject | Internal Mail Subject
Adfactors PR Private Limited | intranet.adfactorspr.com | Holiday List Page | Low | Parthiban | 2025-12-04 | 2025-12-12 |  | Completed | Production | 50 |  | 15 | Page Develoment has completed asked the content for this
Diriyah Gate Development Authority | www.dgs.sa | DGS Registration form | Low | Sowndar | 2025-11-19 | 2025-11-19 |  | Completed | Production | 20 |  |  | The C4C team is currently conducting the review and testing of the form within SAP. We sent a follow-up yesterday, as they had anticipated completing this process today (December 2, 2025). Upon the conclusion of testing and client sign-off, the next step is immediate deployment to the live environment. However, the team has decided they do not wish to proceed with the SAP integration; instead, they prefer to continue using the existing process of fetching email details and storing them in an Excel file.
FIA | farnborough.com | Update the form date format | Low | Abhicheke | 2025-12-08 | 2025-12-08 |  | Completed | Production |  |  |  | Done Moved To Production
Diriyah Gate Development Authority | www.dgs.sa | SEO Assets for DGS Site | Low | Regan | 2025-11-19 |  |  | Completed |  |  |  |  | We have shared the document with the client on December 1, 2025 and are now awaiting their reply and approval. 2nd follow-up sent on December 8, 2025. Awaiting client response Once they approve the changes and provide the Arabic content, we will update the DGS live environment. Since the the event has complete we consider this task has closed |  |  | DGS Microsite | SEO Assets for DGS Site (Discussed 11-11-2025)
Diriyah Gate Development Authority | www.dgs.sa | Missing Content on DGS Page | Low | Regan |  |  |  | Completed |  |  |  |  | We sent a follow-up on December 1, 2025, second follow-up , December 8, 2025. Since the the event has complete we consider this task has closed
Diriyah Gate Development Authority | www.dgda.gov.sa | Initial Wireframes | Low | Balaji | 2025-12-15 | 2025-12-17 |  | Completed
Diriyah Gate Development Authority | www.dgda.gov.sa | Forms Character Limit for DGDA and DGS | Low | Regan | 2025-12-15 | 2025-12-23 |  | Completed | Production |  |  |  | Dayel has agreed to proceed with the form limit, and the team has started working on it. |  |  | Validations required DGDA forms
Diriyah Gate Development Authority | www.dgda.gov.sa | DGDA Version Update | Low | Abhicheke | 2025-12-15 | 2025-12-19 | 2025-12-23 | Completed | Production |  |  |  | Move the changes to live. 14.2.25 – 15.5.25
Adfactors PR Private Limited | intranet.adfactorspr.com | Adfactor Home Page feature Phase 1 | Low | Parthiban | 2025-12-15 | 2025-12-17 |  | Completed | Production | 20
DGS | www.dgs.sa | DGS Home | High | Abhicheke | 2025-12-24 | 2026-01-06 | 2025-12-31 | Completed | Production |  |  |  | Client Approved on 05 Jan 2025 and updated the changes on live |  |  | DGS Microsite
Diriyah Gate Development Authority | www.dgda.gov.sa | Hide Media From Search Console | Low | Regan | 2025-12-10 | 2025-12-11 |  | On Hold / Blocked |  |  |  |  | David needs to get back to us. As regan mentioned david was just asked like why this is showing
Adfactors PR Private Limited | intranet.adfactorspr.com | Holiday List Page | Low | Parthiban |  |  |  | Completed | Production |  |  |  | Changes has done by Adfactor Team
FIA | farnboroughairshow.com | Phase 2 Brand GuidLine Change POI | Low | Abhicheke | 2025-12-03 | 2026-01-21 |  | Completed | Production | 50 |  |  | Done all the changes and Moved to Production on 21 Dec 2025. |  |  | Pioneers of Tomorrow - Brand Updates
FIA | farnboroughairshow.com | FIA Changes on Show Theme | Low | Abhicheke | 2025-12-10 | 2026-01-19 |  | Completed | Production | 10 |  |  | Done all the changes and Moved to Production on 19 Dec 2025.
FIA | farnborough.com | Farnborough Canceled Event | Low | Parthiban | 2025-12-17 | 2026-01-19 | 2025-12-23 | Completed | Production | 10 |  |  | Done all the changes and Moved to Production on 19 Dec 2025.
FIA | farnboroughairshow.com | FIA Version Update | Low | Abhicheke | 2026-01-05 | 2026-01-19 |  | Completed | Production | 30 |  |  | Version Update 13.9.1 to 13.13.0 in FarnboroughAirshow Updated the Umbraco version 13.10.0 to 13.13.0 in Farnborough Vennue
FIA | farnboroughairshow.com | POT Feed Back changes | Low | Abhicheke | 2026-01-09 | 2026-01-19 | 2026-01-12 | Completed | Production
FIA | farnboroughinternationalstudios.com | Studio Site Version Update | Low | Abhicheke | 2026-01-19 | 2026-01-21 |  | Completed | Production |  |  |  | Done all the changes and Moved to Production on 21 Dec 2025.
FIA | farnboroughinternationalstudios.com | New Testimonial Page | Low | Abhicheke | 2026-01-29 | 2026-02-02 | 2026-02-02 | Completed | Production |  |  |  | Done all the changes and Moved to Production on 02 Feb 2026
Diriyah Gate Development Authority | www.dgda.gov.sa | Form Failed Feb-2026 | Low | Abhicheke | 2026-02-04 | 2026-02-05 | 2026-02-05 | Completed | Production |  |  |  | We recommend the to reduce the file size from 5mb to 2mb since the size of payload is very high after change this it start working without any issue
FIA | farnboroughairshow.com | Phase 1 Brand GuidLine Change | Low | Abhicheke | 2025-11-21 | 2026-01-21 | 2025-12-01 | Completed | Production | 70 |  | 20 | Done all the changes and Moved to Production on 21 Dec 2025. However the recent sub task(Came after 21 Dec 2025) which we need to approve to move live. Waiting for Client Approval
Adfactors PR Private Limited | intranet.adfactorspr.com | Adfactor Home Page feature Phase 2 | Low | Parthiban |  |  |  | Completed | Production
Diriyah Gate Development Authority | www.dgda.gov.sa | Summer Program Page | Low | Abhicheke | 2025-12-02 | 2025-12-11 |  | Closed – Billable | Staging | 30 |  |  | DGDA has updated the Arabic site content and finalized development. Staging and CRM integration were completed on Dec 23rd. Per Dayel’s instructions, the schedule is postponed to Nov 2026, and this task is now considered closed. As discussed with Saad Event postponned to November 2026, will close the activity. |  | Payload: Diriyah Horizons - Leadership Programme - Fields Name Payload | Summer Program Page | Arabic Content and Missing Form Fields for Summer Camp Page
Diriyah Gate Development Authority | www.dgda.gov.sa | Leadership component | Low | Abhicheke | 2026-02-05 | 2026-02-12 |  | Completed | Production |  |  |  | We updated the Leadership Component design, including new content and imagery, and submitted it on 09 Feb. Per the client's request on 12 Feb, However, per client instructions on 12 Feb, the final launch is on hold pending direction from their top management. Work completed on 9 Feb, CEO message live 24 Feb |  |  | Leadership component Development for DGA guidelines and Website Content
Adfactors PR Private Limited | intranet.adfactorspr.com | Academy Page | Low | Parthiban | 2026-02-05 | 2026-02-12 |  | Completed | Production |  |  |  | The page was completed and moved to staging. A follow-up was sent on 10/02. The team gave another set of V2 changes on 11/02, which were completed and shared with the client on 13/02. The asked to add few other section we added and share it with client on 19 Feb Few other changes requested by Client AW Completed and Moved To Production on 09 March |  |  | New Intranet Page - Adfactors Academy
Adfactors PR Private Limited | intranet.adfactorspr.com | Author Name on Articale Page | Low |  | 2026-02-16 | 2026-02-16 | 2026-02-20 | Completed | Production |  |  |  | Give two option to the Client waiting for Input from them Completed and Moved To Production on 09 March
Adfactors PR Private Limited | intranet.adfactorspr.com | AF Server Changes | Low | Sowndar | 2026-02-12 | 2026-02-13 | 2026-02-19 | Completed | Production |  |  |  | Team is start working this on 13 Feb. The team need cross testing the full website FTP The changes has done eveything is working ask expected. Completed Three website need to move one more site once it is done point to new server |  |  | Request for Review – New Intranet Website Before Migration
Diriyah Gate Development Authority | www.dgda.gov.sa | Founding day 2026 | Low |  | 2026-02-18 | 2026-02-19 | 2026-02-27 | Completed | Staging |  |  |  | Compleleted and share it with client on 20 Feb. AW for Feedback. Since the event is finished we need to rised the billing only eventhout it is not moved to live |  |  | Founding Day 2026
Adfactors PR Private Limited | intranet.adfactorspr.com | Academy Page - 2 | Low | Parthiban | 2026-02-17 | 2026-02-17 | 2026-02-20 | Completed | Production |  |  |  | Updated the content from live to staging, removed tab spacing where empty, and completed the share with the client on 17 March |  |  | New Intranet Page - Adfactors Academy
Diriyah Gate Development Authority | www.dgda.gov.sa | Form Tracking GA | Low | Ranjith | 2025-11-14 | 2025-12-30 |  | Completed | Production | 30 |  |  | Ranjith confirmed the implementation is functional and has updated the client. Following the DGDA review AW response from David. Since i spoke to Regan he |  |  |  | Regarding the DGDA Form changes | Improve this
FIA | farnboroughairshow.com | FIA AGF Page changes | Low | Parthiban | 2026-01-12 | 2026-01-13 | 2026-01-13 | Completed | Production | 6 |  |  | Completed and share it with Clinet. The client mentioned the will update the content and do the changes
FIA | farnboroughairshow.com | Feb Maintenance changes - 2026 | Low |  | 2026-02-25 | 2026-02-25 | 2026-02-27 | Completed | Production |  |  |  | Completed
FIA | farnboroughairshow.com | MPU Functionality | Low |  | 2026-03-09 | 2026-03-10 | 2026-03-10 | Completed | Production
FIA | farnboroughairshow.com | FIECC - Landing page | Low |  | 2026-03-13 | 2026-03-16 | 2026-03-16 | Completed | Production |  |  |  | Shared with Client on 16 March However they haven't white list the IP from thir end for staging so they couldn't access the website so the will do the check once white list Moved To Production 24 March 1.Currently, we have Lorem Ipsum on the live site. 2.Currently, we have a dummy banner and gallery images on the live site. 3.Currently, we do not have the Checklist ID for the form; the submitted data will be sent to event-enquiries@farnborough.com. 4.Currently, we have a dummy sample PDF, which will be downloaded after someone submits the form.
Diriyah Gate Development Authority | www.dgda.gov.sa | AlMedad Form | [5 empty] | Completed | Production |  |  |  | AlMedad Form Submission error due to arabic content on input value |  |  | [NEW TASK] [DGDA] SignUp Form Button Changes
FIA | aerospaceglobalforum.com | Update 10.8.7 to Umbraco 13 | Low | Sai |  |  |  | Closed / Cancelled |  |  |  |  | Awating Client Input |  |  |  | Website Update - Phase 1.
FIA | farnboroughairshow.com | FIA.com - Marketing Toolkit Page |  | Parthiban | 2026-04-01 | 2026-04-09 |  | Completed | Production | 13.5 | 1.5 |  | Done the changes and moved to staging AW for Customer feed back |  |  |  | [NEW TASK] [FIA] - FIA.com - Marketing Toolkit Page
Diriyah Gate Development Authority | www.dgda.gov.sa | Urban Living | Low | Regan |  |  |  | Closed – Billable |  | No Subtasks | No Subtasks |  | Map approach shared with DGDA on 25/11, AW feedback. Also we are waiting to hear from UMA team on the section mapping for Urban Living. Waiting for UMA section mapping As discussed, we will proceed with the closure as there are no plans for now to launch this page.
Diriyah Gate Development Authority | www.dgda.gov.sa | 360 Degree Image new website | Low | Regan |  |  |  | Closed / Cancelled |  | 0 | 0 |  | Infra - 70Hrs Developement and testing - 120Hrs David said on December 1, 2025 he will come back to us
Diriyah Gate Development Authority | www.dgda.gov.sa | Content Update – Feb 2026 | Medium | Abhicheke | 2026-02-02 | 2026-02-05 | 2026-02-05 | Closed – Billable | Production | 0 | 0 |  | Completed and Initial preview links were distributed on 5 February. Following this, Saad requested a hold on 12 February pending executive direction.Preview shared, waiting sign-off from top management. To Be Billed in Feb - April 2026 |  |  | Development for DGA guidelines and Website Content | Content Update Required for DGDA
Diriyah Gate Development Authority | www.dgda.gov.sa | XMCC Migration | High | Regan |  |  |  | Closed / Cancelled | Production | 0 | 0 |  | Sitecore team to review the exisitng code for any impacts, AW update. Github access granted to them on 11/12. Last update is that migration planned for March 31st. Follow up sent on 11/2 Awaiting update from migration team. Awaiting for update from DGDA to initiate as we have recived confirmation to work on DGA (NDS) As Per 13 April Meeting Saad to confirm IT strategy on CH1. Migration cannot run in parallel with DGA. XMCC Migration Dropped |  |  |  | Sitecore Migration CH1 to XMCC | Need to follow up
Diriyah Gate Development Authority | www.dgda.gov.sa | Open data form | Low | DGDA | 2025-11-13 |  |  | Closed – Billable | Production | No Subtasks | No Subtasks |  | DGDA Website updates - SDAIA Compliance Development work is finished. The task has been handed over to Majd’s team (C4C) for testing and SAP form configuration. Deployment will proceed once their work and the C4C setup are finalized. Follow up sent to CRM team on 1 Feb. Completed by CRM team – awaiting confirmation As discussed 13 April, we will proceed with the closure as there are no plans from the team to proceed with live. Billed on June - Aug 2025 |  | Payload: Data Request Open Data Form - Fields Name Payload |  | Open Data Form |  | 19dd348c2296a417
Diriyah Gate Development Authority | www.dgda.gov.sa | Uma Form | Low | Abhicheke | 2025-12-24 |  |  | Closed – Billable | Staging | 0 | 0 |  | Development on all ER forms was completed and delivered on 6/1. The team is currently working on the Arabic content for the approved forms, with an ETA of 18/1. The forms were shared with the CRM team on 7/1; we are awaiting a response to proceed with integration. David sent a follow-up to the team, and an additional follow-up was sent on 2 Feb (still awaiting response). We Suggest To Set the call and discuss this. Forms delivered, waiting CRM integration response Saad asked us to hold and move to closed |  |  | DGDA Forms meeting with Technology + UMA + CRM | Completed Uma Forms ¦ Questions Regarding Missing Content
Diriyah Gate Development Authority | www.dgda.gov.sa | DevSecOps Onboarding (Intoducing security scripts in our GitHub pipelines) DGDA DevSecOps pipelines set up | Low |  | 2025-12-18 |  |  | Completed | Production | No Subtasks | No Subtasks |  | Alwosta submitted the Phase 1 questionnaire to DevSecOps on 22/12. We are pending an update from the DGDA Infra team before starting Phase 2. Following the delivery of prerequisites on 13/01 and a follow-up on 25/01, we coordinated with Busma to initiate the server setup. Ticket RITM0037232 was successfully raised today, 02 Feb Phase-2 pending Infra team approval Blocker: Saad to obtain IT update/clearance for Alwosta to run security scripts. |  |  |  | Status Update on DGDA DevSecOps Pipelines Setup
Diriyah Gate Development Authority | www.dgda.gov.sa | Cybersecurity Compliance Self-Assessment | Low |  |  |  |  | Completed | Production | 4 | 0 |  | Alwosta team has reviewd the document and updated wherever details can be added. AW claification on few sections, ETA - 9/3 The document was shared by Basmah for review, we have shared our feedback with them. No further action required. We will close it from our end. |  |  |  | Project Update: Cybersecurity Compliance Self-Assessment
Diriyah Gate Development Authority | www.dgda.gov.sa | Whatsapp integration | Low |  |  |  |  | Closed – Not Proceeding |  | No Subtasks | No Subtasks |  | We are identifying vendors and have calls scheduled for 9 March. Following our discussion, Regan will coordinate with the client to gather further details and Enquire with the vendor SMS API MobiShastra API.https://www.mobishastra.com/sms-api.php Blocker: Waiting for AW confirmation to proceed further (sent 9/4). *ETA post-approval. | Client will find the vendor and come back to us |  |  | Project Update: Whatsapp integration |  | 19dcd4a4dcd3b025 | 2026-04-28 16:32
FIA | farnboroughairshow.com | SignUp Changes on FIA |  | Abhicheke | 2026-04-02 | 2026-04-02 | 2026-04-02 | Completed | Production | 2.5 | 2.5 |  | Once the client's content has been updated, we will proceed with the live deployment. |  |  |  | [NEW TASK] [FIA] SignUp Form Button Changes |  | 19dd34b868f7cea6 | 2026-04-30 11:25
FIA | farnboroughairshow.com | FIA Sign-Up Form Integration with Engage | Low | Parthiban | 2026-03-31 | 2026-04-09 |  | Under Review & Testing | Production | 13 | 1 |  | Asked the Key For FIA |  |  | FIA API Method Update – Revised Effort & Cost Estimation | Technical Details – FIA Sign-Up Form Integration with Engage |  | 19dcd55452c6a307 | 2026-04-30 11:25
Adfactors PR Private Limited | intranet.adfactorspr.com | Adfactor Post By Admin | Low |  | 2026-03-17 |  | 2026-03-24 | Completed | Production | 0 | 0 |  | We completed the changes and shared them with the client on March 24th for approval to go live. However, the site has been down since March 26th due to server issues. We requested the team to move staging to live on April 28th. The database has been replaced, and we are currently working on the final changes. We are also facing a permission issue, which we raised with Pushphakhant from the server team. He will get back to us today, April 30th, to set up a call so we can check it together. |  |  |  | Project Update: Adfactor Post By Admin |  | 19dcd2cf998e87cc | 2026-05-06 10:37
Adfactors PR Private Limited | intranet.adfactorspr.com | Adfactor Restore | Low |  | 2026-03-09 |  |  | In Progress | Production | ⚠ Missing Effort | ⚠ Missing Effort |  | Since providing the latest database and requirements on April 9th, the team has been progressing with the remaining pages. We are currently navigating some permission constraints and have coordinated with the server team to troubleshoot this during a call today (30 April). We are also tracking the issue regarding profile pictures in the live environment, which was reported via email on April 27th. | Need to check Realuser profile picture in social feed we need Real User SSO Login credential for testing |  |  | Project Update: Adfactor Restore |  | 19dbe07c1c8a897c | 2026-05-06 10:37
FIA | farnboroughairshow.com | FIA2026: Aircraft & Agenda Pages |  | Abhicheke | 2026-04-01 | 2026-04-09 |  | Completed | Production | 6.5 | 5 |  |  | Need to move the code after enage api fix |  | FIA2026: Aircraft & Agenda Pages | Project Update: FIA2026: Aircraft & Agenda Pages |  | 19dbe2264c925c20 |  | 2026-05-06 10:50
FIA | farnboroughairshow.com | Exhibitor Listing | Low |  | 2026-02-20 | 2026-02-25 |  | Completed | Production | No Subtasks | No Subtasks |  |  | Need to move the code after enage api fix |  |  | Project Update: Exhibitor Listing |  |  |  | 2026-05-06 10:50
FIA | farnboroughairshow.com | FIA Maintenance April 2026 | Low |  | 2026-04-08 | 2026-04-08 | 2026-04-08 | Completed | Production | 15.5 | 13 | [5 empty] | Project Update: FIA Maintenance April 2026 |  | 19dbe28bbe45b817 |  | 2026-05-06 10:50
FIA | farnborough.com | Venue Maintenance April 2026 | Low |  | 2026-04-08 | 2026-04-09 |  | Waiting for Client Input | Production | 16.5 | 15.5 |  | Version Update has by abhi and Parthiban. Cross test done the entier website by them everything work as expeted |  |  |  | Project Update: Venue Maintenance April 2026 |  | 19dbdeb6c1b09ce7 |  | 2026-05-06 10:50
Vajra Global | vajraglobal.com | Adobe Experence Manger and workflow | Low | Rackesh Kumaran | 2026-05-05 | 2026-05-06 |  | Completed | [12 empty] | 2026-05-07 14:13
Adfactors PR Private Limited | intranet.adfactorspr.com | Core Value Page | Low | Abhicheke | 2026-05-04 |  |  | Completed | Production | 0.5 | 0.5 | [5 empty] | [Dev Tracker] TASK UPDATE: Core Value Page |  | 19dfbc3f12c44744 | 2026-05-20 10:11
Vajra Global | vajraglobal.com | Adobe Experience Manager and WorkFront | Low | Rackesh Kumaran | 2026-05-05 | 2026-05-06 |  | Completed | Local | 17 | 15 |  | G Mentioned He will speak to deep try to get the access for backoffice from deep we will review the backend |  |  |  | [Dev Tracker] TASK UPDATE: Adobe Experience Manager and WorkFront |  | 19e348a16c2c39e7 | 2026-06-02 08:52
Adfactors PR Private Limited | intranet.adfactorspr.com | Content Update May | Low |  | 2026-05-01 |  |  | Completed | Production | 22.15 | 20.3 |  | Remove the campaign Link in awards sheet and upload in Awards page Update the sheet and uplod content in AE, AM, Team Decathlon, Updated content in Live Update content in Awards page for 2022 2023,2024 staging Update content in Awards page for 2022 2023,2024 in Live Align the gold silver bronze in 2022 2023 2024 in award page in live |  |  |  | [Dev Tracker] TASK UPDATE: Content Update May |  | 19e8805287b6cb49 | 2026-06-03 17:24
Adfactors PR Private Limited | intranet.adfactorspr.com | Adfactor Restore May | Low |  | 2026-05-01 |  |  | Completed | Production | 69.5 | 66.15 |  |  | Few Profile Pic is missing on the Server Database That Need to fix from their end |  |  | [Dev Tracker] TASK UPDATE: Adfactor Restore May |  | 19eac110abd6a112 | 2026-06-11 09:38
Adfactors PR Private Limited | intranet.adfactorspr.com | Image and Video Edit On Post | Low | Parthiban | 2026-05-15 | 2026-05-20 |  | Completed | Production | 11 | 9.5 | [5 empty] | [Dev Tracker] TASK UPDATE: Image and Video Edit On Post | Users should be able to edit existing posts. Users should be able to: Add new images/videos Replace existing images/videos Remove existing media attachments The updated media should be saved successfully along with the post changes. The system should validate supported file formats and file size limits. Existing permissions and security validations should remain applicable during media updates. | 19eb0c94eff21d41 | 2026-06-11 09:43
FIA | farnboroughairshow.com | FIA Maintenance May 2026 | Low |  | 2026-05-01 |  |  | Completed | Production | 30.5 | 27.5 | [5 empty] | [Dev Tracker] TASK UPDATE: FIA Maintenance May 2026 |  | 19eadc814e627d62 | 2026-06-11 12:11
Adfactors PR Private Limited | intranet.adfactorspr.com | Home Page Changes May 2026 | Medium |  |  |  |  | Completed | Production | 5.5 | 6 | [5 empty] | TASK UPDATE: Home Page Changes May 2026 |  | 19eae0083be71160 | 2026-06-12 10:32
Adfactors PR Private Limited | intranet.adfactorspr.com | Brand Kit Page May 2026 | Medium |  |  |  |  | Completed | Production | 5 | 4.5 |  |  | Arrow design/reference for Brand Kit and site-wide updates. Icon for logo section for each items |  | Intranet Icons | TASK UPDATE: Brand Kit Page May 2026 |  | 19eac11e075ef2ab | 2026-06-12 10:32
Diriyah Gate Development Authority | www.dgda.gov.sa | DGDA Maintenance May 2026 | Low |  | 2026-05-01 |  |  | Completed | Production | 9 | 8 | [5 empty] | [Dev Tracker] TASK UPDATE: DGDA Maintenance May 2026 |  | 19ebccfb12ea8eb7 | 2026-06-13 06:17
Diriyah Gate Development Authority | www.dgda.gov.sa | Open data form Phase - 2 | Urgent |  | 2026-05-13 | 2026-05-18 | 2026-05-18 | Completed | Production | 28 | 23.5 |  |  |  | https://release-dgda.d1pchk3m069rke.amplifyapp.com/en/open-data | Open Data Form - DGDA | TASK UPDATE: Open data form Phase - 2 |  | 19eca52291fae749 | UmNUMDNDTUQyaklRa3A5Zg | 2026-06-17 13:07

## Dev Tracker Sub
Project Name | Main Task Name | Ticket Id | Task | Priority | S Date | E Date | Assigned to | Status | Env | As Per WO | Efforts | Actual Efforts | Informed | Support Needed / Blocker | Dependency Detail | Page Url | Mail Subject | Internal Mail Subject | Gmail Thread ID | Google Subtask ID | Main Google Task ID | Google Nest Status
farnboroughairshow.com | Brand GuidLine Change |  | Usage of the wireframes is fully set out in main brand guidelines | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Where recommended, these should be used across backgrounds and headers | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Brown Bold to be used for other headlines, H tags etc. | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Headers – add in a colour picker for banner descriptions, the same as with titles | Low | 2025-11-25 | 2026-01-19 |  | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Ensure consistent line spacing between title and description. | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Footer – change section headers (Quick Links, Our Brands, Contact Us) to Brown Bold and white | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Add title to stats section | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Hide side by side section (video and 2024 report), will need it again post-airshow | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Add sixth theme onto the same line, currently displaying below the others (on staging site) | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Remove the share this page actions on detail pages: | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | For example, the Sign-Up to FIA Insights bar should always be in grey if directly next to footer | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Avoid having 2 sections next to each other that use the Interstellar gradient. Sections should alternate between white background and either the gradient or grey | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Only to be used for Page Titles and some other headlines where specified (for example, the section headlines on the homepage) | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | 3.Don't use ethnocentric for category headings or company names (use Brown) | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | 4.Review category layout as there is quite a lot to display, on mobile especially you have to scroll a long way. Could this be changed to a simple drop-down filter? | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Replace carousel hero banner with video, centralise text and allow 2 button option. | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Ability to choose the colour of these buttons that would be useful, we can provide options (just to give us flexibility depending on hat we’re talking about) | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Add wireframe to background of gradient section | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Add a hover state to themes (colours to be provided) | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Trade Registration Page Development | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Sponsors & Partners, Official Suppliers, Pioneers of Tomorrow Partner pages 1.Smaller hero banner | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | 2.Remove second title, just keep the one in the hero banner | Low | 2025-11-25 | 2026-01-19 | Abhicheke | Completed | Production | 2025-11-28 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Where the main background used is the Interstellar gradient, we are looking at a different hero image design in white (for example, the Summary pages: Exhibiting Options, Enhance your presence, themes) | Low | 2025-12-03 | 2026-01-19 | Abhicheke | Completed | Production | 2025-12-11 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | New branding being finalised, we will send across new brand guidelines and a more detailed brief for each page by the end of November) | Low | 2025-12-03 | 2026-01-19 | Abhicheke | Completed | Production | 2025-12-11 | 0 | 0
farnboroughairshow.com | Brand GuidLine Change |  | Second Phase (January-March 2026) Redesign of pages (Exhibitor listing, What’s On/Agenda, Aircraft Listing) Further Pioneers pages (to be decided) Further design tweaks | Low | 2025-12-03 | 2026-01-19 | Abhicheke | Completed | Production | 2025-12-11 | 0 | 0
www.dgs.sa | Missing Content on DGS Page |  | Agenda - Waiting for PDF | Medium | 2025-12-10 | 2025-12-10 | Abhicheke | Completed | Production | 2025-12-10 | 0 | 0 |  | Received the PDF Today Updated On The DGS
www.dgs.sa | Missing Content on DGS Page |  | Production Stream - Waiting for actual image, Content and video link | Medium |  |  |  | Completed | Production |  | 0 | 0 |  | AW contents from DGS follow up sent on 01-12-2025
www.dgs.sa | Missing Content on DGS Page |  | Register Form - Need to Map by CRM Team | Medium |  |  |  | Completed | Production |  | 0 | 0 |  | AW contents from DGS follow up sent on 01-12-2025 |  |  |  | We are working on this with C4C team and Update the Mapping and Fix the changes The team need to get back to Us(30-11-2025 to 01-12-2025)
www.dgs.sa | DGS Registration form |  | FirstName And LastName Only allow 40 character | Urgent |  |  | Regan | Completed | Production |  | 0 | 0 |  | We sent a follow-up yesterday (December 1, 2025), 2nd follow-up sent on December 8, 2025. Awaiting client response
www.dgs.sa | DGS Registration form |  | Recaptcha Configuration and Update | Medium | 2025-12-01 | 2025-12-04 | Moswin | Completed | Production |  | 0 | 0 | [5 empty] | Immediate Assistance Needed – reCAPTCHA v3 Key Update for DGS
intranet.adfactorspr.com | Holiday List Page |  | We need to identify the default location, filter the data accordingly, and display the result. | Low | 2025-12-04 | 2025-12-12 | Parthiban | Completed | Production |  | 5 | 0
intranet.adfactorspr.com | Adfactor Home Page feature |  | The system needs to allow post creation and updating to be handled entirely within the popup, instead of within a separate section. | Low | 2025-12-04 | 2025-12-12 | Parthiban | Completed | Production |  | 0 | 0
www.dgs.sa | Missing Content on DGS Page |  | Speaker - Waiting for actual image and content | Medium |  |  |  | Closed – Not Proceeding | Production |  | 0 | 0 |  | AW contents from DGS follow up sent on 01-12-2025
www.dgs.sa | Missing Content on DGS Page |  | Accompanying Exhibition - Waiting for actual image and content | Medium |  |  |  | Closed – Not Proceeding | Production |  | 0 | 0 |  | AW contents from DGS follow up sent on 01-12-2025
intranet.adfactorspr.com | Holiday List Page |  | The Calendar also needs to be updated based on the holiday list and the applied filters. | Low | 2025-12-04 | 2025-12-12 | Parthiban | Completed | Production |  | 5 | 0
www.dgda.gov.sa | DGDA Version Update |  | Version update from 14.2.25 to 15.5.9 | Low | 2025-12-15 | 2025-12-17 | Abhicheke | Completed | Production |  | 0 | 0
www.dgda.gov.sa | DGDA Version Update |  | Apply prefech and pre connect for the speed increase | Low | 2025-12-15 | 2025-12-17 | Abhicheke | Completed | Production |  | 0 | 0 |  | desktop 40 -80 Mobile 32 - 50
www.dgda.gov.sa | DGDA Version Update |  | DGDA Improvment | Low | 2025-12-17 | 2025-12-17 | Parthiban | Completed | Production |  | 0 | 0
farnborough.com | Farnborough Canceled Event |  | Farnborough Canceled Event | Low | 2025-12-22 | 2026-01-16 | Parthiban | Completed | Production |  | 0 | 0
www.dgda.gov.sa | DGDA Version Update |  | Actions to address CVE-2025-55182 and CVE-2025-66478 (Next.js/React Vulnerabilities) | Low | 2025-12-21 | 2025-12-21 | Abhicheke | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Holiday List Page |  | Users must be allowed to download and add all holidays to their personal calendar via an .ics file. | Low | 2025-12-04 | 2025-12-12 | Parthiban | Completed | Production |  | 25 | 0
intranet.adfactorspr.com | Adfactor Home Page feature |  | Fall Back Need to Get from Member | Low | 2025-12-04 | 2025-12-12 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Home Page feature |  | Notification 30 sec refresh with Cache | Low | 2025-12-01 | 2025-12-03 | Parthiban | Completed | Production |  | 0 | 0
farnborough.com | Update the form date format |  | Update the form date format | Low | 2025-12-11 | 2025-12-11 | Abhicheke | Completed | Production |  | 0 | 0
www.dgs.sa | SEO Assets for DGS Site |  | SEO Assets for DGS Site - English | Medium | 2025-11-19 |  | Regan | Completed | Local |  | 0 | 0 |  | We have shared the document with the client on December 1, 2025 and are now awaiting their reply and approval. Once they approve the changes and provide the Arabic content, we will update the DGS live environment. 2nd follow-up sent on December 8, 2025. Awaiting client response |  |  |  | SEO Assets for DGS Site (Discussed 11-11-2025)
www.dgs.sa | SEO Assets for DGS Site |  | SEO Assets for DGS Site - Arabic | Medium | 2025-11-19 |  | Regan | Completed | Local |  | 0 | 0 |  | We have shared the document with the client on December 1, 2025 and are now awaiting their reply and approval. Once they approve the changes and provide the Arabic content, we will update the DGS live environment. 2nd follow-up sent on December 8, 2025. Awaiting client response |  |  |  | SEO Assets for DGS Site (Discussed 11-11-2025)
www.dgda.gov.sa | XMCC Migration |  | Conduct CH1 → XMCC Migration Impact Analysis. Document open questions, scope clarifications, and decisions. | Critical / Blocker |  |  | Regan | Closed – Not Proceeding |  |  | 0 | 0 |  | 1) Share the question with the client. 2) They need to decide whether to perform the migration this month or in April. 3) The DGDA team needs to give the Sitecore team GitHub access.
www.dgda.gov.sa | XMCC Migration |  | Sandbox access approved + answers received so development and testing can proceed without risk. | Critical / Blocker |  |  | Regan | Closed – Not Proceeding |  |  | 0 | 0 |  | 1) Share the question with the client. 2) They need to decide whether to perform the migration this month or in April. 3) The DGDA team needs to give the Sitecore team GitHub access.
www.dgda.gov.sa | 360 Degree Image new website |  | 360 Degree Image new website | Low |  |  | Regan | Closed / Cancelled |  |  | 0 | 0
www.dgda.gov.sa | Form Tracking GA |  | The Dev Team needs to review the form tracking and coordinate with Ranjith for validation. | Low | 2025-11-14 | 2025-11-17 | Ranjith | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Holiday List Page |  | Holiday Content | Low |  |  | Sowndar | Completed | Production |  | 0 | 0 |  | Need to check with Vishal
farnboroughairshow.com | FIA Changes on Show Theme |  | The Show Pages Cards Change and color updates and fetch the pillars from the pillars folder | Low | 2026-01-06 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0
www.dgda.gov.sa | Summer Program Page |  | Summer Program Page | Low | 2025-12-02 | 2025-12-11 | Abhicheke | Completed | Staging |  | 0 | 0 |  | Presently on Staging Alwosta team completed the program activity and integration with CRM is completed on 23/12; Program postponed to November 2026 as advised by Dayel.
www.dgda.gov.sa | Summer Program Page |  | Summer Program Page form | Low | 2025-12-02 | 2025-12-11 | Abhicheke | Completed | Staging |  | 0 | 0 |  | Presently on Staging Alwosta team completed the program activity and integration with CRM is completed on 23/12; Program postponed to November 2026 as advised by Dayel. |  | https://preview-preprod.dgda.gov.sa/en/contact-us/diriyah-horizons
www.dgda.gov.sa | Uma Form | 24-DEC-2025-1 | UMA Content - Close-Out Report (New form) - Phase 1 | Low | 2025-12-24 |  | Abhicheke | Closed – Not Proceeding | Staging |  | 0 | 0 |  | C4C Intergraion Progress
www.dgda.gov.sa | Uma Form | 24-DEC-2025-2 | UMA Content - General Inquiry (Minor Change) - Phase 1 | Low | 2025-12-24 |  |  | Closed – Not Proceeding | Staging |  | 0 | 0 |  | C4C Intergraion Progress ,Current Cateogry is differnt what they have shared on the doucment we need to check with cline and continueq
www.dgda.gov.sa | Uma Form | 24-DEC-2025-3 | UMA Content - Complaints (Minor Change) - Phase 1 | Low | 2025-12-24 |  |  | Closed – Not Proceeding | Staging |  | 0 | 0 |  | C4C Intergraion Progress Current Cateogry is differnt what they have shared on the doucment we need to check with cline and continueq
www.dgda.gov.sa | Uma Form | 24-DEC-2025-4 | UMA Content - Service Request (New form) - Phase 1 | Low | 2025-12-24 |  | Parthiban | Closed – Not Proceeding | Staging |  | 0 | 0 |  | C4C Intergraion Progress English has compeleted arabic will start today
www.dgda.gov.sa | Uma Form | 24-DEC-2025-5 | UMA Content - Book a Meeting (New form) - Phase 1 | Low | 2025-12-24 |  |  | Closed – Not Proceeding | Staging |  | 0 | 0 |  | C4C Intergraion Progress
www.dgda.gov.sa | Uma Form | 24-DEC-2025-6 | UMA Content - Staging Report (New form) - Phase 1 | Low | 2025-12-24 |  | Parthiban | Closed – Not Proceeding | Staging |  | 0 | 0 |  | C4C Intergraion Progress completed in local hoverever this form on phase 2 so we will share with clinet once done the above forms
www.dgda.gov.sa | Uma Form | 24-DEC-2025-7 | OTP Intergration on the Website | Low | 2025-12-24 |  |  | Closed – Not Proceeding |  |  | 0 | 0
www.dgda.gov.sa | Uma Form | 24-DEC-2025-8 | Violation_DGDA Website_Integration API_V1.1 testing in local | Low | 2025-12-29 |  | Abhicheke | Closed – Not Proceeding | Local |  | 0 | 0 |  | 503 Application Shutting Down Error need to check with client
www.dgs.sa | DGS Home | 31-DEC-2025-1 | DGS Video Page(Coming Soon) Instead of the home page, create a new page and update the video on that page. | Low | 2025-12-31 |  |  | Completed | Production |  | 0 | 0 |  | Once got the approval from client need to publish on Production
www.dgs.sa | DGS Home | 31-DEC-2025-2 | DGS pages unpublished and add redirection | Low | 2025-12-31 |  |  | Completed | Production |  | 0 | 0
farnborough.com |  |  | Venue Site Form Data Weekly Export and send to Client | Low | 2026-01-02 |  | Abhicheke | Completed | Production |  | 0 | 0
farnborough.com | Venue Version Update |  | Updated the Umbraco version 13.10.0 to 13.13.0 in Farnborough Vennue | Low | 2026-01-05 | 2026-01-16 | Abhicheke | Completed | Production |  | 0 | 0
www.dgs.sa | DGS Home | 5-Jan-2026-1 | Set up redirects for DGS to the home page since the seminar is over. | Low | 2026-01-05 |  |  | Completed | Production |  | 0 | 0 |  | /en/agenda /en/speakers /en/past-seminars/dgs-2023 /en/past-seminars/dgs-2024 /en/accompanying-exhibition /en/salwa-stage-live-stream /en/alawja-stage-live-stream /en/dgs-registration-closed /en/privacy-policy en/terms-and-conditions /en/cookie-policy /ar/agenda /ar/speakers /ar/past-seminars/dgs-2023 /ar/past-seminars/dgs-2024 /ar/accompanying-exhibition /ar/salwa-stage-live-stream /ar/alawja-stage-live-stream /ar/dgs-registration-closed /ar/privacy-policy /ar/terms-and-conditions /ar/cookie-policy arabic pages to arabic home page is pending.
farnboroughairshow.com | FIA Version Update |  | Version Update 13.9.1 to 13.13.0 in FarnboroughAirshow | Low | 2026-01-05 |  | Abhicheke | Completed | Production |  | 0 | 0
vajraglobal.com | Internal Task |  | Research on self hosted runners and their cost per usage for private and public repos in github | Low | 2026-01-05 |  |  | Completed | Production |  | 0 | 0 |  | GitHub Actions Billing – Runner Cost Overview document done, need to check with Sowndar if he has something else that needs to cover and close this
vajraglobal.com | Internal Task |  | Define industry-standard DevOps-as-a-Service offerings, competitive benchmarking, internal capability mapping, pricing structure, and operational readiness including AWS service scope and scaling considerations. | Low | 2026-01-05 |  |  | Completed | Production |  | 0 | 0 |  | DevOps as a Service Need to get verification from Sowndar before taking it up with Sriram Sir
www.dgda.gov.sa | Uma Form | 06-JAN-2025-1 | Complaints Form Concerned Area remove and change the category and sub-category position | Low | 2026-01-06 |  | Abhicheke | Completed | Staging |  | 0 | 0
www.dgda.gov.sa | Uma Form | 06-JAN-2025-2 | Staging Report,Book a Meeting content change | Low | 2026-01-06 |  | Abhicheke | Completed | Staging |  | 0 | 0
vajraglobal.com | Internal Task |  | Exhibitor Portal Plan | Low | 2026-01-06 |  | Parthiban | Completed | Production |  | 0 | 0 |  | The Process Has happen long before we will restart it later so we close it for now
vajraglobal.com | Internal Task |  | Umbraco Log Check and send auto notification via email | Low | 2026-01-06 |  | Abhicheke | Completed | Production |  | 0 | 0
www.dgs.sa | DGS Home | 5-Jan-2026-2 | Set up redirects for DGS to the home page in a way that all english pages go to english home page , and all arabic home pages go to arabic home pages since the seminar is over. | Low | 2026-01-06 | 2026-01-06 | Moswin | Completed | Production |  | 0 | 0
www.astonbrooke.co.uk/ | AB project CICD failing |  | Aston Brooke CICD is failing because of No space is left because of too many artifacts, need to solve it and provide permanent solution for future proofing. | High | 2026-01-07 | 2026-01-07 | Moswin | Completed | Production |  | 0 | 0 |  | Issue has been resolved. Issue: too many build has been happening in past few days so artifact storage has filled up. Immediate solution: Deleted older artifacts and freed up space , now working fine. Permanent solution: For build artifacts now have kept an expiry of 7 days, now the clean up activity of artifacts will happen by itself regularly.
www.dgda.gov.sa | Uma Form | 07-JAN-2025-1 | Service Request Form - This section will appear if category = Design Compliance and add new 4 fields | Low | 2026-01-07 | 2026-01-07 | Abhicheke | Completed | Staging |  | 0 | 0 |  | 1. Missing fields How do you describe yourself and area ? need to check if we need to include If the user slects Design compliance in Category we will introduce the new section Do we need to place it as first and last name in Owner information or as Owner Name
www.dgda.gov.sa | DGDA DevSecOps pipelines set up | 08-JAN-2025-1 | Meeting to Work along with Saheel and set up Security pipelines in DGDA and generate reports | Low | 2026-01-08 | 2026-01-08 | Moswin | Completed | Local |  | 0 | 0 |  | Discussed and provided details for the DGDA to proceed further with their set up for scnaning.
www.dgda.gov.sa | DGDA DevSecOps pipelines set up | 08-JAN-2025-2 | Document preparation with all the details required from the infra team from DGDA | Low | 2026-01-08 | 2026-01-08 | Moswin | Completed | Local |  | 0 | 0 |  | DGDA_DGS DevSecOps implementation .docx
www.dgda.gov.sa | DGDA monitoring sheet update |  | DGDA monitoring sheet updated for the last 5 days. | Low | 2026-01-08 | 2026-01-08 | Moswin | Completed | Production |  | 0 | 0 |  | DGDA Monitoring Activities
farnboroughairshow.com | POT Feed Back Changes | 09-JAN-2025-1 | Homepage 'Welcome to Pioneers of Tomorrow' font needs to be bolder, use Lexend Black for main page titles Sub-headings, e.g. What's On, Ticket Types & Get Involved should also be Lexend Black You can check how the font weighting should display here: https://fonts.google.com/specimen/Lexend | Low | 2026-01-09 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  |  | FIA2026 Website Updates
farnboroughairshow.com | POT Feed Back Changes | 09-JAN-2025-2 | Menu Could you change the PoT section in the mega menu to the light blue, but keep the drop down as purple once hovered over? The purple blends in too much to the teal colour at the moment | Low | 2026-01-09 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  |  | FIA2026 Website Updates
farnboroughairshow.com | POT Feed Back Changes | 09-JAN-2025-3 | Key Features (summary) Title needs to be bolder (Lexend black) Sub-heading font is fine | Low | 2026-01-09 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  |  | FIA2026 Website Updates
farnboroughairshow.com | POT Feed Back Changes | 09-JAN-2025-4 | Key features (detail) Change useful links box to one of the lighter purple colours Title needs to be bolder (Lexend black) | Low | 2026-01-09 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  |  | FIA2026 Website Updates
farnboroughairshow.com | POT Feed Back Changes | 09-JAN-2025-5 | Get Involved (detail) Not publishing, but should sit under PoT section | Low | 2026-01-09 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  |  | FIA2026 Website Updates
farnboroughairshow.com | POT Feed Back Changes | 09-JAN-2025-6 | Tickets Reduce the size of the hero banner (same size as the trade FIA ticket page would be ideal) Titles needs to be bolder (Lexend black) When adding another ticket type the new box is FIA teal colour rather than purple | Low | 2026-01-09 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  |  | FIA2026 Website Updates
farnboroughairshow.com | POT Feed Back Changes | 09-JAN-2025-7 | FIA Homepage Theme Section – could the hover colour match the colour of the theme (see brand guidelines for hexcodes) | Low | 2026-01-09 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  |  | FIA2026 Website Updates
farnborough.com |  |  | Venue Site Form Data Weekly Export and send to Client | Low | 2026-01-09 | 2026-01-09 | Parthiban | Completed | Production |  | 0 | 0
www.dgda.gov.sa |  |  | Remove the Land Management Services From e-service | Low | 2026-01-12 | 2026-01-12 | Abhicheke | Completed | Production |  | 0 | 0
farnboroughinternationalstudios.com | Studio Site Version Update |  | Version Update 13.9.1 to 13.13.0 in FarnboroughAirshow | Low | 2026-01-19 | 2026-01-21 | Abhicheke | Completed | Production |  | 0 | 0
farnboroughairshow.com |  |  | FIA Website Final Changes | Low | 2026-01-16 | 2026-01-16 | Abhicheke | Completed | Production |  | 0 | 0
farnboroughairshow.com |  |  | FIA 2026 and POT 2026 Changes moved to live and version update move to live | Low | 2026-01-19 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  |  | FIA2026 Website Updates
intranet.adfactorspr.com |  |  | Adfactors sso login issue fix and move the changes to staging and live and test the site | High | 2026-01-19 | 2026-01-19 | Abhicheke | Completed | Production |  | 0 | 0
www.dgda.gov.sa |  |  | DGDA Monitoring sheet update for the last 4 days | Low | 2026-01-13 | 2026-01-13 |  | Completed | Production |  | 2 | 0
www.dgda.gov.sa |  |  | Cloudflare resolver issue analysis with the 1.1.1.1 IP. Have identified nothing to worry about in our particular case. | Low | 2026-01-21 | 2026-01-21 |  | Completed | Production |  | 3.5 | 0
www.dgda.gov.sa |  |  | DGDA Diagram work for documentation | Low | 2026-01-27 | 2026-01-27 |  | Completed | Production |  | 3 | 2
www.dgda.gov.sa | National Design System (DGA) | 22-JAN-2026-1 | National Design System design apply for home page and header and footer | Low | 2026-01-22 | 2026-01-26 | Abhicheke | Completed | Production |  | 15 | 10
farnboroughinternationalstudios.com | New Testimonial Page |  | Develope Testimonials Page | Medium | 2026-01-29 | 2026-02-02 | Abhicheke | Completed | Production |  | 0 | 0 |  | Design Link https://www.figma.com/design/rFsGHt32JQmdSu5yTx6Ni3/Farnborough-studios?node-id=128-2&t=b4BY2SVqY9tQB9mE-0 |  |  | Studios website - testimonials
|  |  | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-01-01 | 2026-01-30 | Parthiban | Completed | Production |  | 0 | 0 |  | Daily mornitoring the websites (working status,log error,page speed)
farnborough.com |  |  | Venue Site Form Data Weekly Export and send to Client | Medium | 2026-01-30 | 2026-01-30 | Parthiban | Completed | Production |  | 0 | 0
www.dgda.gov.sa | Form Failed Feb-2026 |  | Forms payload duplicate fix - Golf Club Hiring Opportunity form | High | 2026-02-03 |  | Abhicheke | Completed | Production |  | 0 | 0
www.dgda.gov.sa | Content Update – Feb 2026 |  | DGDA Content Update Menu 1.Diriyah Community changed to Life in Diriyah 2.url Changed from https://preview-preprod.dgda.gov.sa/en/diriyah-community to https://preview-preprod.dgda.gov.sa/en/life-in-diriyah 3.Update the page banner text from Diriyah Community changed to Life in Diriyah Learn at Diriyah https://preview-preprod.dgda.gov.sa/en/program/dal 1.Title Updated 2.Content Updated 3.Program Card Image Updated https://preview-preprod.dgda.gov.sa/en/program/dgs-students-poster-showcase 1.New Program Page Created 2.Title Updated 3.Content Updated 4.Banner Image Updated 5.Program Card Image Updated https://preview-preprod.dgda.gov.sa/en/program/diriyah-horizons 1.Title Updated 2.Content Updated 3.Banner Image Updated 4.Program Card Image Updated Heritage and Culture https://preview-preprod.dgda.gov.sa/en/place/at-turaif 1.Content Updated | Medium | 2026-02-05 | 2026-02-05 | Abhicheke | Completed | Production |  | 0 | 0 |  | After got approval need to publish the page on live
farnboroughinternationalstudios.com |  |  | Film at Farnborough FAM Trip form fix | Medium | 2026-02-09 | 2026-02-09 |  | Completed | Production |  | 0 | 0 |  |  |  | https://farnboroughinternationalstudios.com/film-at-farnborough-fam-trip/
farnboroughinternationalstudios.com |  |  | SEO optimization for the FIL Studios website | [7 empty] | 0 | 0
www.dgda.gov.sa | Leadership component |  | Leadership Component Change the Desgin for this Leadership Team and update the content and Images | Medium | 2026-02-09 | 2026-02-09 |  | Completed | Production |  | 0 | 0 |  |  |  | https://preview-preprod.dgda.gov.sa/en/about/leadership
intranet.adfactorspr.com | Academy Page | 05-FEB-2026-1 | Create a Adfactors About adfactor academy,Internal Programmes,Cohort-based Programmes | Medium | 2026-02-05 | 2026-02-06 | Parthiban | Completed | Production |  | 6 | 0 |  | Waiting for client approval to move live |  | https://intranetstaging.adfactorspr.com/knowledge-corner/adfactors-academy/
intranet.adfactorspr.com | Academy Page | 05-FEB-2026-2 | Academy Detail page | Medium | 2026-02-05 | 2026-02-06 | Parthiban | Completed | Production |  | 2 | 0 |  | Waiting for client approval to move live |  | https://intranetstaging.adfactorspr.com/knowledge-corner/adfactors-academy/
intranet.adfactorspr.com | Academy Page | 11-FEB-2026-1 | Create a Adfactors Academy Page version 2 with accordions | Medium | 2026-02-11 | 2026-02-11 | Parthiban | Completed | Production |  | 5 | 0 |  | Create a another Design based on the client need and shown as new page named as Academy page V2.Moved to staging for client review. |  | https://intranetstaging.adfactorspr.com/knowledge-corner/adfactors-academy-version-2/
farnboroughairshow.com | Phase 1 Brand GuidLine Change | 11-FEB-2026-2 | Create new field for Ticket Price Image | Medium | 2026-01-21 | 2026-02-11 | Abhicheke | Completed | Production |  |  | 0 |  | After Received Approval need to move the code and create field to live
farnborough.com |  |  | Venue Site Form Data Weekly Export and send to Client | Medium | 2026-02-10 | 2026-02-10 | Parthiban | Completed | Production |  |  | 0
www.dgda.gov.sa | Leadership component | 12-FEB-2026-1 | Leadership Components (HRH) Text Alignment fix in coding | Medium | 2026-02-11 | 2026-02-12 | Abhicheke | Completed | Production |  |  | 0
intranet.adfactorspr.com | AF Server Changes | 12-FEB-2026-6 | Change the website server | Medium | 2026-02-11 | 2026-02-11 | Sowndar | Completed | Production |  | 6 | 0
farnboroughairshow.com | FIA AGF Page changes | 12-FEB-2026-2 | Add a Featured Exhibitors in aerospace global forum | Medium | 2026-02-12 | 2026-02-13 | Parthiban | Completed | Production |  | 4 | 0 |  | Waiting for client approval to move live
www.dgda.gov.sa |  | 12-FEB-2026-3 | DGDA CTA and Header Tracking Code Update | Medium | 2026-02-12 | 2026-02-12 | Abhicheke | Completed | Production |  |  | 0
intranet.adfactorspr.com | AF Server Changes | 12-FEB-2026-4 | Test Entire page and functionality in Adfactors new website | Medium | 2026-02-12 | 2026-02-16 | Parthiban | Completed | Production |  |  | 0
intranet.adfactorspr.com | Academy Page | 12-FEB-2026-5 | Change the padding in Internal Programmes,Cohort-based Programmes cards | Medium | 2026-02-12 | 2026-02-12 | Parthiban | Completed | Production |  | 1 | 0 |  | Client sugested to padding and cards alaingment.changes are Done and moved to staging |  | https://intranetstaging.adfactorspr.com/knowledge-corner/adfactors-academy-version-2/
farnborough.com |  | 13-FEB-2026-1 | Venue Site Form Data Weekly Export and send to Client | Medium | 2026-02-13 | 2026-02-13 | Parthiban | Completed | Production |  |  | 0
intranet.adfactorspr.com |  | 16-FEB-2026-1 | The hyperlinks on these pages aren't opening in a new tab script fix | Medium | 2026-02-16 | 2026-02-16 | Abhicheke | Completed | Production |  |  | 0
intranet.adfactorspr.com | Author Name on Articale Page | 16-FEB-2026-2 | Add Author name field for artical page | Medium | 2026-02-16 | 2026-02-16 | Abhicheke | Completed | Production |  |  | 0 |  |  |  | https://intranetstaging.adfactorspr.com/knowledge-corner/current-affairs/industry-reports/us-india-trade-agreement-framework-a-structural-analysis/
intranet.adfactorspr.com |  | 16-FEB-2026-3 | Excel to table data not showing issue fix on adfactors | Medium | 2026-02-16 | 2026-02-16 | Abhicheke | Completed | Production |  |  | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 16-FEB-2026-4 | Create a Posts & Moderation for admin post detail page | Medium | 2026-02-16 | 2026-02-16 | Parthiban | Completed | Production |  | 4 | 0 |  |  |  | https://localhost:44380/admin-post-detail?postId=d302be2f-fb49-45e9-8d9f-5caea8ea5925
intranet.adfactorspr.com | Adfactor Admin Dashboard | 16-FEB-2026-5 | Add Edit post ,Archive,Delete button and make it functional | Medium | 2026-02-16 | 2026-02-16 | Parthiban | Completed | Production |  | 4 | 0 |  |  |  | https://localhost:44380/admin-post-detail?postId=d302be2f-fb49-45e9-8d9f-5caea8ea5925
intranet.adfactorspr.com | Adfactor Admin Dashboard | 17-FEB-2026-1 | Design a Post and moderation Table in admin dashboard | Medium | 2026-02-17 | 2026-02-17 | Parthiban | Completed | Production |  | 4 | 0 |  |  |  | https://localhost:44380/admin-dashboard/admin-post-moderation/
intranet.adfactorspr.com | Adfactor Admin Dashboard | 17-FEB-2026-2 | Fetch the Preview image from Db and show it as preview in Table | Medium | 2026-02-17 | 2026-02-17 | Parthiban | Completed | Production |  | 2 | 0 |  |  |  | https://localhost:44380/admin-dashboard/admin-post-moderation/
intranet.adfactorspr.com | Adfactor Admin Dashboard | 17-FEB-2026-3 | Redesign the Admin Post detail page match with our existing design | Medium | 2026-02-18 | 2026-02-18 | Parthiban | Completed | Production |  | 2 | 0 |  |  |  | https://localhost:44380/admin-post-detail?postId=d302be2f-fb49-45e9-8d9f-5caea8ea5925
intranet.adfactorspr.com | Adfactor Admin Dashboard | 18-FEB-2026-1 | Add a Filter and search buttons into the Post and moderation and Activity Log | Medium | 2026-02-18 | 2026-02-18 | Parthiban | Completed | Production |  | 2 | 0 |  |  |  | https://localhost:44380/admin-dashboard/admin-post-moderation/
intranet.adfactorspr.com | Adfactor Admin Dashboard | 18-FEB-2026-2 | Add Export Log in Admin Activity log Functionality | Medium | 2026-02-18 | 2026-02-18 | Parthiban | Completed | Production |  | 2 | 0 |  |  |  | https://localhost:44380/admin-dashboard/admin-activity-log/
intranet.adfactorspr.com | Adfactor Admin Dashboard | 18-FEB-2026-3 | Add Entity Id as in Action Description and Redirect to post detail page | Medium | 2026-02-18 | 2026-02-18 | Parthiban | Completed | Production |  | 4 | 0 |  |  |  | https://localhost:44380/admin-dashboard/admin-activity-log/
intranet.adfactorspr.com | Adfactor Admin Dashboard | 19-FEB-2026-1 | Create a System Generated Post with Drag and drop Functionality | Medium | 2026-02-19 | 2026-02-19 | Parthiban | Completed | Production |  |  | 0
intranet.adfactorspr.com | Academy page | 19-FEB-2026-2 | Create a new pages Adfactors Academy Version 2.1 and V2.2 Create a new section Reach Out to Us for both page | Medium | 2026-02-19 | 2026-02-19 | Parthiban | Completed | Production |  | 4 | 0 |  | client suggested a additonal 2 pages named as Adfactors acadamy version 2.1 and 2.2 with additional sections.changes are done and moved to staging Waiting For client approval to move live
www.dgda.gov.sa | Founding day 2026 |  | 1. Clone the Founding day page and change the old page url to fd-25 2. Remove some sections and change the bg color for a section 3. Change the icon for a section | Medium | 2026-02-18 | 2026-02-19 | Abhicheke | Completed | Production |  |  | 0 |  | Hold for client feedback Since Founding Day Activations has finished. We consider this task as closed |  | https://preview-preprod.dgda.gov.sa/en/fd-25 https://feat-founding-day-2026.d38541r9nlp4br.amplifyapp.com/en/founding-day
intranet.adfactorspr.com | Author Name on Articale Page |  | Author Name Get the data drom the database and pick the author name from the author folder | Medium | 2026-02-19 |  | Abhicheke | Completed | Production |  |  | 0
farnboroughairshow.com | Exhibitor Listing |  | FIA2026 ¦ Exhibitor Listing Page Filter Any Category to Any Priorities Filter Any Theme to Any Priorities Theme/s changed to Priorities Apply new design for this page and change the accordion to popup | Medium | 2026-02-20 | 2026-02-25 | Abhicheke | Completed | Production |  |  | 0 |  | Code updated and moved to git |  | https://staging.farnboroughairshow.com/the-show/exhibitor-listing/
intranet.adfactorspr.com | Adfactor Admin Dashboard | 23-FEB-2026-1 | Add archive and Restore for the admin activity | Medium | 2026-02-23 | 2026-02-23 | Parthiban | Completed | Production |  | 3 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 23-FEB-2026-2 | Do the changes in post moderation and Activity log | Medium | 2026-02-23 | 2026-02-23 | Parthiban | Completed | Production |  | 3 | 0 |  | change the button style and remove the image preview,hide the archive post in post moderation table and show in activity log |  | https://localhost:44380/admin-post-detail?postId=d302be2f-fb49-45e9-8d9f-5caea8ea5925
intranet.adfactorspr.com | Adfactor Admin Dashboard | 24-FEB-2026-2 | pilot testing for system generated post. create auto generated post | Medium | 2026-02-24 | 2026-02-24 | Parthiban | Completed | Production |  | 0 | 0
www.dgda.gov.sa | Leadership component | 24-FEB-2026-1 | Leadership Components (HRH) Text Alignment fix in coding and CEO Message Design Moved to Production | Medium | 2026-02-24 | 2026-02-24 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  | https://www.dgda.gov.sa/en/about
intranet.adfactorspr.com | Adfactor Admin Dashboard | 24-FEB-2026-3 | create a admin and super admin to show the admin icon and delete functionality | Medium | 2026-02-24 | 2026-02-24 | Parthiban | Completed | Production |  | 2 | 0 |  | Based on the backofice access we do the admin access and super admin access
farnboroughairshow.com | Feb Maintenance changes - 2026 | 25-FEB-2026-1 | Please update the sticky button colour from orange to purple (Pioneers, light purple) Fix typo on public (PoT) enquiries (screenshot), should be Pioneers of Tomorrow We now have over 27 featured exhibitor logos for the homepage and it takes several minutes to see them all. Please could we speed up the scroll slightly and add an additional row? (see mock-up) If the second row could start from exhibitor 15 AMDIE | Medium | 2026-02-25 | 2026-02-26 | Abhicheke | Completed | Production |  | 0 | 0
farnboroughairshow.com | Feb Maintenance changes - 2026 | 26-FEB-2026-1 | Exhibitor Logo in Same Direction For the Sticky Button need to add the color picker | Medium | 2026-02-26 | 2026-02-26 | Abhicheke | Completed | Production |  | 0 | 0
intranet.adfactorspr.com |  |  | Adfactors Production Test the site after point the new server | Medium | 2026-02-16 |  |  | Completed | Production |  | 0 | 0
intranet.adfactorspr.com |  |  | Adfactors Staging Test the site after point the new server | Medium | 2026-02-16 |  |  | Completed | Production |  | 0 | 0
work.adfactorspr.com |  |  | Work Adfactors Production Test the site after point the new server | Medium | 2026-02-16 |  |  | Completed | Production |  | 0 | 0
work.adfactorspr.com |  |  | Work Adfactors Staging Test the site after point the new server | Medium | 2026-02-16 |  |  | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Social Feed | 02-MAR-2026-1 | Create a Filter for Social Feed Posts | Medium | 2026-03-02 | 2026-03-02 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Academy Page | 09-MAR-2026-1 | Adfactors Academy Page remove the border botton and add the section title Add the Enable Tab Button Logic | Medium | 2026-03-09 | 2026-03-09 | Abhicheke | Completed | Production |  | 5 | 0 |  | Create a another Design based on the client need and shown as new page named as Academy page V2.Moved to staging for client review. |  | https://intranetstaging.adfactorspr.com/knowledge-corner/adfactors-academy-version-2/
intranet.adfactorspr.com | Academy Page | 09-MAR-2026-2 | Move the academy Page to live | Medium | 2026-03-09 | 2026-03-09 | Abhicheke | Completed | Production |  | 0 | 0
farnboroughairshow.com | MPU Functionality | 09-MAR-2026-3 | Theme Page MPU Implementation in FIA | Medium | 2026-03-05 | 2026-03-11 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  | https://staging.farnboroughairshow.com/the-show/themes/global-security/ | FIA Website ¦ Theme Page Leaderboard
intranet.adfactorspr.com | Adfactor Admin Dashboard | 10-MAR-2026-1 | change the admin and super admin access for admin dashborad via Member group backofice | Medium | 2026-03-10 | 2026-03-10 | Parthiban | Completed | Production |  | 0 | 0
www.dgda.gov.sa | Emergency Service Form | 12-MAR-2026-1 | Emergency Service Form With OTP and GIS API | Medium | 2026-03-12 |  | Abhicheke | On Hold / Blocked | Local |  | 0 | 0 |  |  | SMS API Working Good Waiting for Production URL 3rd Api not working 1st and 2nd Api Working
www.dgda.gov.sa |  | 12-MAR-2026-2 | Qmatic API for Booking School Visit Form | Medium | 2026-03-12 |  | Sowndar | In Progress | Local |  | 0 | 0 |  | Waiting for the client to share the UAT API links
www.dgda.gov.sa |  | 12-MAR-2026-3 | Packages fix https://github.com/dgcl-cloud/dgda/security/dependabot | Medium | 2026-03-12 |  | Abhicheke | Pipeline / To Do | Local |  | 0 | 0 |  | Waiting for Moswin input - We need to done the task thats tagged with Development
intranet.adfactorspr.com | Adfactor Admin Dashboard | 12-MAR-2026-4 | Check the system generated Post in staging | Medium | 2026-03-12 | 2026-03-12 | Parthiban | Completed | Staging |  | 0 | 0 |  | share the staging link with sai and review it and if any change they need to fix that
farnborough.com | Form Test | 13-MAR-2026-1 | Test All the forms in DGDA and Farnborugh | Medium | 2026-03-13 | 2026-03-13 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 13-MAR-2026-2 | Change the allignment and add fonts size ,Start Center End allignment in System Genereted Post preview and after post.Add Line breaking | Medium | 2026-03-13 | 2026-03-13 | Parthiban | Completed | Production |  | 0 | 0
farnborough.com | Farnborough Weekly Report | 13-MAR-2026-3 | Weekly Export Forms in Farnborough | Medium | 2026-03-13 | 2026-03-13 | Parthiban | Completed | Production |  | 0.5 | 0
msmehealthengine.fametn.com | MSME Phase 2 |  | CI / CD for backend Staging + Production | Medium | 2026-03-13 | 2026-03-13 | Moswin | Completed | Production |  | 6 | 0
farnborough.com | FIECC - Landing page | 13-MAR-2026-4 | FIECC - Landing page Development and Move to Production | Medium | 2026-03-13 | 2026-03-24 | Abhicheke | Completed | Production |  | 0 | 0 |  | https://www.figma.com/proto/Oxi5zyx20OGwglaaWWAXhS/Farnborough-venue?page-id=115%3A2&node-id=115-1814&viewport=364%2C384%2C0.47&t=pqOk7KSBeCne8OJa-1&scaling=min-zoom&content-scaling=fixed&starting-point-node-id=115%3A4757 1.Currently, we have Lorem Ipsum on the live site. 2.Currently, we have a dummy banner and gallery images on the live site. 3.Currently, we do not have the Checklist ID for the form; the submitted data will be sent to event-enquiries@farnborough.com. 4.Currently, we have a dummy sample PDF, which will be downloaded after someone submits the form. |  | farnborough.com/landing-page
www.dgda.gov.sa | Cybersecurity Compliance Self-Assessment |  | Fill the Cybersecurity Compliance Self-Assessment document and share back with the client | Medium | 2026-03-13 | 2026-03-13 | Moswin | Completed | Production |  | 4 | 0
intranet.adfactorspr.com | Academy Page - 2 | 17-MAR-2026-1 | Update the content from staging to live in backoffice | Medium | 2026-03-17 | 2026-03-17 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Academy Page - 2 | 17-MAR-2026-2 | Academy Page Title Border Logic | Medium | 2026-03-17 | 2026-03-17 | Abhicheke | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Post By Admin | 17-MAR-2026-3 | Test the Behalf of comapy and behalf of user functionality in Home page | Medium | 2026-03-17 | 2026-03-17 | Parthiban | Completed | Production |  | 0 | 0
msmehealthengine.fametn.com | MSME Phase 2 |  | Disaster recovery plan and prepare a document on it.. | Medium | 2026-03-16 | 2026-03-16 | Moswin | Completed | Production |  | 6 | 0 |  | https://docs.google.com/document/d/1sKpXIeZkRqO2P7UP6aU-Rp7B50l07Mr2/edit?usp=sharing&ouid=108220845174973423951&rtpof=true&sd=true
https://hellowizadmin.hellowiz.com/ | Hellowiz architecture |  | Fill this document for Architecture questionnaire for HelloWiz | Low | 2026-03-18 | 2026-03-18 | Moswin | Completed | Completed |  | 0 | 0
intranet.adfactorspr.com | Adfactor Post By Admin | 18-MAR-2026-1 | Make the userename as Comms desk and post sublines with corresponding posts ifor system generated post | Medium | 2026-03-18 | 2026-03-18 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Post By Admin | 19-MAR-2026-1 | Add Mention tag and get notfication for the Corresponding User after system generated post | Medium | 2026-03-19 | 2026-03-19 | Parthiban | Completed | Production |  | 0 | 0 |  |  | Need to check the Real User get Notification while auto post generation post the Birthday or Work Anniversary
intranet.adfactorspr.com | Adfactor Post By Admin | 19-MAR-2026-2 | Need to check what column have in New Joiner table for Joining date | Medium | 2026-03-19 | 2026-03-19 | Parthiban | Completed | Production |  | 0 | 0
farnborough.com | FIA-DGDA Maintenance 04 2026 | 20-MAR-2026-1 | Test All the Forms in DGDA and Farnborough | Medium | 2026-03-20 | 2026-03-20 | Parthiban | Completed | Local |  | 0 | 0
farnborough.com | Farnborough Weekly Report | 20-MAR-2026-2 | Farnborough Weekly Form Export | Medium | 2026-03-20 | 2026-03-20 | Parthiban | Completed | Local |  | 0.5 | 0
intranet.adfactorspr.com | Academy Page - 2 | 20-MAR-2026-3 | Academy Page Move to Production | Medium | 2026-03-20 | 2026-03-20 | Abhicheke | Completed | Production |  | 0 | 0 |  |  |  | https://intranet.adfactorspr.com/adfactors-academy/
intranet.adfactorspr.com | Adfactor Admin Dashboard | 20-MAR-2026-4 | Fix the alignment issue in the System Generated Post (Rich Text Editor) | Medium | 2026-03-23 | 2026-03-24 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 20-MAR-2026-5 | Provide the complete list of user variables available in the database | Medium | 2026-03-23 | 2026-03-24 | Parthiban | Completed | Production |  | 0 | 0 |  | server database Employee Detail colum
intranet.adfactorspr.com | Adfactor Admin Dashboard | 20-MAR-2026-6 | Correct the line spacing for System Generated Posts | Medium | 2026-03-23 | 2026-03-24 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 20-MAR-2026-7 | Remove the “Edit” option for System Generated Posts on the Post Moderation page | Medium | 2026-03-23 | 2026-03-23 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 20-MAR-2026-8 | Remove the fields: Age in Years, Email ID, and Mobile Number | Medium | 2026-03-23 | 2026-03-23 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Post By Admin | 20-MAR-2026-9 | Add a toggle option for “Post on behalf of Company” | Medium | 2026-03-23 | 2026-03-23 | Parthiban | Completed | Production |  | 0 | 0
https://astonbrooke.co.uk/ | AstonBrooke Demo environment set up | 19-MAR-2026-1 | AstonBrooke Demo Environment set up and deployment of application in there and testing is done | Medium | 2026-03-18 | 2026-03-18 | Moswin | Completed | Production |  | 6 | 0
https://astonbrooke.co.uk/ | AstonBrooke Demo environment set up | 19-MAR-2026-2 | DNS set up for Hellowiz demo site with demo as subdomain and update the mappings. | Medium | 2026-03-19 | 2026-03-19 | Moswin | Completed | Production |  | 2 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 25-MAR-2026-1 | Analysis the Log for New joiner and fix the date time issue | Medium | 2026-03-25 | 2026-03-25 | Parthiban | Completed | Production |  | 0 | 0
| Adfactor Admin Dashboard | 25-MAR-2026-2 | Fix the alignment issue in the System Generated Post (Rich Text Editor) and after post | Medium | 2026-03-25 | 2026-03-25 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 25-MAR-2026-3 | check Date of joining update in Staging DB | Medium | 2026-03-25 | 2026-03-25 | Parthiban | Completed | Production |  | 0 | 0
www.dgda.gov.sa | DGDA Adoc 04 2026 | 26-MAR-2026-1 | Update the Almedad Mail Subject to English from arabic | Medium | 2026-03-26 | 2026-03-26 | Abhicheke | Completed | Production |  | 0 | 0
vajraglobal.com | Rackesh Training | 26-MAR-2026-2 | Train Reckesh to Monthly Maintance Report ,Form submision in DGDA and Farnborough | Medium | 2026-03-26 | 2026-03-26 | Parthiban | Completed | Local |  | 0 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 26-MAR-2026-3 | Check the Log for new joiner will present with Date Time format | Medium | 2026-03-26 | 2026-03-26 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 26-MAR-2026-4 | check the code base and auto generation post cause server issue | Medium | 2026-03-26 | 2026-03-26 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | Farnborough Weekly Report | 27-MAR-2026-1 | Weekly Form Export-Farborough | Medium | 2026-03-27 | 2026-03-27 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | Maintenance 04 2026 | 27-MAR-2026-2 | Form Test Farnborough Production and DGDA Preview | Medium | 2026-03-27 | 2026-03-27 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Admin Dashboard | 27-MAR-2026-3 | Check the Log for new joiner will present with Date Time format | Medium | 2026-03-27 | 2026-03-27 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | FIA Maintenance 04 2026 | 27-MAR-2026-4 | Listing all the pages with preformance score in Vennue | Medium | 2026-03-27 | 2026-03-27 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | FIA Maintenance 04 2026 | 27-MAR-2026-5 | Listing all the pages with preformance score in FIA | Medium | 2026-03-27 | 2026-03-27 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | FIA Maintenance 04 2026 | 30-MAR-2026-1 | Fix the performance issue for Mobile and desktop in Farnborough Vennue | Medium | 2026-03-30 | 2026-03-30 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | FIA Maintenance 04 2026 | 30-MAR-2026-2 | After fix the performance List all the pages again for Performance score | Medium | 2026-03-30 | 2026-03-30 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | FIA Maintenance 04 2026 | 31-MAR-2026-1 | Fix the Marked Low performance score pages to optimize speed in farnborough venue | Medium | 2026-03-31 | 2026-03-31 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | FIA Maintenance 04 2026 | 31-MAR-2026-2 | Test again all the marked pages Performance | Medium | 2026-03-31 | 2026-03-31 | Parthiban | Completed | Production |  | 0 | 0
farnboroughairshow.com | Farnborough Monthly Report | 31-MAR-2026-3 | check and add the task in Monthly maintance report for Farnborough and Intranet | Medium | 2026-03-31 | 2026-03-31 | Parthiban | Completed | Production |  | 0 | 0
www.dgda.gov.sa | DGDA |  | DGDA Sheet update for the past week | Medium | 2026-03-31 | 2026-03-31 | Moswin | Completed | Production |  | 1 | 1
farnboroughairshow.com | Maintenance 04 2026 | 1-APR-2026-1 | Test the all pages in staging compared with live for design layout functionality and forms after speed Optimize in FIA | Medium | 2026-04-01 | 2026-04-01 | Parthiban | Completed | Staging |  | 0 | 0
farnboroughairshow.com | SignUp Changes on FIA |  | Top Nav Popup section on the FIA | Medium | 2026-04-02 | 2026-04-02 | Abhicheke | Completed | Production |  | 0 | 0
www.dgda.gov.sa | Emergency services form |  | OTP Integration on DGDA Form resend logic using Mobi Shastra API | Medium | 2026-04-02 |  | Abhicheke | Waiting For Client Input | Local |  | 0 | 0 |  |  | .
farnboroughairshow.com | FIA Sign-Up Form Integration with Engage | 1-APR-2026-3 | Clone all farnborough projects and check there is using Engage API in Project | Medium | 2026-04-02 | 2026-04-02 | Parthiban | Completed | Local |  | 0 | 0 |  |  | Need to move the code after enage api fix
farnboroughairshow.com | FIA.com - Marketing Toolkit Page | 2-APR-2026-4 | Marketing Toolkit Page | Medium | 2026-04-02 | 2026-04-03 | Parthiban | Completed | Production |  | 12 | 0
farnboroughairshow.com | FIA2026: Aircraft & Agenda Pages |  | Whats on page Design Change | Medium | 2026-04-02 | 2026-04-07 | Abhicheke | Awaiting Client Feedback | Staging |  | 0 | 0 |  |  | Need to move the code after enage api fix | https://staging.farnboroughairshow.com/the-show/whats-on/
farnboroughairshow.com | FIA2026: Aircraft & Agenda Pages |  | Whats on page Design Change on POT | Medium | 2026-04-02 | 2026-04-07 | Abhicheke | Awaiting Client Feedback | Staging |  | 0 | 0 |  |  | Need to move the code after enage api fix | https://staging.farnboroughairshow.com/pioneers-of-tomorrow/whats-on/
farnboroughairshow.com | FIA2026: Aircraft & Agenda Pages |  | Aircraft Listing Mobile Design | Medium | 2026-04-06 | 2026-04-06 | Abhicheke | Awaiting Client Feedback | Staging |  | 0 | 0 |  | https://docs.google.com/document/d/19v8lP-ynYEOs90V00npsW9_5QUlLek1xcG8O2t615JI/edit?tab=t.0 | Need to move the code after enage api fix | https://staging.farnboroughairshow.com/the-show/aircraft-listing/
farnboroughairshow.com | FIA.com - Marketing Toolkit Page | 06-APR-2026-1 | Marketing toolkit page Fix | Medium | 2026-04-06 | 2026-04-06 | Parthiban | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Restore | 06-APR-2026-2 | Check the ADF DB in local and Drive | Medium | 2026-04-06 | 2026-04-06 | Parthiban | Completed | Local |  | 4 | 0
intranet.adfactorspr.com | Adfactor Restore | 06-APR-2026-3 | Restore all the Backup Production DB and check the latest blogs casestudy | Medium | 2026-04-06 | 2026-04-06 | Parthiban | Completed | Local |  | 5 | 0
www.dgda.gov.sa | DGDA Monitoring |  | DGDA monitoring sheet last week fill. | Medium | 2026-04-06 | 2026-04-06 |  | Completed | Production |  | 1 | 0 |  | DGDA Monitoring Activities
farnboroughairshow.com | FIA Sign-Up Form Integration with Engage | 07-APR-2026-1 | check the Current Engage APi and remove it and add Rest APIAdd common Service and link the rest API for FIA Forms | Medium | 2026-04-07 | 2026-04-07 | Parthiban | Completed | Local |  | 9 | 0
farnboroughairshow.com | FIA2026: Aircraft & Agenda Pages |  | Aircraft Listing Page Mobile Design Move to Production | Medium | 2026-04-07 | 2026-04-07 | Abhicheke | Awaiting Client Feedback | Staging |  | 0 | 0 |  |  | Need to move the code after enage api fix | https://staging.farnboroughairshow.com/the-show/whats-on/
farnboroughairshow.com | FIA2026: Aircraft & Agenda Pages |  | Whasts on page Client Feedback Changes | Medium | 2026-04-07 | 2026-04-07 | Abhicheke | Awaiting Client Feedback | Staging |  | 0 | 0 |  |  | Need to move the code after enage api fix | https://staging.farnboroughairshow.com/pioneers-of-tomorrow/whats-on/
farnboroughairshow.com | FIA.com - Marketing Toolkit Page | 06-APR-2026-1 | Marketing toolkit page Fix Client Feedback Changes | Medium | 2026-04-07 | 2026-04-07 | Abhicheke | Awaiting Client Feedback | Production |  | 0 | 0
farnboroughairshow.com | FIA Maintenance April 2026 |  | Error Analysis Report – farnboroughairshow.com fix | Medium | 2026-04-07 | 2026-04-07 | Abhicheke | In Progress | Production |  | 0 | 0
farnboroughairshow.com | FIA Maintenance April 2026 |  | Airshow full site cross testing and ads functionality on local | Medium | 2026-04-07 |  | Abhicheke | Completed | Local |  | 0 | 0
farnborough.com | FIA Maintenance April 2026 |  | Error Analysis for Farnborough Venue | Medium | 2026-04-07 | 2026-04-08 | Abhicheke | Completed | Production |  | 0 | 0
intranet.adfactorspr.com | Adfactor Restore | 08-APR-2026-1 | Test the Adfactors project and sso login | Medium | 2026-04-08 | 2026-04-08 | Parthiban | Completed | Production |  | 2 | 0
intranet.adfactorspr.com | Adfactor Restore | 08-APR-2026-2 | Analysis and Take the file path which is need for server restoreration and system requirement | Medium | 2026-04-08 | 2026-04-08 | Parthiban | Completed | Local |  | 2 | 0
farnboroughairshow.com | FIA Sign-Up Form Integration with Engage | 08-APR-2026-3 | Test the Engage API with Email notification Check the DB form is submited check the API respose with Breakpoint for All FIA Forms | Medium | 2026-04-08 | 2026-04-08 | Parthiban | Completed | Production |  | 3 | 0 |  | All Froms are tested with Engage API response DB present and user Email check
intranet.adfactorspr.com | Adfactor Restore | 08-APR-2026-4 | Analysis and Take the file path which is need for server restoreration and system requirement | Medium | 2026-04-08 | 2026-04-08 | Abhicheke | Completed | Local |  | 0 | 0
farnboroughairshow.com | FIA.com - Marketing Toolkit Page | 08-APR-2026-5 | Rackesh Training for create a fields on live and update the content and coding move to staging | Medium | 2026-04-08 | 2026-04-08 | Abhicheke | Completed | Production |  | 1 | 1
farnboroughairshow.com | Rackesh Training | 08-APR-2026-6 | Marketing toolkit page Create on live and update the content on live | Medium | 2026-04-08 | 2026-04-08 | Abhicheke | Completed | Production |  | 1 | 1
farnboroughairshow.com | Rackesh Training | 08-APR-2026-7 | Marketing toolkit page Create on live and update the content on live | Medium | 2026-04-08 | 2026-04-08 | Rackesh | Completed | Production |  | 2 | 2
farnboroughairshow.com | SignUp Changes on FIA | 08-APR-2026-8 | Top Nav Popup section on the FIA Button Color update logo and font size increase update | Medium | 2026-04-08 | 2026-04-08 | Rackesh | Completed | Production |  | 0 | 0
farnboroughairshow.com | FIA.com - Marketing Toolkit Page | 08-APR-2026-9 | Marketing Page Code Change to Value Method | Medium | 2026-04-08 | 2026-04-08 | Abhicheke | Completed | Production |  | 0 | 0
farnboroughairshow.com | FIA.com - Marketing Toolkit Page | 09-APR-2026-1 | Marketing toolkit page Move to live | Medium | 2026-04-09 | 2026-04-09 | Abhicheke | Completed | Production |  | 0.5 | 0.5 |  |  |  | https://farnboroughairshow.com/marketing-page/
farnboroughairshow.com | SignUp Changes on FIA | 09-APR-2026-2 | Top Nav Popup section Move to Production | Medium | 2026-04-09 | 2026-04-09 | Abhicheke | Completed | Production |  | 0.5 | 0.5
farnborough.com | Venue Maintenance April 2026 | 09-APR-2026-4 | CSP Error Fix on Venue | Medium | 2026-04-09 | 2026-04-09 | Abhicheke | Completed | Production |  | 3 | 3
farnboroughairshow.com | FIA Maintenance April 2026 | 09-APR-2026-4 | CSP Error Fix on FIA | Medium | 2026-04-09 | 2026-04-09 | Parthiban | Completed | Production |  | 3 | 2
farnboroughairshow.com | Expo Platform Changes | 09-APR-2026-6 | Expo Platform Aircraft Content Update | Medium | 2026-04-09 | 2026-04-09 | Parthiban | Completed | Production |  | 2 | 2.5
farnboroughairshow.com | Expo Platform Changes | 09-APR-2026-7 | Expo Platform WhatsOn Content Update | Medium | 2026-04-09 | 2026-04-09 | Parthiban | Completed | Production |  | 2 | 1.5
| Rackesh Training |  | Rackesh Training Aircraft and WhatsOn Content Update | Medium | 2026-04-09 | 2026-04-09 | Parthiban | Completed | Staging |  | 1 | 1
farnboroughairshow.com | Expo Platform Changes | 09-APR-2026-8 | Expo Platform Aircraft Content Update | Medium | 2026-04-09 | 2026-04-09 | Rackesh | Completed | Staging |  | 2 | 3
farnboroughairshow.com | Expo Platform Changes | 09-APR-2026-9 | Expo Platform WhatsOn Content Update | Medium | 2026-04-09 | 2026-04-09 | Rackesh | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 09-APR-2026-10 | Expo Platform Functionality Exhibitor | Medium | 2026-04-09 |  | Sowndar | Waiting for Client Input |  |  | 9 | 0
farnboroughairshow.com | Expo Platform Changes |  | Expo Platform Functionality Aircraft | Medium | 2026-04-09 |  | Sowndar | Waiting for Client Input |  |  | 9 | 0
farnboroughairshow.com | Expo Platform Changes |  | Expo Platform Functionality WhatsOn | Medium | 2026-04-09 |  | Sowndar | Waiting for Client Input |  |  | 9 | 0
intranet.adfactorspr.com | Adfactor Restore | 09-APR-2026-11 | Check All the pages in Adfactors and Mark in sheet | Medium | 2026-04-09 | 2026-04-09 | Parthiban | Completed | Local |  | 2 | 2
farnboroughairshow.com | SignUp Changes on FIA | 09-APR-2026-12 | Toggle Button for enable Book now and Sign up form | Medium | 2026-04-09 |  | Abhicheke | Completed | Production |  | 2 | 2 |  | Will complete the task of 10.4.26 First Half
farnborough.com | Farnborough Weekly Report | 10-APR-2026-1 | Weekly Form Export-Farborough | Medium | 2026-04-10 | 2026-04-10 | Parthiban | Completed | Production |  | 0.5 | 0.5 |  | Completed and shared to sai
farnboroughairshow.com | FIA Maintenance 04 2026 | 10-APR-2026-2 | Need to make the newsletter form sticky on the right hand side | Medium | 2026-04-10 | 2026-04-10 | Rackesh | Completed | Production |  | 1 | 1.5
farnboroughairshow.com | Rackesh Training | 10-APR-2026-3 | Need to make the newsletter form sticky on the right hand side | Medium | 2026-04-10 | 2026-04-10 | Abhicheke | Completed | Production |  | 0.5 | 1.5
farnborough.com | FIA Maintenance 04 2026 | 10-APR-2026-3 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-04-10 | 2026-04-10 | Parthiban | Completed | Production |  | 0.45 | 0.45 |  | Done and Updated in Sheet
farnboroughairshow.com | FIA2026: Aircraft & Agenda Pages | 09-APR-2026-3 | Client Feedback 1 Location Filter Location Sub Title Title Design Change Detail Page | Medium | 2026-04-09 |  | Abhicheke | Completed | Staging |  | 5 | 3.5 |  | Completed 75% of work Done Need to work on the Switch to Section Development Will complete the task of 10.4.26 First Half | Need to move the code after enage api fix
farnboroughairshow.com | FIA2026: Aircraft & Agenda Pages | 10-APR-2026-1 | Client Feedback 1 Switch to Section Development | Medium | 2026-04-10 | 2026-04-10 | Parthiban | Completed | Staging |  | 1.5 | 1.5 |  | Done Moved to staging and shared to sai | Need to move the code after enage api fix
www.dgda.gov.sa | National Design System (DGA) | 10-APR-2026-2 | Test the Home page | Medium | 2026-04-10 | 2026-04-10 | Parthiban | Completed | Local |  | 1 | 1 |  | Compleded testing with Fonts forn size and resposive for Desktop,Mobile and Ipads
www.dgda.gov.sa | Venue Maintenance April 2026 | 10-APR-2026-4 | Form Test Farnborough Production and DGDA Preview | Medium | 2026-04-10 | 2026-04-10 | Parthiban | Completed | Production |  | 1.5 | 1.5 |  | Submit all Forms in farnborough Production and DGDA preview
farnboroughairshow.com | FIA Sign-Up Form Integration with Engage | 10-APR-2026-5 | Change the API key and test the forms in FIA | Medium | 2026-04-10 | 2026-04-10 | Parthiban | Completed | Staging |  | 1 | 1 |  |  | Done in staging need to move live
farnborough.com | Venue Maintenance April 2026 |  | Venue Version Update 13.13.0 to 13.13.1 and cross test the entire site forms and functionality | Medium | 2026-04-10 | 2026-04-10 | Abhicheke | Completed | Production |  | 6 | 5
farnboroughairshow.com | Venue Maintenance April 2026 | 10-APR-2026-8 | check the Entire site with Forms ,menus,redirection,responsivenes after Version Update 13.13.0 to 13.13.1 | Medium | 2026-04-10 | 2026-04-10 | Parthiban | Completed | Production |  | 3.5 | 3.15 |  | Done all working fine
farnboroughairshow.com | FIA Maintenance 04 2026 | 13-APR-2026-1 | FIA Version Update 13.13.0 to 13.13.1 and cross test the entire site forms and functionality | Medium | 2026-04-13 | 2026-04-13 | Parthiban | Completed | Production |  | 5 | 2 |  | Done and moved to staging
farnboroughairshow.com | FIA Maintenance 04 2026 | 13-APR-2026-2 | Train Reckesh How to Update the version in umbraco and Move to staging in FIA | Medium | 2026-04-13 | 2026-04-13 | Parthiban | Completed | Local |  | 0.5 | 1 |  | Done and moved to staging
farnborough.com | Venue Maintenance April 2026 |  | Venue Staging Site Log check after version udpate and check the forms | Medium | 2026-04-13 | 2026-04-13 | Abhicheke | Completed | Production |  | 2 | 2
farnboroughairshow.com | Adfactor Restore | 13-APR-2026-5 | Restore the Old and new DB and share it in group List the table and make sheet what tables are need to add in server | Medium | 2026-04-13 | 2026-04-13 | Parthiban | Completed | Local |  | 1 | 1 |  | Done and share it in group
intranet.adfactorspr.com | Adfactor Restore | 13-APR-2026-6 | Version Update 13.9.2 to 13.13.1 in Adfactors | Medium | 2026-04-13 | 2026-04-13 | Parthiban | Completed | Local |  | 0.5 | 0.5 |  | Done in local need to move
farnboroughairshow.com | Adfactor Restore | 13-APR-2026-7 | Restore the DB scripts for update Table from dec to March in ADF share it in Drive | Medium | 2026-04-13 | 2026-04-13 | Parthiban | Completed | Local |  | 1 | 1 |  | Done and share it in group
vajraglobal.com | Umbraco Feature | 13-APR-2026-8 | Create a New Table in DB and count the page counts with page name URL and view counts | Medium | 2026-04-13 | 2026-04-14 | Parthiban | Completed | Local |  | 4 | 3 |  | Create a Table and do a functionaly for View count with recomented rule page count and page view count is working. But i face issue not all pages get the page name correctly some page name are getting null. Now its done
farnboroughairshow.com | Rackesh Training | 13-APR-2026-9 | FIA Version update 13.13.0 to 13.13.1 guide Parthiban and Rakesh | Medium | 2026-04-13 | 2026-04-13 | Abhicheke | Completed | Production |  | 2 | 1
farnboroughairshow.com | FIA testing | 13-APR-2026-10 | Cross test the entire FIA site and make note the error in console for the each page to fix that errors | Medium | 2026-04-13 | 2026-04-13 | Rackesh | Completed | Production |  | 6 | 7
farnboroughairshow.com | Umbraco Feature | 14-APR-2026-1 | "Add a new tables Page table and View log table adding futures Popular Content Ranking “Most Viewed” Page view counts,Most viewed (week),Trending (last 24h),Recently viewed (this browser) in backofice" | Medium | 2026-04-14 | 2026-04-14 | Parthiban | Completed | Local |  | 9 | 8.5
aerospaceglobalforum.com | Rackesh Training | 14-APR-2026-2 | How to take Db Backup and move to local via Ultrviewer and overview about iss server | Medium | 2026-04-14 | 2026-04-14 | Parthiban | Completed | Local |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA | 14-APR-2026-2 | DGDA Sheet update for the past week | Medium | 2026-03-31 | 2026-03-31 | Moswin | Completed | Production |  | 1 | 1
farnborough.com | Venue Maintenance April 2026 |  | Venue Version Update 13.13.0 to 13.13.1 move to live and cross test the entire site | Medium | 2026-04-15 |  | Abhicheke | Completed | Production |  | 5 | 5
farnboroughairshow.com | FIA Maintenance 04 2026 |  | FIA Site Version update from 13.13.0 to 13.13.1 move to live and cross test the entire site | Medium |  |  | Abhicheke | On Hold / Blocked | Production |  | 5 | 0 |  | Need to move the code after enage api fix
vajraglobal.com | Rackesh Training |  | Rackesh Laptop SQL Fix | Medium | 2026-04-15 | 2026-04-15 | Abhicheke | Completed | Local
farnboroughairshow.com | Umbraco Feature | 15-APR-2026-1 | Make the view count into models to call in anywhere in UI pages | Medium | 2026-04-15 | 2026-04-15 | Parthiban | Completed | Local |  | 4 | 3.45
| Vajra - Innovation | 15-APR-2026-2 | Vajra - Innovation -extern to Implementation steps umbraco support make it in sheet | Medium | 2026-04-15 | 2026-04-15 | Parthiban | Completed | Local |  | 3.5 | 3.15
| Vajra - Innovation | 15-APR-2026-2 | Vajra - Innovation get 5 ideas and analysis how to do that | Medium | 2026-04-15 | 2026-04-15 | Abhicheke | Completed | Local |  | 4 | 2
intranet.adfactorspr.com | Adfactor Restore | 15-APR-2026-4 | Adfactors PR - Intranet Restoration-meeting | Medium | 2026-04-15 | 2026-04-15 | Parthiban | Completed | Local |  | 0.5 | 1
farnborough.com | Venue Maintenance April 2026 | 15-APR-2026-5 | Venue site redirection form https://farnborough.com/ to https://www.farnborough.com/ on web.config | Medium | 2026-04-15 | 2026-04-15 | Abhicheke | Completed | Production |  | 0.5 | 0.5
| FIA Maintenance April 2026 | 15-APR-2026-7 | Add the tracking code on the 2 tickets page | Medium | 2026-04-15 | 2026-04-15 | Abhicheke | Completed | Production |  | 0.5 | 0.5
farnboroughinternationalstudios.com | Studio Maintenance 04 2026 | 16-APR-2026-2 | Fix the console error 500 (Internal Server Error) check the recaptcha 401 (Unauthorized) compare the API keys with live vs stagigng Submit all the forms and check in backofice Entire site crosstest in with responsive in farnboroughinternationalstudios in staging | Medium | 2026-04-16 | 2026-04-16 | Parthiban | Completed | Production |  | 5 | 5
intranet.adfactorspr.com | Adfactor Restore | 16-APR-2026-3 | Adfactors PR Intranet – Restoration Approach & Next Steps | Medium | 2026-04-16 | 2026-04-16 | Parthiban | Completed | Local |  | 0.5 | 0.5
intranet.adfactorspr.com | Adfactor Restore | 16-APR-2026-3 | Restore the current Academy Pages in local VPN connection and desktop connection Try to upload the files in adfactors server | Medium | 2026-04-16 | 2026-04-16 | Parthiban | Completed | Local |  | 2 | 1.5
farnboroughinternationalstudios.com | Rackesh Training | 16-APR-2026-4 | How to submit the forms and How to check the Entries for both Umbraco forms in backoffice and custom forms in ssms | Medium | 2026-04-16 | 2026-04-16 | Abhicheke | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | Qmatic Integration | 16-FEB-2026-5 | SMS API Testing | Medium | 2026-02-17 | 2026-02-17 | Abhicheke | Completed | UAT |  | 1 | 1
farnborough.com | Farnborough Weekly Report | 17-APR-2026-1 | Weekly Form Export-Farborough | Medium | 2026-04-17 | 2026-04-17 | Parthiban | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | Venue Maintenance April 2026 | 17-APR-2026-2 | Form Test Farnborough Production and DGDA Preview | Medium | 2026-04-17 | 2026-04-17 | Parthiban | Completed | Production |  | 2 | 2 |  | School Visit form didn't have Calendar Date so that form we cant test | Need to add dates in calender to resolve this issue
farnboroughairshow.com | FIA Maintenance April 2026 | 17-APR-2026-3 | Fix the FIA Accommodation issue | Medium | 2026-04-17 | 2026-04-27 | Parthiban | Completed | Production |  | 2 | 1.5 |  | Moved to Live
intranet.adfactorspr.com | Adfactor Restore | 17-APR-2026-4 | Move the files to intranet staging and fix the server to Host the staing site | Medium | 2026-04-17 | 2026-04-17 | Parthiban | Completed | Production |  | 4 | 5
vajraglobal.com | Vajra - Innovation | 17-APR-2026-5 | Analyis and upted the Current Market Competitor Our Advantage Feasibility Integration Approach API Cost / Pricing for Vajra-inovation | Medium | 2026-04-17 | 2026-04-17 | Parthiban | Completed | Production |  | 2 | 1.5
www.dgda.gov.sa | DGDA - Qmatic & E-services webpage | 17-FEB-2026-7 | DGDA - Qmatic & E-services webpage analysis | Medium | 2026-02-17 | 2026-02-17 | Abhicheke | Completed | Local |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore | 20-APR-2026-1 | Meeting With client to add the Database script in staging Database | Medium | 2026-04-20 | 2026-04-20 | Parthiban | Completed | Local |  | 0.5 | 0.5
intranet.adfactorspr.com | Adfactor Restore | 20-APR-2026-3 | Change the user name adfactorspr to Comms Desk in backofice and DB script | Medium | 2026-04-20 | 2026-04-20 | Parthiban | Completed | Production |  | 1 | 1 |  | Need to Update script in staging and live | Update the script in staging DB to check
intranet.adfactorspr.com | Adfactor Restore | 20-APR-2026-4 | Add Admin Dashboad in backofice and restore it in staging | Medium | 2026-04-20 | 2026-04-20 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore | 20-APR-2026-5 | Fix the issue in NBD Lead Registration Form | Medium | 2026-04-20 | 2026-04-20 | Parthiban | Completed | Production |  | 2 | 2 |  | Need Testing ID to move further | Need a Tesing ID Or client need to submit the for how its work
intranet.adfactorspr.com | Rackesh Training | 20-APR-2026-6 | Train to how restore the Db and use it connectionstring and instal the packages and run the project in ADF | Medium | 2026-04-20 | 2026-04-20 | Parthiban | Completed | Local |  | 0.5 | 0.5
intranet.adfactorspr.com | Adfactor Restore | 20-APR-2026-7 | Check all the functionality and backoffice page and upload images | Medium | 2026-04-20 | 2026-04-20 | Parthiban | Completed | Production |  | 2 | 3
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-1 | Restore the Academy page | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 2 | 1.5
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-2 | Fix the Excel formating issue | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 2 | 1
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-3 | Check and add the locations in Locations page | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-4 | Restore the rainmaker-s-leaderboard page | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-5 | Restore the cross-sell-initiative Page | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-6 | Restore the holiday-list-2026 pages | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 1 | 1.5
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-7 | Get and Test the DB query for delete all values in social DB | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 0.5 | 0.5
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-8 | Move to Live and test the entire functionality and Pages in ADF Live | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore | 21-APR-2026-9 | Add logo and Icons for missing pages | Medium | 2026-04-21 | 2026-04-21 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore | 20-Apr-2026-1 | DB Script update with Ashish | Medium | 2026-02-19 | 2026-02-19 |  | Completed | Production
intranet.adfactorspr.com | Adfactor Restore | 20-Apr-2026-1 | Adfactor - Media Folder Changes | High | 2026-04-20 | 2026-04-20 |  | Completed | Production |  |  | 0
intranet.adfactorspr.com | Adfactor Restore | 20-Apr-2026-2 | Adfactor - Permission | High | 2026-04-20 | 2026-04-20 |  | Completed | Production |  |  | 0
intranet.adfactorspr.com | Adfactor Restore | 20-Apr-2026-2 | Adfactor - Live | High | 2026-04-20 | 2026-04-20 |  | Completed | Production |  |  | 0
intranet.adfactorspr.com | Adfactor Restore | 19-Apr-2026-1 | NDB Form Testing | Medium | 2026-04-20 | 2026-04-20 |  | Completed | Production |  |  | 0 |  | Since we don't have user id vishal will check and come back to us
intranet.adfactorspr.com | Adfactor Restore | 21-Apr-2026-2 | Update the content for 8 pages in Adf Staging Site and Decathlon excel file data format fix | Medium | 2026-04-21 | 2026-04-21 | Abhicheke | Completed | Production |  | 6 | 6
intranet.adfactorspr.com | Adfactor Restore | 21-Apr-2026-3 | Update the icon for 4 pages around 30+ icons on the live | High | 2026-04-21 | 2026-04-21 | Abhicheke | Completed | Production |  | 3 | 3
intranet.adfactorspr.com | Adfactor Restore | 21-Apr-2026-4 | Cross test the entire site after move to live | High | 2026-04-21 | 2026-04-21 | Abhicheke | Completed | Production |  | 2 | 1.5
intranet.adfactorspr.com | Adfactor Restore | 22-Apr-2026-1 | test the entire functionality and Pages in ADF Live Chsnge the database name and moved to staging | Medium | 2026-04-22 | 2026-04-22 | Parthiban | Completed | Production |  | 5 | 5
intranet.adfactorspr.com | Adfactor Restore | 22-Apr-2026-2 | Remove the recomented pages in Live | Medium | 2026-04-22 | 2026-04-22 | Parthiban | Completed | Production |  | 2 | 1
intranet.adfactorspr.com | Adfactor Restore | 22-Apr-2026-3 | Add and remove some links on footer | Medium | 2026-04-22 | 2026-04-22 | Abhicheke | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | Research Inquiry Forms | 22-Apr-2026-4 | Research Inquiry forms development and add the form on 3 sections | Medium | 2026-04-22 | 2026-04-23 | Abhicheke | Under Review & Testing | UAT |  | 8 | 7.5 |  | Card 2 (Currently, we have updated the description content with lorem ipsum.) Card 3 (Currently, we have updated the description content with lorem ipsum. The triangle design is used for all promotion sections, so I have used the same for this section as well. If you would like to change the icon, please let me know.) | Need Arabic content and Description Form need to map on c4c | Payload Link Page Url Card 1 Card 2 (Currently, we have updated the description content with lorem ipsum.) Card 3 | https://docs.google.com/presentation/d/1bVxbVlIFbB2UTiBRq-zjlK58qrXlAQva0RuVYrTzLtY/edit?slide=id.p6#slide=id.p6
intranet.adfactorspr.com | Adfactor Restore | 22-Apr-2026-5 | Remove the dates of the next month Post in behalf of Adfactors Copyright 2025 to be removed change different font size for different post Align the User profile pic to the fields Need admin and super admin access for vishal | Medium | 2026-04-22 | 2026-04-22 | Parthiban | Completed | Production |  | 3 | 2.5
intranet.adfactorspr.com | Adfactor Restore | 22-Apr-2026-7 | Cross test the entire site after move to live | Medium | 2026-04-22 | 2026-04-22 | Rackesh | Completed | Production |  | 4 | 3
vajraglobal.com | Vajra - Innovation | 22-Apr-2026-8 | Vajra Innovation Initiative – Idea Research & Feasibility Analysis | Medium | 2026-04-22 | 2026-04-22 | Rackesh | Completed | Local |  | 6 | 6
intranet.adfactorspr.com | Adfactor Restore | 21-Apr-2026-9 | Cross test the entire site after move to live | Medium | 2026-04-22 | 2026-04-22 | Abhicheke | Completed | Production |  | 0.5 | 0.5
intranet.adfactorspr.com | Adfactor Restore | 24-Apr-2026-2 | Download and Move the Profile pic images to staging and Test it | Medium | 2026-04-24 | 2026-04-24 | Parthiban | Completed | Staging |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore | 24-Apr-2026-1 | Restore the Profile picture in social feed and other pages | Medium | 2026-04-24 | 2026-04-24 | Parthiban | Completed | Production |  | 4 | 5 |  |  | Need to check Realuser profile picture in social feed Update the the lateast Live DB to staging to check the user profile pic. or else we need Real User SSO Login credential for testing
intranet.adfactorspr.com | Adfactor Restore | 24-Apr-2026-3 | Restore the Profile picture in Birthday Workanniversary | Medium | 2026-04-24 | 2026-04-24 | Parthiban | Completed | Production |  | 2 | 2 |  |  | There is No images for New Joiner.
farnboroughinternationalstudios.com | Rackesh Training | 24-Apr-2026-2 | Teach the Rackesh about the version update on the Stuidio site | Medium | 2026-04-24 | 2026-04-24 | Abhicheke | Completed | Production |  | 4 | 4
farnboroughinternationalstudios.com | Studio Maintenance 04 2026 | 24-Apr-2026-3 | Studio Site Version update from 13.13.0 to 13.13.1 move to Live and cross test the entire site | Medium | 2026-04-24 | 2026-04-24 | Abhicheke | Completed | Production |  | 4 | 4
www.dgda.gov.sa | DGDA | 14-APR-2026-2 | DGDA Sheet update for the past 1.5 weeks | Medium | 2026-04-24 | 2026-04-24 | Moswin | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore | 27-Apr-2026-1 | Restore the Profile picture in social feed and other pages | Medium | 2026-04-27 | 2026-04-27 | Parthiban | Completed | Production |  | 4 | 4
intranet.adfactorspr.com | Adfactor Restore | 27-Apr-2026-2 | Create a Admindashboard in staging and add logger to check the tagged notifications for that user | Medium | 2026-04-27 | 2026-04-27 | Parthiban | Completed | Production |  | 3 | 3 |  | Need permission in WAF service | Need to create a new image folder and give permisson to that folder then only system generated post saved in db and show it in social feed
intranet.adfactorspr.com | Adfactor Restore | 27-Apr-2026-3 | 10 elements for AE, AM, and Team Decathlon Content update | Medium | 2026-04-27 | 2026-04-27 | Abhicheke | Completed | Production |  | 2.5 | 2.5 |  |  |  | https://intranet.adfactorspr.com/ae-decathlon-30/ Decathlon FAQs, Timelines, Rules, and Explanations (old page) https://intranet.adfactorspr.com/am-decathlon-20/ Decathlon FAQs, Timelines, Rules, and Explanations (old page) https://intranet.adfactorspr.com/team-decathlon-30/ Other Information (old page)
intranet.adfactorspr.com | Adfactor Restore | 27-Apr-2026-4 | Create a post in System generetaed post and check the Permissons in server | Medium | 2026-04-27 | 2026-04-27 | Parthiban | Completed | Production |  | 2 | 1 |  | Need permission in WAF service
intranet.adfactorspr.com | Adfactor Restore | 27-Apr-2026-5 | Article detail page article info featch from Db and backoffice logic fix | Medium | 2026-04-27 | 2026-04-27 | Abhicheke | Completed | Staging |  | 2 | 2
www.dgda.gov.sa | Research Inquiry Forms | 28-Apr-2026-1 | Please place the 3rd card between the programs and digital library on the Learn At Diriyah Page | Medium | 2026-04-28 | 2026-04-28 | Abhicheke | Completed | UAT |  | 1 | 1 |  |  |  | https://feat-research-inquiry.d38541r9nlp4br.amplifyapp.com/en/learn-at-diriyah
farnboroughairshow.com |  | 28-Apr-2026-2 | Take the Farnborough site DB Backup | Medium | 2026-04-28 | 2026-04-28 | Abhicheke | Completed | Production |  | 2 | 0
intranet.adfactorspr.com | Adfactor Restore | 28-Apr-2026-3 | Check all the 403 forbiden API url in network tab and Note it for whitelist | Medium | 2026-04-28 | 2026-04-28 | Parthiban | Completed | Production |  | 2 | 2
farnboroughairshow.com | FIA Maintenance April 2026 | 28-Apr-2026-4 | Clone a new project and fix the engage API | Medium | 2026-04-28 | 2026-04-28 | Parthiban | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore | 28-Apr-2026-5 | fix the changes.The icon size should increase Copy URL, it is not showing the posted person name Privacy Policy - Remove SGP, creative dimensions | Medium | 2026-04-28 | 2026-04-28 | Parthiban | Completed | Local |  | 2 | 1.5
intranet.adfactorspr.com | Adfactor Restore | 28-Apr-2026-5 | Edit Delete options for Company post | Medium | 2026-04-28 | 2026-04-28 | Parthiban | Completed | Local |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore | 28-Apr-2026-6 | Enable/Disable Toggle for System Generated Posts | Medium | 2026-04-28 | 2026-04-28 | Parthiban | Completed | Local |  | 2 | 2.5
www.dgda.gov.sa | Emergency services form | 28-Apr-2026-8 | GIS Api Testing on the postman and call with client and test the SMS API | Medium | 2026-04-28 | 2026-04-28 | Abhicheke | Completed | UAT |  | 6 | 6
intranet.adfactorspr.com | Adfactor Admin Dashboard | 29-Apr-2026-1 | Coding Done Check Employe Id fetch from Db in Staging | Medium | 2026-04-29 | 2026-04-29 | Parthiban | Completed | Production |  | 2 | 0.5 |  | Code fixed in local need to move staging and check Emp ID is receive | Sever show Please Wait message
intranet.adfactorspr.com | Adfactor Restore | 29-Apr-2026-2 | Alert message-Remove all the browser allert and add a popup alert for every functions | Medium | 2026-04-29 | 2026-04-29 | Parthiban | Completed | Local |  | 2 | 3 |  | Browser alert message Remove and add Altert popup Once Fix the server Moved to Staging and check | Sever show Please Wait message
www.dgda.gov.sa |  | 29-Apr-2026-3 | For some users the AlMedad not submit because of the many characters the payload size is high fix that issue on the form | Medium | 2026-04-29 | 2026-04-29 | Abhicheke | Completed | Production |  | 1 | 1 |  |  |  | https://main.d3jcmxm4xwijj.amplifyapp.com/en/contact-us/AlMedad
intranet.adfactorspr.com | FIA Maintenance April 2026 | 29-Apr-2026-4 | FIA-Moved to staging FIA Form Submit and check it in DB and Mail List all the checklist ID for all Forms | Medium | 2026-04-29 | 2026-04-29 | Parthiban | Completed | Local |  | 1 | 1.5
intranet.adfactorspr.com | Adfactor Restore | 29-Apr-2026-5 | Test all functionality after Live DB restore | Medium | 2026-04-29 | 2026-04-29 | Parthiban | Completed | Local |  | 1 | 2 |  | User Profile pic is missing need to check kajol profile is updated in server Stil facing 403 forbiden Error in system generated post | Need t check in sever for kajol profile is updated and check the permissons is give for system generated post URL
intranet.adfactorspr.com | Adfactor Restore | 29-Apr-2026-6 | Update Holiday list In staging and Live Updated the Company post username as Display name | Medium | 2026-04-29 | 2026-04-29 | Parthiban | Completed | Local |  | 1 | 1
intranet.adfactorspr.com | Demo Page | 29-Apr-2026-6 | Clone a Class of 2038 page in Aboutus and add content in staging and live | Medium | 2026-04-29 | 2026-04-29 | Parthiban | Completed | Production |  | 1 | 0.5 |  | Pages are cloned and unpublished Need content to update Folow up with sai 30/04/2026 | Content is needed from client
www.dgda.gov.sa | Emergency services form | 29-Apr-2026-7 | SMS API Production URL Document Testing | Medium | 2026-04-28 | 2026-04-28 | Abhicheke | On Hold / Blocked | UAT |  | 2 | 2 |  |  | I tried both No Auth and Basic Auth username - ffffa747-d38b-3971-83e5-facd68d4fd40 Password - SAPCPI_SMS__API_OAUTH_e650058 but it show unauthorized_client
www.dgda.gov.sa |  | 29-Apr-2026-8 | Check the DGDA logs to see if there have been any issues on the site over the last 30 days. | Medium | 2026-04-29 | 2026-04-29 | Abhicheke | Completed | Production |  | 4 | 4
www.dgda.gov.sa |  |  | Send 1 month logs to Abhicheke for preview preprod environment | Medium | 2026-04-29 | 2026-04-29 | Moswin | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore | 29-Apr-2026-10 | Leadership Team enhancement:implemented Umbraco-driven designation grouping (via LeadershipDesignation dropdown), preserved person-specific titles, and fixed blank-selection behavior by enforcing mandatory designation validation. | Medium | 2026-04-29 | 2026-04-30 | Rackesh Kumaran | Completed | Local
www.dgda.gov.sa |  |  | DGDA monitoring sheet last week fill. | Medium | 2026-04-30 | 2026-04-30 | Moswin | In Progress | Local |  | 1 | 0
intranet.adfactorspr.com | Adfactor Restore | 30-Apr-2026-1 | upload content on the Power of One Guidelines page.staging and live | Medium | 2026-04-30 | 2026-04-30 | Parthiban | Completed | Production |  | 1 | 1.5
farnboroughairshow.com | FIA Maintenance April 2026 | 30-Apr-2026-2 | we need to remove the newsletter email ID from the post detail page & place a sign-up form which will have the same pop-up form utilised on the Navigation bar. | Medium | 2026-04-30 | 2026-04-30 | Abhicheke | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Exhibitor Listing | 30-Apr-2026-2 | Exhibitor Listing Count, mismatch | Medium | 2026-04-29 | 2026-04-29 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Rackesh Training | 30-Apr-2026-3 | Monitor rackesh for Leadership-Team page | Medium | 2026-04-29 | 2026-04-29 | Parthiban | Completed | Local |  | 1 | 2
intranet.adfactorspr.com | Adfactor Restore May | 30-Apr-2026-4 | Test the Adfactors staging Functionality | Medium | 2026-04-30 | 2026-04-30 | Parthiban | Completed | Staging |  | 2 | 2.15
intranet.adfactorspr.com | FIA Maintenance April 2026 | 30-Apr-2026-5 | FIA-Moved to staging Delete the Exbhitor values in staging DB | Medium | 2026-04-30 | 2026-04-30 | Parthiban | Completed | Staging |  | 0.5 | 0.5
www.dgda.gov.sa |  | 30-Apr-2026-6 | check the List of task in DGDA Feb to aprl Updated the project tracker sheet Feb to aprl | Medium | 2026-04-30 | 2026-04-30 | Parthiban | Completed | Local |  | 1 | 0
farnboroughairshow.com | FIA Maintenance April 2026 | 01-May-2026-1 | FIA-Moved to Live Submit the Forms Test all the pages in live | High | 2026-05-01 | 2026-05-01 | Parthiban | Completed | Production |  | 3 | 2
intranet.adfactorspr.com | Adfactor Restore May | 04-May-2026-1 | ADF-April Task list | Medium | 2026-05-04 | 2026-05-04 | Parthiban | Completed | Local |  | 1 | 1
farnboroughairshow.com | FIA Maintenance April 2026 | 04-May-2026-2 | Test the Entire pages in FIA Live | Medium | 2026-05-04 | 2026-05-04 | Parthiban | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Demo Page | 04-May-2026-3 | Add Content in Demon Farm page in staging | Medium | 2026-05-04 | 2026-05-04 | Parthiban | Completed | Staging |  | 2 | 2
intranet.adfactorspr.com | Demo Page |  | Add Content in Demon Farm page and move to live | Medium |  |  | Parthiban | Pipeline / To Do | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore May | Change the server settings for pool Always running in staging Test system generated post in staging | 1. The names need to be in alphabetical order. 2. Confirm only the people who are part of the Demon Farm cohort have access to the Knowledge Hub. 3. Change the text in the knowledge hub to say "The Knowledge Hub is designed to be an exclusive and collaborative space for you as members of the Class of 2038. Whether it’s industry developments, leadership lessons, or simply resources you’ve found useful, this is where we can learn from each other and grow together." 4. Add the same banner we have used in Class of 2038 for the Knowledge Hub in this as well. | Medium | 2026-05-04 | 2026-05-04 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore May | 04-May-2026-5 | Add Acess for Kajol and hemant.gaule for knowledge hub button | Medium | 2026-05-04 | 2026-05-04 | Parthiban | Completed | Production |  | 1 | 1 | Access is handeled in coding by manish not in backofice
intranet.adfactorspr.com | Adfactor Restore May | 04-May-2026-6 | Fix the profile Pic Falback to default while 30min idile site | Medium | 2026-05-04 | 2026-05-04 | Parthiban | Completed | Production |  | 3 | 2
farnboroughairshow.com | FIA Maintenance May 2026 | 04-May-2026-7 | farnboroughairshow full site cross testing | Medium | 2026-05-04 | 2026-05-04 | Rackesh Kumaran | Completed | Production |  | 2 | 1
intranet.adfactorspr.com | Adfactor Restore May | 04-May-2026-8 | In Adfactors creating the field and updating the pics for the each individual in the leadership team | Medium | 2026-05-04 | 2026-05-04 | Rackesh Kumaran | Completed | Staging |  | 3 | 2
intranet.adfactorspr.com | Adfactor Restore May | 04-May-2026-9 | Testing the adfactors demon-farm employee list | Medium | 2026-05-04 | 2026-05-04 | Rackesh Kumaran | Completed | Staging |  | 1 | 1
N8N automation | learning | 04-May-2026-10 | Learning the n8n automation tool for the automation& intial setup | Low | 2026-05-04 | 2026-05-04 | Rackesh Kumaran | Completed | Local |  | 1 | 1
Automation SEO/AEO Tool | Vajra - Intranet | 04-May-2026-11 | Automation SEO/AEO Tool : learning to understand the automated process for this tool and code structure from the n8n automation | Medium | 2026-05-04 | 2026-05-04 | Rackesh Kumaran | Completed | Local |  | 0 | 0
Frontend Setup for the Automation SEO/AEO Tool | learning | 04-May-2026-12 | learning react for the frontend setup for this project is started | Medium | 2026-05-04 | 2026-05-04 | Rackesh Kumaran | Completed | Local |  | 0 | 0
Daily Monitoring site cross test and Update in sheet | Site Cross testing | 04-May-2026-13 | Site cross testing for the entire projects Farnborough & Dgda | High | 2026-05-04 | 2026-05-04 | Rackesh Kumaran | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore May | 04-May-2026-14 | Take the unused fields name list on the intranet Sheet Link take the fields name and check with the coding | Medium | 2026-05-04 | 2026-05-04 | Abhicheke | Completed | Production |  | 5 | 5
intranet.adfactorspr.com | Core Value Page | 04-May-2026-15 | Core Value Image Update | Medium | 2026-05-04 | 2026-05-04 | Abhicheke | Completed | Production |  | 0.5 | 0.5
intranet.adfactorspr.com | Content Update May | 05-May-2026-1 | Remove the campaign Link in awards sheet and upload in Awards page | Medium | 2026-05-05 | 2026-05-05 | Parthiban | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore May | 05-May-2026-2 | Fix the Awards show null issue | Medium | 2026-05-05 | 2026-05-05 | Parthiban | Completed | Production |  | 2 | 2
farnboroughairshow.com | FIA Maintenance May 2026 | 05-May-2026-3 | Farnborough International Airshow 2026 - API sheet | Medium | 2026-05-05 |  | Abhicheke | Under Review & Testing | Local |  | 4 | 4 |  |  |  | Changes on Farnborough International Airshow 2026 - API sheet
intranet.adfactorspr.com | Content Update May | 05-May-2026-4 | Update the sheet and uplod content in AE, AM, Team Decathlon, | Medium | 2026-05-05 | 2026-05-05 | Parthiban | Completed | Production |  | 2 | 2.15
www.dgda.gov.sa | Quamatic Integration | 05-May-2026-4 | Booking Appointment DGDA | Medium | 2026-05-05 | 2026-05-05 | Abhicheke | On Hold / Blocked | Local |  | 9 | 3
intranet.adfactorspr.com | Content Update May | 05-May-2026-6 | Updated content in Live | Medium | 2026-05-05 | 2026-05-05 | Parthiban | Completed | Production |  | 2 | 1
Daily Monitoring site cross test and Update in sheet | Site Cross testing | 05-May-2026-7 | Site cross testing for the entire projects Farnborough & Dgda | High | 2026-05-05 | 2026-05-05 | Rackesh Kumaran | Completed | Production |  |  | 0
Automation SEO/AEO Tool | Vajra - Intranet | 05-May-2026-8 | start to understanding n8n automation and learning the project setup | Medium | 2026-05-05 | 2026-05-05 | Rackesh Kumaran | Completed | Local |  |  | 0
intranet.adfactorspr.com | Adfactor Restore May | 05-May-2026-9 | Fix and move the Awards and decathlon page to live | Medium | 2026-05-05 | 2026-05-05 | Abhicheke | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore May | 05-May-2026-10 | Fix and move the Awards and decathlon pages to live and test | Medium | 2026-05-05 | 2026-05-05 | Parthiban | Completed | Production |  | 2 | 2
New Adoptation CMS | Adobe Experience Manager and WorkFront | 05-May-2026-11 | Research and Analysis the New adaptation of the Adobe Experience Manager , Adobe WorkFlow Front to create the website | Medium | 2026-05-05 | 2026-05-05 | Rackesh Kumaran | Completed | Local |  |  | 0
intranet.adfactorspr.com | Intranet Tech Queries | 05-May-2026-12 | Intranet Tech Queries | Medium | 2026-05-05 | 2026-05-06 |  | Completed | Production |  | 6 | 6
farnboroughairshow.com | FIA Maintenance April 2026 | 06-May-2026-1 | Identify the Meeting and Conference Rooms Form and test the form data export and convert that from json format | Medium | 2026-05-06 | 2026-05-06 | Abhicheke | Completed | Production |  | 1.5 | 1.5 |  |  |  | https://docs.google.com/spreadsheets/d/1ChWS3hmJFcLYzmbwYPVmVEDXxkqJ8Ry1xaTtTv7zu3c/edit?gid=0#gid=0
intranet.adfactorspr.com | Adfactor Restore May | 06-May-2026-2 | Server cross test follow up | Medium | 2026-05-06 | 2026-05-06 | Parthiban | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore May | 06-May-2026-3 | Replace the live media folder to staging | Medium | 2026-05-06 | 2026-05-06 | Abhicheke | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore May | 06-May-2026-4 | Move the leadership page to staging and move dll to site | Medium | 2026-05-06 | 2026-05-06 | Abhicheke | Completed | Production |  | 3 | 3
intranet.adfactorspr.com | Adfactor Restore May | 06-May-2026-5 | Update the profile pic in comments and reply Add Logo profile pic for Company posts Add toggle in backofice | Medium | 2026-05-06 | 2026-05-07 | Parthiban | Completed | Production |  | 2 | 7 |  | Facing issue in server 500 error after moved dll for everysingle time
intranet.adfactorspr.com | Adfactor Restore May | 07-May-2026-1 | only the “Directors” heading to be hidden. Not the whole section logic on the leadership page if there is no description content need no need to show the hover effect and no need to go to single page | Medium | 2026-05-07 | 2026-05-07 | Abhicheke | Completed | Staging |  | 1.5 | 1.5 |  |  |  | https://intranetstaging.adfactorspr.com/about-us/leadership-team-new/
farnboroughairshow.com | FIA Maintenance April 2026 | 07-May-2026-2 | FAQ Page H1,H2,H3 Formating ul and li fix | Medium | 2026-05-07 | 2026-05-07 | Abhicheke | Completed | Production |  | 2.5 | 2.5
intranet.adfactorspr.com | Adfactor Restore May | 07-May-2026-3 | Fix the Name conversion and Emplyoyee ID in post moderation | Medium | 2026-05-07 | 2026-05-07 | Parthiban | Completed | Staging |  | 2 | 1
vajraglobal.com | Adobe Experience Manager and WorkFront | 07-May-2026-4 | Adobe Experience Manger learning, research & explore how this similar with existing CMS (sitecore) and make the initial starter documentation | Medium | 2026-05-07 | 2026-05-08 | Rackesh Kumaran | Completed | Local |  | 17 | 15
intranet.adfactorspr.com | Adfactor Restore May | 07-May-2026-5 | Leadership Team page content added on live and sort by alphabet order | Medium | 2026-05-07 | 2026-05-07 | Abhicheke | Completed | Production |  | 3 | 3
intranet.adfactorspr.com | Adfactor Restore May | 07-May-2026-5 | Testing the Leadership Team page in the live | Medium | 2026-05-07 | 2026-05-07 | Rackesh Kumaran | Completed | Production |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) | 07-May-2026-6 | National Design System design apply for all pages | Medium | 2026-05-07 | 2026-05-14 | Abhicheke | Under Review & Testing | UAT |  | 30 | 22.5
intranet.adfactorspr.com | Adfactor Restore May | 07-May-2026-7 | Fix 403 Forbiden Error in autogenerated posts and Profile Pic | Medium | 2026-05-07 | 2026-05-08 | Parthiban | Completed | Production |  | 5 | 4
intranet.adfactorspr.com | Content Update May | 07-May-2026-8 | Update content in Awards page for 2022 2023,2024 staging | Medium | 2026-05-07 | 2026-05-07 | Parthiban | Completed | Production |  | 4 | 3
farnboroughairshow.com | FIA Maintenance April 2026 | 07-May-2026-10 | Changes on Farnborough International Airshow 2026 - API sheet , in this sheet i worked in the 'Any category section' by remove the tags and make updates the values in the sheet | Medium | 2026-05-07 | 2026-05-07 | Rackesh Kumaran | Completed | Production |  | 2 | 1.5
intranet.adfactorspr.com | Intranet Tech Queries | 05-May-2026-11 | Intranet Tech Queries | Medium | 2026-05-05 | 2026-05-06 | Sowndar | Completed | Production |  | 0.5 | 0.5
intranet.adfactorspr.com | Content Update May | 08-May-2026-1 | Update content in Awards page for 2022 2023,2024 in Live | Medium | 2026-05-08 | 2026-05-08 | Parthiban | Completed | Production |  | 2 | 1.5
farnboroughairshow.com | FIA Maintenance April 2026 | 08-May-2026-2 | Remove Any Priority Drop-down & Priorities list on the pop-up on the Exhibitor Listing page Change this logo to the FIA2026 | Medium | 2026-05-08 | 2026-05-08 | Abhicheke | Completed | Staging |  | 2 | 0 | Need to move from git history
farnboroughairshow.com | FIA Maintenance April 2026 | 08-May-2026-3 | Need to add a new image field on the What's On detail page for mobile App API which donot need to showcase on the website | Medium | 2026-05-08 | 2026-05-08 | Abhicheke | Completed | Production |  | 0.5 | 0.5
intranet.adfactorspr.com | Content Update May | 08-May-2026-4 | Align the gold silver bronze in 2022 2023 2024 in award page in live | Medium | 2026-05-08 | 2026-05-08 | Parthiban | Completed | Production |  | 2 | 1.5 | Align the Order Gold silver bronze in all sheets and update again
intranet.adfactorspr.com | Adfactor Restore May | 08-May-2026-5 | Enable the profile pic in auto generated post | Medium | 2026-05-08 | 2026-05-08 | Parthiban | Completed | Production |  | 3 | 3
intranet.adfactorspr.com | Adfactor Restore May | 08-May-2026-6 | Remove the Exposed logs in code which is show in backofice | Medium | 2026-05-08 | 2026-05-08 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Analysis and Documnet | 08-May-2026-7 | Anaysis the Intranet Integration - Technical Questions Mail and make document | Medium | 2026-05-08 | 2026-05-08 | Parthiban | Completed | Production |  | 1 | 2 |  |  |  | Intranet_Pipedrive_API_Integration_Response
intranet.adfactorspr.com | Content Update May | 08-May-2026-8 | Update content in Awards page for 2022 2023,2024 in Live | Medium | 2026-05-08 | 2026-05-08 | Rackesh Kumaran | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore May | 11-May-2026-3 | Analysis the Pipedrive in coding | Medium | 2026-05-11 | 2026-05-11 | Parthiban | Completed | Local |  | 2 | 1.5
intranet.adfactorspr.com | Adfactor Restore May | 11-May-2026-4 | Remove the Session cookie for Profile pic and change it to Authenticated cookie to show profile pic | Medium | 2026-05-11 | 2026-05-11 | Parthiban | Completed | Production |  | 2 | 2 | Remove the session cookie because profile pic unauthorize after 30 Minutes of inactivity
intranet.adfactorspr.com | Adfactor Restore May | 11-May-2026-5 | changed the seession cookie to Authenticated cookie for CommentsController (GetComments and other comment endpoints) PostsController (feed + actions) UsersController (/api/Users/current) MediaController (uploads) RealUserService (author info) becuase of 30min inactivity Test the Entire staging site | Medium | 2026-05-11 | 2026-05-11 | Parthiban | Completed | Production |  | 3 | 4 | Remove the session cookie because profile pic unauthorize after 30 Minutes of inactivity
farnboroughairshow.com | FIA Maintenance May 2026 | 11-May-2026-6 | Test the idex and no idex in Venue and Airshow Live & staging | Medium | 2026-05-11 | 2026-05-11 | Parthiban | Completed | Production |  | 1 | 1
farnboroughairshow.com | FIA Maintenance May 2026 | 11-May-2026-7 | check and learn how to fix the issue of the webcrawl of the staging site files like media are showing in the browser while searching for the live site in the browser | Medium | 2026-05-11 | 2026-05-11 | Rackesh Kumaran | Completed | Staging |  | 3 | 3
intranet.adfactorspr.com | Adfactor Restore May | 11-May-2026-8 | make fix the spacing issue in between the section of the leadershipteam new page | Medium | 2026-05-11 | 2026-05-11 | Rackesh Kumaran | Completed | Staging |  | 2 | 2
vajraglobal.com | Site Cross testing | 11-May-2026-9 | Site cross testing for the entire projects Farnborough & Dgda | Medium | 2026-05-11 | 2026-05-11 | Rackesh Kumaran | Completed | Production |  | 1 | 1
vajraglobal.com | Seo Automation Tool | 11-May-2026-10 | started to make the frontend project setup for the Seo Internal tool | Medium | 2026-05-11 | 2026-05-11 | Rackesh Kumaran | Completed | Production |  | 3 | 3
www.dgda.gov.sa |  | 12-May-2026-1 | Set DGDA Codebase with Abhicheke ID | High | 2026-05-12 | 2026-05-12 | Parthiban | Completed | Local |  | 2 | 1.5
intranet.adfactorspr.com | Adfactor Restore May | 12-May-2026-2 | Change the server settings Always running in staging Test system generated post in staging | Medium | 2026-05-12 | 2026-05-12 | Parthiban | Completed | Production |  | 1 | 1.5 | Need to do same for Live
intranet.adfactorspr.com | Adfactor Restore May | 12-May-2026-3 | Fix the already been declared console error in Home page | Medium | 2026-05-12 | 2026-05-12 | Parthiban | Completed | Production |  | 1 | 1
farnboroughairshow.com | FIA Maintenance May 2026 | 12-May-2026-4 | Analyis the Expoplatform in FIA coding | Medium | 2026-05-11 |  | Parthiban | Pipeline / To Do | Staging |  | 2 | 0
intranet.adfactorspr.com | Content Update May | 12-May-2026-5 | Remove the Rakesh Aulaya from leadership page in Live and staging | Medium | 2026-05-12 | 2026-05-12 | Parthiban | Completed | Production |  | 0.15 | 0.15
intranet.adfactorspr.com | Adfactor Restore May | 12-May-2026-6 | Fix the Academy page rendering issue while scroll | Medium | 2026-05-12 | 2026-05-12 | Parthiban | Completed | Production |  | 2 | 1
www.dgda.gov.sa | National Design System (DGA) | 12-May-2026-7 | check the National Design System compared to design | Medium | 2026-05-11 | 2026-05-11 | Parthiban | Completed | Local |  | 2 | 4 |  | Page Not found
www.dgda.gov.sa | National Design System (DGA) | 12-May-2026-8 | National Design System Error fix | Medium | 2026-05-12 | 2026-05-12 | Abhicheke | Completed | UAT |  | 4 | 4
www.dgda.gov.sa | National Design System (DGA) | 12-May-2026-9 | Update the outdated packages on the National Design System branch | Medium | 2026-05-12 | 2026-05-12 | Abhicheke | Completed | UAT |  | 5 | 5
vajraglobal.com | Seo Automation Tool | 12-May-2026-10 | Research and Analysis of the Seo Automation Process , and the documentation workflow , understanding and dicsuss with the TL for the project setup | Medium | 2026-05-12 | 2026-05-12 | Rackesh Kumaran | Completed | Production |  | 10 | 10
www.dgda.gov.sa | National Design System (DGA) | 13-May-2026-1 | NDA Checklist changes | Medium | 2026-05-13 | 2026-05-13 |  | Under Review & Testing | UAT |  | 4 | 0 |  |  |  | https://docs.google.com/spreadsheets/d/1n5q-U3l5wBUjmIFQpP8Qksejprd7liSbL9h2pA9R1ek/edit?gid=0#gid=0
intranet.adfactorspr.com | Content Update May | 13-May-2026-2 | Update content in AE,AM,Team Decathlon in Live | Medium | 2026-05-13 | 2026-05-13 | Parthiban | Completed | Production |  | 2 | 2.5
www.dgda.gov.sa | National Design System (DGA) | 13-May-2026-3 | check the National Design System compared to design | Medium | 2026-05-12 | 2026-05-13 | Parthiban | Completed | Local |  | 2 | 1.5
farnboroughairshow.com | FIA Maintenance May 2026 | 13-May-2026-4 | Fix the multinode tree picker path on Whats on POT and the Whats on page Events on Live | Medium | 2026-05-13 | 2026-05-13 | Abhicheke | Completed | Production |  | 3 | 2.5
farnboroughairshow.com | FIA Maintenance May 2026 | 13-May-2026-5 | Update multinode tree picker path on Whats on page Events on Staging | Medium | 2026-05-13 | 2026-05-13 | Parthiban | Completed | Production |  | 2 | 1
farnboroughinternationalstudios.com | Studio Maintenance 04 2026 | 13-May-2026-6 | make Templete duplicate and add it under Production Type in staging and live | Medium | 2026-05-13 | 2026-05-13 | Parthiban | Completed | Production |  | 4 | 4
intranet.adfactorspr.com | Content Update May | 13-May-2026-7 | Update content in AE,AM,Team Decathlon in Live | Medium | 2026-05-13 | 2026-05-13 | Rackesh Kumaran | Completed | Production |  | 2 | 2.5
www.dgda.gov.sa | Eservices and Qmatic Webpages | 11-May-2026-11 | Eservices and Qmatic Webpages Discussed Point | Medium | 2026-05-11 | 2026-05-11 | Sowndar | In Progress | Local |  | 0.25 | 0.25 |  | The Qmatic email has been shared with Dayel’s team to request access; Saad confirmed that development will begin as soon as access are provided | The Qmatic email has been shared with Dayel’s team to request access; Saad confirmed that development will begin as soon as access are provided
www.dgda.gov.sa | Emergency services form | 11-May-2026-12 | GIS Api issue need to sort with Ashma | Medium | 2026-05-11 | 2026-05-11 | Sowndar | In Progress | Local |  | 0.25 | 0.25 |  | Regan Coordinate with Ashma, He is followup with her. | Regan Coordinate with Ashma, He is followup with her.
www.dgda.gov.sa | Emergency services form | 11-May-2026-13 | SMS API | Medium | 2026-05-11 | 2026-05-11 | Sowndar | In Progress | Local |  | 0.25 | 0.25 |  | We need to speak with Kamran. To ensure we hear back by the end of the week, Regan will follow up on Monday (May 11) and again on Wednesday (May 13). | We need to speak with Kamran. To ensure we hear back by the end of the week, Regan will follow up on Monday (May 11) and again on Wednesday (May 13).
www.dgda.gov.sa | Emergency services form | 11-May-2026-14 | CRM Need to Configured | Medium | 2026-05-11 | 2026-05-11 | Sowndar | Waiting for Client Input | Local |  | 0.25 | 0.25 |  |  | CRM Need to Configured
www.dgda.gov.sa | Research Inquiry Forms | 11-May-2026-15 | CRM Need to Configured | Medium | 2026-05-11 |  | Sowndar | Waiting for Client Input | Local |  | 0.25 | 0.25 |  | Need to coordinate with raza. Just send the follow up she will send quickly | Need to coordinate with raza
www.dgda.gov.sa | DGDA Application PT Finding | 11-May-2026-16 | DGDA Application PT Finding | Medium | 2026-05-11 |  | Sowndar | Waiting for Client Input | Local |  | 0.25 | 0.25 |  | Saad needs to understand why we are performing this task, though he mentioned he will handle the changes. Regan explained to Saad that G specifically wants to address this because it is a critical issue that points back to us. , G advised Regan to explain the situation to Saad. Ultimately, Saad acknowledged that this is our accountability | Waiting for saad Approval
www.dgda.gov.sa | Events Application and Diriyah Horizon | 12-May-2026-1 | Requerement Gathering and Other Works | Medium | 2026-05-15 | 2026-05-15 | Sowndar | In Progress | Local |  | 18 | 18
intranet.adfactorspr.com | Adfactor Restore May | 14-May-2026-1 | ADF-Move to live | High | 2026-05-14 | 2026-05-14 | Parthiban | Completed | Production |  | 2 | 1.15
intranet.adfactorspr.com | Adfactor Restore May | 14-May-2026-2 | Fix Drag and drop issue in Social Post live | High | 2026-05-14 | 2026-05-14 | Parthiban | Completed | Production |  | 1 | 0.45
www.dgda.gov.sa | National Design System (DGA) | 14-May-2026-3 | Test National design Fixes and share the issue | Medium | 2026-05-14 | 2026-05-14 | Parthiban | Completed | Local |  | 5 | 4
www.dgda.gov.sa | National Design System (DGA) | 14-May-2026-4 | Fixes issue in National Design System Test again all the pages | Medium | 2026-05-14 | 2026-05-14 | Parthiban | Completed | Local |  | 2 | 2
intranet.adfactorspr.com | Adfactor Restore May | 14-May-2026-5 | Fix the Posted by Email issue in company post | High | 2026-05-14 | 2026-05-14 | Parthiban | Completed | Production |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) | 14-May-2026-6 | Test The forms and take payload for Failed Forms | Medium | 2026-05-14 | 2026-05-14 | Parthiban | Completed | Local |  | 1 | 0.5
www.dgda.gov.sa | Open data form Phase - 2 |  | Check the Form error on national ID | Medium | 2026-05-14 |  |  | Completed | Production |  | 1 | 1
www.dgda.gov.sa | Open data form Phase - 2 |  | Meeting with team | Medium | 2026-05-14 |  | Sowndar | Completed | Production |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) |  | Update the version on the National Design System branch 15.5.8 to 15.5.8 | Medium | 2026-05-14 | 2026-05-14 | Abhicheke | Completed |  |  | 9 | 9
vajraglobal.com | Seo Automation Tool | 14-May-2026-11 | Make the Frontend project setup for the SEO automation Tool and created the github repo and push the initial setup to the main branch | Medium | 2026-05-14 | 2026-05-14 | Rackesh Kumaran | Completed | Production |  | 9 | 7.5
farnboroughinternationalstudios.com | Remove the Other Stages Section | 14-May-2026-12 | Removed the other stages section from the farnboroughinternationalstudios live and staging | Medium | 2026-05-14 | 2026-05-14 | Rackesh Kumaran | Completed | Production |  | 2 | 2.5
www.dgda.gov.sa | Open data form Phase - 2 | 15-May-2026-1 | Move the open data request to live | Medium | 2026-05-15 |  | Abhicheke | Completed | Production |  | 4 | 0
www.dgda.gov.sa | National Design System (DGA) | 15-May-2026-3 | clone again DGDA Project and fix the reading 'push' | Medium | 2026-05-15 | 2026-05-15 | Parthiban | Completed | Local |  | 2 | 3
intranet.adfactorspr.com | Content Update May | 15-May-2026-4 | Update content in AE and AM Decathlon in Live | Medium | 2026-05-15 | 2026-05-15 | Parthiban | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | Open data form Phase - 2 | 15-May-2026-5 | Check the missing Arabic content in NDS | Medium | 2026-05-15 | 2026-05-15 | Parthiban | Completed | Production |  | 2 | 2
www.dgda.gov.sa | National Design System (DGA) | 15-May-2026-6 | Fixes issue in National Design System Test again all the pages | Medium | 2026-05-15 | 2026-05-15 | Parthiban | Completed | Local |  | 2 | 2
www.dgda.gov.sa | National Design System (DGA) | 15-May-2026-7 | Connect with Moswin and Fix the issue in dgda | High | 2026-05-15 | 2026-05-15 | Parthiban | Completed | Production |  | 2 | 0
farnborough.com | FIA Maintenance May 2026 | 15-May-2026-8 | Form testing for FIA | Medium | 2026-05-15 | 2026-05-15 | Rackesh Kumaran | Completed | Production |  | 1 | 1
www.dgda.gov.sa | DGDA Maintenance May 2026 | 15-May-2026-9 | Form testing for DGDA | Medium | 2026-05-15 | 2026-05-15 | Rackesh Kumaran | Completed | Production |  | 1 | 1
vajraglobal.com | Seo Automation Tool | 15-May-2026-9 | Now i started to make the backend setup for this SEO automation Tool and push the initial setup please | Medium | 2026-05-15 | 2026-05-15 | Rackesh Kumaran | Completed | Production |  | 7 | 7
www.dgda.gov.sa | Events Application and Diriyah Horizon | 15-May-2026-10 | Internal Discussion DGDA ¦ Events Booking System | Medium | 2026-05-15 | 2026-05-15 | Sowndar | Completed | Production |  | 1.5 | 1.5
www.dgda.gov.sa | National Design System (DGA) | 16-May-2026-1 | Connect with Moswin and Fix the issue in dgda github | High | 2026-05-16 | 2026-05-16 | Parthiban | Completed | Production |  | 5 | 5
www.dgda.gov.sa | Open data form Phase - 2 | 17-May-2026-1 | Root Causes Analysis For Persmission issue | High | 2026-05-18 | 2026-05-18 | Moswin | Completed | Production |  | 0 | 0
www.dgda.gov.sa | Open data form Phase - 2 | 18-May-2026-1 | Cross Test Full Website | Medium | 2026-05-18 | 2026-05-18 | Rackesh Kumaran | Completed | Production |  | 7 | 7.5
www.dgda.gov.sa | Open data form Phase - 2 | 18-May-2026-2 | Check the Form Submission | Medium | 2026-05-18 | 2026-05-18 | Rackesh Kumaran | Completed | Production |  | 3 | 3
www.dgda.gov.sa | Open data form Phase - 2 | 18-May-2026-3 | Test the Entire site in DGDA Live | Medium | 2026-05-18 | 2026-05-18 | Parthiban | Completed | Production |  | 5 | 3
www.dgda.gov.sa | Open data form Phase - 2 | 18-May-2026-4 | Publish the content for Freedom of information and open data,data resques page in English and arabic | Medium | 2026-05-18 | 2026-05-18 | Parthiban | Completed | Production |  | 3 | 3
www.dgda.gov.sa | Raise Concern | 18-May-2026-5 | Create a new category and sub category fileds in Raise and Concern form English | Medium | 2026-05-18 | 2026-05-18 | Parthiban | Completed | Production |  | 3 | 2.5
farnboroughairshow.com | FIA Maintenance May 2026 | 18-May-2026-6 | FIA Moved to staging | Medium | 2026-05-18 | 2026-05-18 | Parthiban | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa |  | 19-May-2026-1 | Explain how to create a form in site core with Manager | High | 2026-05-19 | 2026-05-19 | Parthiban | Completed | Production |  | 0.5 | 0.45
www.dgda.gov.sa | Raise Concern | 19-May-2026-2 | Create a new category and sub category fileds in Raise and Concern form Arabic and test it | Medium | 2026-05-19 | 2026-05-19 | Parthiban | Completed | Production |  | 3 | 3.5
www.dgda.gov.sa | Open data form Phase - 2 | 19-May-2026-5 | Update the missing arabic content | High | 2026-05-19 | 2026-05-19 | Parthiban | Completed | Production |  | 1 | 2
intranet.adfactorspr.com | Image and Video Edit On Post | 15-May-2026-3 | Add Image and Video option while Edit the post in social and post detail page | High | 2026-05-19 | 2026-05-20 | Parthiban | Completed | Production |  | 8 | 6
intranet.adfactorspr.com | Image and Video Edit On Post | 20-May-2026-1 | Add Image and Video option while Edit the post in Admin post Moderation detail page Move to staging and Test the functionality | High | 2026-05-20 | 2026-05-20 | Parthiban | Completed | Production |  | 3 | 3.5
intranet.adfactorspr.com | Adfactor Restore May | 20-May-2026-2 | Fix the Space issue in Social feed posts | High | 2026-05-20 | 2026-05-20 | Parthiban | Completed | Production |  | 1 | 0.45
intranet.adfactorspr.com | Adfactor Restore May | 20-May-2026-3 | Apply Post by adim in Postmoderation Admin Detail page | Medium | 2026-05-20 | 2026-05-20 | Parthiban | Completed | Production |  | 1 | 0.45
intranet.adfactorspr.com | Content Update May | 20-May-2026-4 | Align and Update content in Leadership Team and Holiday list | Medium | 2026-05-20 | 2026-05-20 | Parthiban | Completed | Production |  | 1 | 1
farnboroughinternational.org |  | 20-May-2026-5 | Upload the missing images in drive | Medium | 2026-05-20 | 2026-05-20 | Parthiban | Completed | Production |  | 1 | 0.5
www.dgda.gov.sa | Events Application and Diriyah Horizon | 20-May-2026-6 | Fw: Diriyah Horizons X Solutions - Call with team | Medium | 2026-05-20 | 2026-05-20 | Sowndar | Completed | Production |  | 0.75 | 0.75
www.dgda.gov.sa | Events Application and Diriyah Horizon | 20-May-2026-7 | Fw: Diriyah Horizons X Solutions - Call with team | Medium | 2026-05-20 | 2026-05-20 | Regan | Completed | Production |  | 0.75 | 0.75
www.dgda.gov.sa | DGDA Maintenance May 2026 |  | RCA for DGDA live and staging cicd issue. | Medium | 2026-05-18 | 2026-05-18 | Moswin | Completed | Production |  | 3 | 3
https://msmehealthengine.fametn.com/ | MSME |  | MSME live moving and testing | Medium | 2026-05-19 | 2026-05-19 | Moswin | Completed | Production |  | 1 | 1
www.dgda.gov.sa | DGDA Additional tasks |  | rotate PAT Tokens for 1 year | Medium | 2026-05-21 | 2026-05-21 | Moswin | Pipeline / To Do |  |  | 2 | 0
www.dgda.gov.sa | DGDA Additional tasks |  | check functionality of all workflows and identify if anything failing | Medium | 2026-05-20 | 2026-05-20 | Moswin | Pipeline / To Do |  |  | 2 | 0
www.dgda.gov.sa | DGDA Additional tasks |  | identify all the secrets/variables expiring and proactively update the values | Medium | 2026-05-20 | 2026-05-20 | Moswin | Pipeline / To Do |  |  | 2 | 0
www.dgda.gov.sa | DGDA Additional tasks |  | Light house workflow check | Medium | 2026-05-20 | 2026-05-20 | Moswin | Completed | Production |  | 3 | 2.5
www.dgda.gov.sa | DGDA Additional tasks |  | GitHub Breach analysis and follow up news and take necessary precaution | Medium | 2026-05-20 | 2026-05-20 | Moswin | Completed | Local |  | 2 | 2 |  |  |  | https://www.indiatoday.in/amp/technology/news/story/github-suffers-breach-in-internal-code-hackers-claim-they-have-source-code-for-sale-2914354-2026-05-20
intranet.adfactorspr.com | Adfactor Restore May | 20-May-2026-5 | New joiner Auto post generation Date time issue | Medium |  |  |  | Pipeline / To Do | Staging |  | 2 | 0 |  | Now New joiner Auto post are not posted because they use 1week of datas in DB we use Today date Time
farnboroughairshow.com | FIA Maintenance May 2026 | 21-May-2026-1 | Create field and test the Opening Times in Airshow Add Min height for exbhitor cards Move to staging and and check the exbhitor listing | Medium | 2026-05-21 | 2026-05-21 | Parthiban | Completed | Production |  | 1 | 2.5
intranet.adfactorspr.com | Content Update May | 21-May-2026-2 | Update content in Leadership Team | Medium | 2026-05-21 | 2026-05-21 | Parthiban | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | Open data form Phase - 2 | 21-May-2026-3 | List the NDS Templete and add date | Medium | 2026-05-21 | 2026-05-21 | Parthiban | Completed | Production |  | 1 | 1
farnboroughairshow.com | FIA Maintenance May 2026 | 21-May-2026-4 | change the font size for footer description | Medium | 2026-05-21 | 2026-05-21 | Parthiban | Completed | Production |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) | 21-May-2026-5 | Fix the issue in NDS Home page and media Room | Medium | 2026-05-21 | 2026-05-21 | Parthiban | Completed | Local |  | 1 | 2.5
www.dgda.gov.sa | Raise Concern | 21-May-2026-6 | Publish content and test in live for Raise cencern Form | Medium | 2026-05-21 | 2026-05-21 | Parthiban | Completed | Production |  | 1 | 1.5
farnboroughairshow.com | FIA Maintenance May 2026 | 21-May-2026-7 | Exhibitor new fields add on website | Medium | 2026-05-20 | 2026-05-20 | Sowndar | In Progress | Staging |  | 10 | 10
farnboroughairshow.com | FIA Maintenance May 2026 | 22-May-2026-1 | Move Exbhitor and Footer change and create filed in Live | Medium | 2026-05-22 | 2026-05-22 | Parthiban | Completed | Production |  | 1 | 1
www.dgda.gov.sa | Raise Concern | 22-May-2026-2 | Fix the issue in Complaint type and sub category in DGDA Live | Medium | 2026-05-22 | 2026-05-22 | Parthiban | Completed | Production |  | 2 | 2
www.dgda.gov.sa | National Design System (DGA) | 22-May-2026-3 | Fix the NDS issue in careers page and FAQ page | Medium | 2026-05-22 | 2026-05-22 | Parthiban | Completed | Local |  | 2 | 1.5
www.dgda.gov.sa | National Design System (DGA) | 22-May-2026-4 | Fix the Alignment issue in all Detail pages in NDS | Medium | 2026-05-22 | 2026-05-22 | Parthiban | Completed | Local |  | 2 | 2
www.dgda.gov.sa | National Design System (DGA) | 22-May-2026-5 | Fix the Alignment issue in all pages in NDS | Medium | 2026-05-22 | 2026-05-22 | Parthiban | Completed | Local |  | 2 | 2.5 |  | Color change and some unknown alignment is balance to fix
www.dgda.gov.sa | S3 url generation - EN |  | Upload english pdfs in s3 bucket and share asset urls with the team . | Medium | 2026-05-20 | 2026-05-20 | Moswin | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | S3 url generation - AR |  | Upload Arabic pdfs in s3 bucket and share asset urls with the team . | Medium | 2026-05-21 | 2026-05-21 | Moswin | Completed | Production |  | 0.5 | 0.5
farnborough.com | FIA Maintenance 04 2026 | 25-May-2026-1 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-05-25 | 2026-05-25 | Parthiban | Completed | Production |  | 1 | 1 |  | Done and Updated in Sheet
farnborough.com | FIA Maintenance 04 2026 | 25-May-2026-2 | Submit forms For Farnborough in Live | Medium | 2026-05-25 | 2026-05-25 | Parthiban | Completed | Production |  | 1 | 1
www.dgda.gov.sa | DGDA Maintenance May 2026 | 25-May-2026-3 | Submit forms For DGDA in Staging | Medium | 2026-05-25 | 2026-05-25 | Parthiban | Completed | Staging |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) | 25-May-2026-4 | Fix the banner text alaingment issue | Medium | 2026-05-25 | 2026-05-25 | Parthiban | Completed | Staging |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) | 25-May-2026-5 | Fix the allignment issue in Water dispense page | Medium | 2026-05-25 | 2026-05-25 | Parthiban | Completed | Staging |  | 1 | 1
www.dgda.gov.sa | DGDA Maintenance May 2026 | 25-May-2026-6 | Fix the info@dgda.gov.sa issue in general inquery | Medium | 2026-05-25 | 2026-05-25 | Parthiban | Completed | Staging |  | 4 | 3
www.dgda.gov.sa | National Design System (DGA) | 25-May-2026-7 | Test All the Pages In NDS | Medium | 2026-05-25 | 2026-05-25 | Parthiban | Completed | Staging |  | 2 | 1
www.dgda.gov.sa | National Design System (DGA) | 25-May-2026-8 | NDS DGDA QC fix | Medium | 2026-05-25 | 2026-05-26 | Abhicheke | Completed | UAT |  | 25 | 20.5
www.dgda.gov.sa | Events Application and Diriyah Horizon | 26-May-2026-1 | Regan,Sowndar | Medium | 2026-05-26 | 2026-05-26 | Sowndar | Completed | Production |  | 2 | 2
www.dgda.gov.sa | Events Application and Diriyah Horizon |  | Understand the requirement and call with the team | Medium | 2026-05-20 | 2026-05-20 | Moswin | Completed | Local |  | 3 | 3
www.dgda.gov.sa | Events Application and Diriyah Horizon |  | DGDA Arch dia + requirement sheet | Medium | 2026-05-22 | 2026-05-25 | Moswin | Completed | Local |  | 6 | 6
www.dgda.gov.sa | Events Application and Diriyah Horizon |  | Refactor Arch dia to dgdas format | Medium | 2026-05-22 | 2026-05-25 | Moswin | Completed | Local |  | 6 | 6
www.dgda.gov.sa | Events Application and Diriyah Horizon | Events Application and Diriyah Horizon | Prepare Architecture flow with the same flow as dgda has given | Medium | 2026-05-26 | 2026-05-26 | Moswin | Completed | Local |  | 5 | 0
www.dgda.gov.sa | Events Application and Diriyah Horizon |  | PAT Token and related queries analyse and mail response. | Medium | 2026-05-25 | 2026-05-26 | Moswin | In Progress | Local |  | 4 | 0
farnborough.com | FIA Maintenance 04 2026 | 26-May-2026-2 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-05-26 | 2026-05-26 | Parthiban | Completed | Production |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) | 26-May-2026-1 | Test All the Pages In NDS After Fix and update in sheet in both English and Arabic | Medium | 2026-05-26 | 2026-05-26 | Parthiban | Completed | Local |  | 5 | 7.5 |  |  |  | https://docs.google.com/spreadsheets/d/1wDN-TQsaPOOxhlgWcuQqhUNPhx87mAUBfKShyoFqqeM/edit?gid=0#gid=0
www.dgda.gov.sa | Adfactor Restore May | 26-May-2026-1 | Search New joiner query and clarify the Image and Vedio edit | Medium | 2026-05-26 | 2026-05-26 | Parthiban | Completed | Production |  | 0.5 | 0.5
farnborough.com | FIA Maintenance 04 2026 | 27-May-2026-1 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-05-27 | 2026-05-27 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com |  | 27-May-2026-2 | ADF-Task List | Medium | 2026-05-27 | 2026-05-27 | Parthiban | Completed | Production |  | 1 | 1
farnborough.com | FIA Maintenance 04 2026 | 27-May-2026-3 | Farnborugh Db backup to local | Medium | 2026-05-27 | 2026-05-27 | Parthiban | Completed | Local |  | 1 | 1
vajraglobal.com |  | 27-May-2026-4 | Explore Adobe Experience Manager and WorkFront | Medium | 2026-05-27 | 2026-05-27 | Parthiban | Completed | Local |  | 3 | 2.5
www.dgda.gov.sa |  | 27-May-2026-5 | DGDA project setup | Medium | 2026-05-27 | 2026-05-27 | Parthiban | Completed | Local |  | 3 | 3
www.dgda.gov.sa | Events Application and Diriyah Horizon | 27-May-2026-6 | DGDA Arch dia + requirement sheet | Medium | 2026-05-27 | 2026-05-27 | Moswin | Completed | Local |  | 3 | 3
farnboroughairshow.com | FIA Maintenance 04 2026 | 27-May-2026-7 | update the table content and fix the table style | Medium | 2026-05-27 | 2026-05-27 | Abhicheke | Completed | Production |  |  | 2 |  |  |  | https://www.farnboroughairshow.com/the-show/aerospace-global-forum/defence-summit/ https://www.farnboroughairshow.com/the-show/aerospace-global-forum/technology-summit/ https://www.farnboroughairshow.com/the-show/aerospace-global-forum/finance-summit/
farnborough.com | FIA Maintenance 04 2026 | 28-May-2026-1 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-05-28 | 2026-05-28 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore May | 28-May-2026-2 | Update the media file live to staging Test the profile picture | Medium | 2026-05-28 | 2026-05-28 | Parthiban | Completed | Production |  | 1 | 1
|  | 28-May-2026-3 | Explore the Intranet-Dgda | Medium | 2026-05-28 | 2026-05-28 | Parthiban | Completed | Local |  | 2 | 2
www.dgda.gov.sa | National Design System (DGA) | 28-May-2026-4 | Fix arabic alignment issue in NDS | Medium | 2026-05-28 | 2026-05-28 | Parthiban | Completed | Local |  | 6 | 5
farnborough.com | FIA Maintenance 04 2026 | 29-May-2026-1 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-05-29 | 2026-05-29 | Parthiban | Completed | Production |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) | 29-May-2026-2 | Fix Moblie and Ipads layout issue in NDS | Medium | 2026-05-29 | 2026-05-29 | Parthiban | Completed | Local |  | 6 | 6.5
www.dgda.gov.sa | National Design System (DGA) | 29-May-2026-3 | Fix font size for mobile responsive | Medium | 2026-05-29 | 2026-05-29 | Parthiban | Completed | Local |  | 1 | 1
intranet.adfactorspr.com |  | 29-May-2026-4 | ADF-Meeting | Medium | 2026-05-29 | 2026-05-29 | Parthiban | Completed | Local |  | 0.5 | 0.5
www.dgda.gov.sa | National Design System (DGA) | 29-May-2026-3 | Fix font size for mobile responsive | Medium | 2026-05-29 | 2026-05-29 | Moswin | Completed | Local |  | 1 | 1
intranet.adfactorspr.com | Home Page Changes May 2026 | 29-May-2026-4 | Home Page – Carousel Updates Remove the bottom navigation dots from the home page post carousel. Remove the black overlay displayed at the bottom of the carousel. Add left and right navigation arrows with a black overlay, similar to the Bootstrap carousel design. | Medium | 2026-06-02 | 2026-06-02 | Parthiban | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Home Page Changes May 2026 | 29-May-2026-5 | Home Page – Video Display Fix Fix the issue where videos with a very small width display with an excessively large height. Ensure videos maintain the correct aspect ratio and responsive behavior across all screen sizes on home page posts. | Medium | 2026-06-02 | 2026-06-02 | Parthiban | Completed | Production |  | 2 | 2.5
intranet.adfactorspr.com | Brand Kit Page May 2026 | 29-May-2026-6 | Change the arrow direction on the Brand Kit page. Apply the same arrow direction changes across the entire website. | Medium | 2026-06-02 | 2026-06-02 | Parthiban | Completed | Production |  | 2 | 2
intranet.adfactorspr.com | Brand Kit Page May 2026 | 29-May-2026-7 | Add a logo icon for each item in the Logo section. | Medium | 2026-06-02 | 2026-06-02 | Parthiban | Completed | Production |  | 3 | 2.5
intranet.adfactorspr.com | Case Study Page May 2026 | 29-May-2026-8 | Add the client logo to each case study so users can easily identify the client. Vishal will provide the complete template/design for this page. | Medium | 2026-05-29 |  | Parthiban | On Hold / Blocked | Local |  | 0 | 0 |  | need templete from client
vajraglobal.com | Seo Automation Tool | 01-June-2026-1 | Frontend: Implemented Super Admin Console enhancements, authentication UX improvements, and organization-aware dashboard updates. | Medium | 2026-06-01 | 2026-06-01 | Rackesh Kumaran | Completed | Production |  | 5 | 5
vajraglobal.com | Seo Automation Tool | 01-June-2026-2 | Backend : Enhanced organization management APIs, improved invite and seat management logic, and integrated organization context into authentication flows. | Medium | 2026-06-01 | 2026-06-01 | Rackesh Kumaran | Completed | Production |  | 4 | 4.5
intranet.adfactorspr.com | Adfactor Admin Dashboard | 01-June-2026-3 | Adfactor Admin Dahboard Cross test | Medium | 2026-06-01 | 2026-06-02 | Abhicheke | Completed | Staging |  | 3 | 3
www.dgda.gov.sa | National Design System (DGA) | 01-June-2026-4 | NDS Responsive Fix and color code update and icon fix | Medium | 2026-06-01 |  | Abhicheke | In Progress | UAT |  | 23 | 23
www.dgda.gov.sa | National Design System (DGA) |  | DGDA AWS Amplify build error dependency fix | Medium | 2026-06-01 | 2026-06-01 | Moswin | Completed | UAT |  | 2 | 2
www.dgda.gov.sa | DGDA Maintenance June 2026 |  |  | Medium | 2026-06-02 | 2026-06-02 | Moswin | Completed | Production |  | 1 | 1
www.dgda.gov.sa | DGDA Maintenance June 2026 |  | DGDA amplify build fail logs grep and send as mail without requesting access from dgda | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 2 | 0
www.dgda.gov.sa | DGDA Maintenance June 2026 |  | DGDA amplify build fail logs grep and send as mail without requesting access from dgda | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 2 | 0
www.dgda.gov.sa | DGDA EMS Infra set up |  | DGDA EMS alibaba free tier set up to specifically test mail logic | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 5 | 0 |  |  | Company credit card required.
www.dgda.gov.sa | DGDA EMS Infra set up |  | Alibaba cloud infra set up dev | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 10 | 0 |  |  | Access required for both alibaba and github
www.dgda.gov.sa | DGDA EMS Infra set up |  | Alibaba cloud infra set up staging | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 10 | 0 |  |  | Access required for both alibaba and github
www.dgda.gov.sa | DGDA EMS Infra set up |  | Alibaba cloud infra set up live | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 15 | 0 |  |  | Access required for both alibaba and github
www.dgda.gov.sa | DGDA EMS Infra set up |  | Github repo and CICD dev | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 3 | 0 |  |  | Access required for both alibaba and github
www.dgda.gov.sa | DGDA EMS Infra set up |  | Github repo and CICD staging | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 3 | 0 |  |  | Access required for both alibaba and github
www.dgda.gov.sa | DGDA EMS Infra set up |  | Github repo and CICD Live | Medium |  |  | Moswin | Pipeline / To Do | Local |  | 3 | 0 |  |  | Access required for both alibaba and github
vajraglobal.com | Seo Automation Tool | 02-June-2026-1 | Frontend: Implemented responsive UI improvements across Dashboard, Console, Authentication, Members, and Organization pages, including mobile navigation, sidebar enhancements, responsive layouts, and UI/UX fixes. Backend: Developed organization management and account owner management features, including organization details, seat usage tracking, invite workflows, account owner APIs, authentication enhancements, database migration updates, and related documentation. | Medium | 2026-06-02 | 2026-06-02 | Rackesh Kumaran | Completed | Production |  | 7 | 8
farnboroughairshow.com | FIA Maintenance 04 2026 | 03-June-2026-1 | FIA The Enterprise Gatweway Programme Table update | Medium | 2026-06-03 | 2026-06-03 | Abhicheke | Completed | Production |  | 0.5 | 0.5
farnboroughairshow.com | FIA Maintenance 04 2026 | 03-June-2026-2 | FIA-Exhibitor Listing spacing issue and cards show fix Test all the pages in Exhibitor Listing | Medium | 2026-06-03 | 2026-06-03 | Parthiban | Completed | Production |  | 3 | 3
farnboroughairshow.com | FIA Maintenance 04 2026 | 03-June-2026-3 | Test mobile responsive in FIA pages | Medium | 2026-06-03 | 2026-06-03 | Parthiban | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | National Design System (DGA) | 03-June-2026-4 | Test the NDS all pages in Desktop Big screen for English and arabic | Medium | 2026-06-03 | 2026-06-03 | Parthiban | Completed | Local |  | 3 | 3
intranet.adfactorspr.com | Home Page Changes May 2026 | 03-June-2026-5 | create a fields in backofice & Move the changes to live and check the changes in live | Medium | 2026-06-03 | 2026-06-03 | Parthiban | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Content Update June | 03-June-2026-6 | Update the content in awards page | Medium | 2026-06-03 | 2026-06-03 | Parthiban | Completed | Production |  | 1 | 1
farnboroughairshow.com | FIA Maintenance 04 2026 | 03-June-2026-7 | FIA The Enterprise Gatweway Programme Table fix | Medium | 2026-06-03 | 2026-06-03 | Parthiban | Completed | Production |  | 1 | 1
vajraglobal.com | Seo Automation Tool | 03-June-2026-5 | Frontend : Implemented dashboard navigation enhancements, branding updates, user management improvements, and responsive layout fixes across organization and member modules. | Medium | 2026-06-03 | 2026-06-03 | Rackesh Kumaran | Completed | Production |  | 5 | 5
vajraglobal.com | Seo Automation Tool | 03-June-2026-6 | Backend : Developed Super Admin account management APIs, enhanced user profile and authentication tracking capabilities, and introduced supporting database migrations for user activity management. | Medium | 2026-06-03 | 2026-06-03 | Rackesh Kumaran | Completed | Production |  | 4 | 4.5
farnborough.com | FIA Maintenance 04 2026 | 03-June-2026-7 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-03 | 2026-06-03 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 03-June-2026-8 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-03 | 2026-06-03 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | National Design System (DGA) | 03-June-2026-9 | NDS tag colors icon size update and large screen responsive fix | Medium | 2026-06-03 | 2026-06-03 | Abhicheke | Completed | UAT |  | 8.5 | 8
farnborough.com | FIA Maintenance 04 2026 | 04-June-2026-1 | Fix The Enterprise Gatweway Programme Table responsive | Medium | 2026-06-04 | 2026-06-04 | Parthiban | Completed | Production |  | 0.5 | 0.5
intranet.adfactorspr.com | Home Page Changes May 2026 | 04-June-2026-2 | Test the latest changes in Live | Medium | 2026-06-04 | 2026-06-04 | Parthiban | Completed | Production |  | 0.5 | 0.5
intranet.adfactorspr.com | Adfactor Restore June | 04-June-2026-3 | Fix the Leadership Team sorting issue | Medium | 2026-06-04 | 2026-06-04 | Parthiban | Completed | Production |  | 2 | 2
farnborough.com | FIA Maintenance 04 2026 | 04-June-2026-4 | Analysis the Changes on Farnborough International Airshow 2026 - API sheet | Medium | 2026-06-04 | 2026-06-04 | Parthiban | Completed | Production |  | 2 | 2
www.dgda.gov.sa | EMS Project | 04-June-2026-5 | Analysis the DGDA EMS Project | Medium | 2026-06-04 | 2026-06-04 | Parthiban | Completed | Production |  | 5 | 2
intranet.adfactorspr.com | Adfactor Restore June | 04-June-2026-6 | Update the Leadership Team memebers short | Medium | 2026-06-04 | 2026-06-04 | Parthiban | Completed | Production |  | 2 | 1.5
farnborough.com | FIA Maintenance 04 2026 | 04-June-2026-7 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-04 | 2026-06-04 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 04-June-2026-8 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-04 | 2026-06-04 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
farnborough.com | FIA Maintenance 04 2026 | 04-June-2026-9 | Monthly report making for the all the Farnborough sites | Medium | 2026-06-04 | 2026-06-04 | Rackesh Kumaran | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore June | 04-June-2026-10 | Monthly report making for the Adfactors | Medium | 2026-06-04 | 2026-06-04 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 04-June-2026-11 | Frontend: 1)Super Admin user management UI enhancements and responsive layout improvements 2)Dark-mode refinements and authentication page usability updates 3)Engineering standards and frontend documentation updates | Medium | 2026-06-04 | 2026-06-04 | Rackesh Kumaran | Completed | Production |  | 4 | 3
vajraglobal.com | Seo Automation Tool | 04-June-2026-12 | Backend : 1)Security Phase A implementation and authentication hardening 2)Production safeguards and secure error-handling enhancements 3)JWT security improvements and sensitive data protection measures 4)Production readiness and technical documentation updates | Medium | 2026-06-04 | 2026-06-04 | Rackesh Kumaran | Completed | Production |  | 5 | 5
farnborough.com | FIA Maintenance 04 2026 | 05-June-2026-1 | FIA-Moved the fix code to live | Medium | 2026-06-05 | 2026-06-05 | Parthiban | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | National Design System (DGA) | 05-June-2026-2 | Cross tes the entire pages in NDS English and Arabic Test in mobile and Desktop | Medium | 2026-06-05 | 2026-06-05 | Parthiban | Completed | Local |  | 3 | 3.5
intranet.adfactorspr.com | Content Update June | 05-June-2026-3 | Create a new Casestydy In live | Medium | 2026-06-05 | 2026-06-05 | Parthiban | Completed | Local |  | 1 | 1
intranet.adfactorspr.com | Content Update June | 05-June-2026-4 | sort and update the Leadership team members | Medium | 2026-06-05 | 2026-06-05 | Parthiban | Completed | Production |  | 2 | 1.5
intranet.adfactorspr.com | Content Update June | 05-June-2026-5 | Update content in Cross sell inivative winner list | Medium | 2026-06-05 | 2026-06-05 | Parthiban | Completed | Production |  | 1 | 1
farnborough.com | FIA Maintenance 04 2026 | 05-June-2026-6 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-05 | 2026-06-05 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 05-June-2026-7 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-05 | 2026-06-05 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
farnborough.com | FIA Maintenance 04 2026 | 05-June-2026-8 | Form Testing & submission for the Farnborough websites | Medium | 2026-06-05 | 2026-06-05 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 05-June-2026-9 | Form Testing & submission for the DGDA websites | Medium | 2026-06-05 | 2026-06-05 | Rackesh Kumaran | Completed | Production |  | 1 | 1
intranet.adfactorspr.com | Adfactor Restore June | 05-June-2026-10 | Testing the leadership team page for all the members are present in the correct designation, Team members are present correctly in the given sorted order | Medium | 2026-06-05 | 2026-06-05 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 05-June-2026-11 | Frontend : 1) Phase 2 frontend integration with backend API enhancements and workflow quota handling 2) Account settings and change password functionality implementation 3) User profile, identity, and session experience improvements 4) User management responsiveness and usability enhancements | Medium | 2026-06-05 | 2026-06-05 | Rackesh Kumaran | Completed | Production |  | 3 | 3
vajraglobal.com | Seo Automation Tool | 05-June-2026-12 | Backend : 1)Change password API and email validation enhancements 2)Credential validation and workflow module refactoring 3)Audit logging and workflow results export implementation 4)Workflow quota management and backend documentation updates. | Medium | 2026-06-05 | 2026-06-05 | Rackesh Kumaran | Completed | Production |  | 4 | 4.5
www.dgda.gov.sa | DGDA EMS Infra set up |  | Alibaba account creation payment application deependency set up in new server Application migration to the server k6 testing plan |  | 2026-06-04 | 2026-06-05
www.dgda.gov.sa | DGDA Maintenance June 2026 |  | Update the nextjs from version 15.5.18 to 16.2.7 | Medium | 2026-06-08 |  | Abhicheke | In Progress |  |  |  | 0
farnborough.com | FIA Maintenance 04 2026 | 08-June-2026-1 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-08 | 2026-06-08 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5 | 0
www.dgda.gov.sa | DGDA Maintenance June 2026 | 08-June-2026-2 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-08 | 2026-06-08 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 08-June-2026-3 | Frontend : 1) Workflow management enhancements with quota handling and improved error management 2) Account settings and change password functionality integration 3) User profile, identity, and session experience improvements 4) User management and organization administration UI refinements | Medium | 2026-06-08 | 2026-06-08 | Rackesh Kumaran | Completed | Production |  | 3 | 3
vajraglobal.com | Seo Automation Tool | 08-June-2026-4 | Backend : 1) Change password API and comprehensive email validation enhancements 2) Credential validation and service-repository architecture refactoring 3) Audit logging and workflow results export implementation 4) Workflow quota management and trigger enforcement across automation processes 5) API enhancements, documentation updates, and frontend integration support | Medium | 2026-06-08 | 2026-06-08 | Rackesh Kumaran | Completed | Production |  | 3 | 3
farnboroughairshow.com | FIA Maintenance 04 2026 | 08-June-2026-5 | Testing the what's on (event page) , aircraft listing page | Medium | 2026-06-08 | 2026-06-08 | Rackesh Kumaran | Completed | Staging |  | 3 | 3
www.dgda.gov.sa | National Design System (DGA) | 09-June-2026-1 | Cross test the entire NDS site with responsive in FireFox browser | Medium | 2026-06-09 | 2026-06-09 | Parthiban | Completed | Local |  | 2 | 2
www.dgda.gov.sa | National Design System (DGA) | 09-June-2026-2 | Cross test the entire NDS site with responsive in Edge browser | Medium | 2026-06-09 | 2026-06-09 | Parthiban | Completed | Local |  | 2 | 2
farnborough.com | FIA Maintenance 04 2026 | 09-June-2026-3 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-09 | 2026-06-09 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 09-June-2026-4 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-09 | 2026-06-09 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 09-June-2026-5 | Frontend : 1) Workflow execution experience enhancements with live status tracking and real-time run updates 2) Google Sheets results integration with sync, download, and direct sheet access capabilities 3) Results management improvements for sheet-based workflows and snapshot handling 4) Workflow status and notification UX refinements | Medium | 2026-06-09 | 2026-06-09 | Rackesh Kumaran | Completed | Production |  | 4 | 4
vajraglobal.com | Seo Automation Tool | 09-June-2026-6 | Backend: 1) Google Sheets synchronization and workflow run tracking enhancements 2) Workflow APIs for results retrieval, synchronization, and CSV export implementation 3) Results processing infrastructure improvements with run-based status management 4) Development utilities and automated scripts for Google Sheets integration testing 5) End-to-end validation of Google Sheets sync functionality using service account authentication | Medium | 2026-06-09 | 2026-06-09 | Rackesh Kumaran | Completed | Production |  | 5 | 5.5
https://www.nfs-hospitality.com/ |  | 09-June-2026-7 | Update the images on the NFS Website | Medium | 2026-06-09 | 2026-06-09 | Abhicheke | Completed |  |  | 8 | 8
intranet.adfactorspr.com | Dev Update June | 09-June-2026-8 | Update and fix the issue in SQL for restore Database | Medium | 2026-06-09 | 2026-06-09 | Parthiban | Completed | Local |  | 4 | 3.5
intranet.adfactorspr.com | Dev Update June | 10-June-2026-1 | List the Case study with published and Article date | Medium | 2026-06-09 | 2026-06-10 | Parthiban | Completed | Local |  | 3 | 2
intranet.adfactorspr.com | Dev Update June | 10-June-2026-2 | change name Adfactors PR 1/3 carosel badge Remove bold for value in current affairs System generated post Text changes Enable the Auto post generation Fix the EmployeeID in Post moderation Add AE AM decathlon in utilities page | Medium | 2026-06-10 | 2026-06-10 | Parthiban | Completed | Staging |  | 4 | 4.5
intranet.adfactorspr.com | Dev Update June | 10-June-2026-2 | Left align the text in system generated post | Medium | 2026-06-10 | 2026-06-10 | Parthiban | Completed | Staging |  | 1 | 1
www.dgda.gov.sa | National Design System (DGA) | 10-June-2026-3 | Cross test the entire NDS site with responsive in FireFox Edge and chrome browser | Medium | 2026-06-10 | 2026-06-10 | Parthiban | Completed | Local |  | 2 | 2.5
farnborough.com | FIA Maintenance 04 2026 | 10-June-2026-4 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-10 | 2026-06-10 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 10-June-2026-5 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-10 | 2026-06-10 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 10-June-2026-6 | Frontend : 1) Workflow history enhancements with advanced filtering and navigation improvements 2) Results page usability refinements, including data visibility and table interaction improvements 3) Excel export functionality aligned with Google Sheets/n8n workbook structure | Medium | 2026-06-10 | 2026-06-10 | Rackesh Kumaran | Completed | Production |  | 4 | 4
vajraglobal.com | Seo Automation Tool | 10-June-2026-7 | Backend : 1) Google Sheets integration enhancements with improved error handling and sheet classification 2) Workflow run isolation and team activity tracking enhancements for organization-level visibility 3) Results synchronization and caching improvements for run-based and organization-level processing 4) Workflow quota controls and organization usage reporting enhancements 5) Database performance optimizations, developer utilities, and configuration documentation updates | Medium | 2026-06-10 | 2026-06-10 | Rackesh Kumaran | Completed | Production |  | 5 | 5
intranet.adfactorspr.com | Dev Update June | 10-June-2026-8 | update the directors heading in the leader ship new page in the adfactors | Medium | 2026-06-10 | 2026-06-10 | Rackesh Kumaran | Completed | Staging |  | 0.5 | 0.5
intranet.adfactorspr.com | Dev Update June | 10-June-2026-9 | Need profile pic update | Medium |  |  | Parthiban | Pipeline / To Do | Local |  | 4 | 0
intranet.adfactorspr.com | Dev Update June | 10-June-2026-10 | Quick links view count | Medium |  |  | Parthiban | Pipeline / To Do | Local |  | 6 | 0
intranet.adfactorspr.com | Dev Update June | 10-June-2026-11 | Remove footer when post count is large | Medium |  |  | Parthiban | Pipeline / To Do | Local |  | 2 | 0
intranet.adfactorspr.com | Dev Update June | 10-June-2026-12 | logo in case study | Medium |  |  | Parthiban | Pipeline / To Do | Local |  | 3 | 0
www.dgda.gov.sa | DGDA Maintenance June 2026 | 10-June-2026-9 | Develope the single page for the latest finding | Medium | 2026-06-10 | 2026-06-11 | Abhicheke | Completed | Production |  | 20 | 15 | Code moved to live but on the unpublished |  |  | Summary Page https://feat-finding-details.d38541r9nlp4br.amplifyapp.com/en/latest-findings/ Detail Page https://feat-finding-details.d38541r9nlp4br.amplifyapp.com/en/latest-findings/wadi-safar
www.dgda.gov.sa | EMS Project | 11-June-2026-1 | Cross test the functionality and Responsiveness in DGDA EMS | Medium | 2026-06-11 | 2026-06-11 | Parthiban | Completed | Local |  | 4 | 4
www.dgda.gov.sa | National Design System (DGA) | 11-June-2026-2 | Cross test the functionality and Responsiveness in DGDA in responsively app | Medium | 2026-06-11 | 2026-06-11 | Parthiban | Completed | Local |  | 3 | 2.5
www.dgda.gov.sa | National Design System (DGA) | 11-June-2026-3 | Fix the issue in NDS responsiveness | Medium | 2026-06-11 | 2026-06-11 | Parthiban | Completed | Local |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 11-June-2026-4 | Move the FIA to staging | Medium | 2026-06-11 | 2026-06-11 | Parthiban | Completed | Staging |  | 0.5 | 0.5
farnborough.com | FIA Maintenance 04 2026 | 11-June-2026-5 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-11 | 2026-06-11 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 11-June-2026-6 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-11 | 2026-06-11 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 11-June-2026-7 | Frontend : 1) Workflow history enhancements with period-based viewing and advanced filtering capabilities 2) Results page improvements with state persistence and in-sheet date filtering across main and subsheets | Medium | 2026-06-11 | 2026-06-11 | Rackesh Kumaran | Completed | Production |  | 4 | 4
vajraglobal.com | Seo Automation Tool | 11-June-2026-8 | Backend : 1) Security Phase B implementation with production hardening and infrastructure safeguards 2) Security testing enhancements, including automated tests and validation coverage improvements 3) Results synchronization and cache management fixes for Google Sheets integration 4) Database optimization and DevOps utility enhancements to improve system performance and maintainability 5) Production configuration and technical documentation updates | Medium | 2026-06-11 | 2026-06-11 | Rackesh Kumaran | Completed | Production |  | 5 | 5.5
farnboroughairshow.com | Expo Platform Changes | 05-June-2026-13 | “Submitted” | Medium | 2026-06-05 | 2026-06-05 | Sowndar | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 12-June-2026-3 | “&” is doing the “amp;” | Medium | 2026-06-12 | 2026-06-12 | Sowndar | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 12-June-2026-4 | The ID changed from 1094 to 4691. | Medium | 2026-06-09 | 2026-06-09 | Sowndar | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 12-June-2026-5 | The parameter ID is a matching mechanism, used only for updates and only after the session (what's on) and product (aircraft) have been created. | Medium | 2026-06-09 | 2026-06-09 | Sowndar | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 12-June-2026-6 | --form 'custom_fields[wingspan][]="test wingspan"' \ --form 'custom_fields[length][]="test length"' \ | Medium | 2026-06-09 | 2026-06-09 | Sowndar | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 12-June-2026-7 | We received a product category of "270", which does not exist. We have a "207" | Medium | 2026-06-09 | 2026-06-09 | Sowndar | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 12-June-2026-8 | Additionally, a couple of exhibitors had an issue regarding the hall/stand parameter: | Medium | 2026-06-09 | 2026-06-09 | Sowndar | Completed | Staging |  | 2 | 2
farnboroughairshow.com | Expo Platform Changes | 12-June-2026-1 | FIA-Moved files to staging | Medium | 2026-06-12 | 2026-06-12 | Parthiban | Completed | Local |  | 0.5 | 0.45
www.dgda.gov.sa | EMS Project | 12-June-2026-2 | Cross test the functionality and Responsiveness in DGDA EMS | Medium | 2026-06-12 | 2026-06-12 | Parthiban | Completed | Local |  | 2 | 2.45
www.dgda.gov.sa | DGDA Maintenance June 2026 | 12-June-2026-3 | crosstest the latest finding page with responsive | Medium | 2026-06-12 | 2026-06-12 | Parthiban | Completed | Local |  | 0.5 | 0.5
farnborough.com | FIA Maintenance 04 2026 | 12-June-2026-4 | FIA-Fix the log error in live | Medium | 2026-06-12 | 2026-06-12 | Parthiban | Completed | Staging |  | 3 | 2
farnborough.com | FIA Maintenance 04 2026 | 12-June-2026-5 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-12 | 2026-06-12 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 12-June-2026-6 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-12 | 2026-06-12 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
farnborough.com | FIA Maintenance 04 2026 | 12-June-2026-7 | Form Testing & submission for the Farnborough websites | Medium | 2026-06-12 | 2026-06-12 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 12-June-2026-8 | Form Testing & submission for the DGDA websites | Medium | 2026-06-12 | 2026-06-12 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 12-June-2026-9 | Frontend: 1) Super Admin log viewer implementation with filtering, analytics, and detailed log inspection capabilities 2) Client-side logging and error reporting enhancements for improved application monitoring 3) Shared UI pattern adoption and frontend styling standardization across dashboard and console modules 4) Workflow history and results management usability improvements, including session persistence and advanced filtering | Medium | 2026-06-12 | 2026-06-12 | Rackesh Kumaran | Completed | Production |  | 4 | 3
vajraglobal.com | Seo Automation Tool | 12-June-2026-10 | Backend: 1) Platform logging framework implementation with centralized log storage and retrieval APIs 2) Frontend error capture and backend log ingestion capabilities with access control and rate limiting 3) Enhanced application observability through automated error tracking and contextual logging improvements 4) Database, logging infrastructure, and API enhancements to support Super Admin monitoring and troubleshooting | Medium | 2026-06-12 | 2026-06-12 | Rackesh Kumaran | Completed | Production |  | 5 | 5.5
www.dgda.gov.sa | National Design System (DGA) | 15-June-2026-1 | Test and fix the Font size in NDS arabic | Medium | 2026-06-15 | 2026-06-15 | Parthiban | Completed | Local |  | 2 | 3
farnborough.com | FIA Maintenance 04 2026 | 15-June-2026-2 | FIA-Move to live and Test the pages | Medium | 2026-06-15 | 2026-06-15 | Parthiban | Completed | Production |  | 2 | 1
www.dgda.gov.sa | DGDA Maintenance June 2026 | 15-June-2026-3 | Submit all the forms in DGDA and take payload | Medium | 2026-06-15 | 2026-06-15 | Parthiban | Completed | Local |  | 2 | 0.45
farnborough.com |  | 15-June-2026-4 | Fix the Log error in Venue | Medium | 2026-06-15 | 2026-06-15 | Parthiban | Completed | Local |  | 2 | 1
intranet.adfactorspr.com | Dev Update June | 15-June-2026-5 | Fix the notification post detail pages issue | Medium | 2026-06-15 | 2026-06-15 | Parthiban | Completed | Local |  | 2 | 1.5
vajraglobal.com |  | 15-June-2026-6 | Analysis the Testing tools for web application | Medium | 2026-06-15 | 2026-06-15 | Parthiban | Completed | Local |  | 1 | 0.5
farnborough.com | FIA Maintenance 04 2026 | 15-June-2026-7 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-15 | 2026-06-15 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 15-June-2026-8 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-15 | 2026-06-15 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 15-June-2026-9 | Frontend : 1) Workflow history and results management enhancements with improved filtering, navigation, and sheet synchronization capabilities 2) Dashboard usability improvements through workflow result shortcuts and theme-based UI refinements 3) Composite workflow experience implementation for alt-text and internal-links automation processes 4) Shared workflow interaction improvements through reusable project selection and workflow patterns | Medium | 2026-06-15 | 2026-06-15 | Rackesh Kumaran | Completed | Production |  | 4 | 4
vajraglobal.com | Seo Automation Tool | 15-June-2026-10 | Backend : 1) Composite workflow architecture implementation for multi-phase automation processes 2) Workflow API enhancements to support grouped workflows and review-driven execution flows 3) Alt-text workflow service implementation with phase-based triggering capabilities 4) Validation and business rule enforcement for approved alt-text injection processes 5) Workflow execution infrastructure improvements using BullMQ job queue integration | Medium | 2026-06-15 | 2026-06-15 | Rackesh Kumaran | Completed | Production |  | 5 | 5.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 15-June-2026-11 | On the Latest Finding Single page change the description text box to RTE and update the content for that page Some items goes to 404 error fix the path issue | Medium | 2026-06-15 | 2026-06-15 | Abhicheke | Completed | Production |  | 5.5 | 5.5 | Code moved to live but on the unpublished |  |  | Summary Page https://feat-finding-details.d38541r9nlp4br.amplifyapp.com/en/latest-findings/ Detail Page https://feat-finding-details.d38541r9nlp4br.amplifyapp.com/en/latest-findings/wadi-safar
farnborough.com | Venue Maintenance June 2026 | 16-June-2026-1 | Venue Site Umbraco version from 13.13.1 to 13.14.0 and site cross test | Medium | 2026-06-16 | 2026-06-18 | Abhicheke | Completed | Production |  | 8 | 8
farnboroughairshow.com | FIA Maintenance June 2026 | 16-June-2026-2 | FIA Site Umbraco version from 13.13.1 to 13.14.0 and site cross test | Medium | 2026-06-16 | 2026-06-18 | Abhicheke | Completed | Production |  | 8 | 8
www.dgda.gov.sa | National Design System (DGA) | 16-June-2026-3 | Remove the green overlay in baneers in NDS | Medium | 2026-06-16 | 2026-06-16 | Parthiban | Completed | Local |  | 2 | 2
www.dgda.gov.sa | National Design System (DGA) | 16-June-2026-4 | Test the added overlay compare with live in English and Arabic | Medium | 2026-06-16 | 2026-06-16 | Parthiban | Completed | Local |  | 2 | 2.5
farnborough.com | FIA Maintenance 04 2026 | 16-June-2026-5 | FIA-Moved to staging | Medium | 2026-06-16 | 2026-06-16 | Parthiban | Completed | Staging |  | 0.5 | 0.5
vajraglobal.com |  | 16-June-2026-6 | Analysis the Testing methods | Medium | 2026-06-16 | 2026-06-16 | Parthiban | Completed | Local |  | 2 | 1.5
intranet.adfactorspr.com | Dev Update June | 16-June-2026-7 | create a Company post name-Employee Name and Employe ID in Post moderation Moved to staging | Medium | 2026-06-16 | 2026-06-16 | Parthiban | Completed | Staging |  | 3 | 2.5
farnborough.com | FIA Maintenance 04 2026 | 16-June-2026-8 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-16 | 2026-06-16 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 16-June-2026-9 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-16 | 2026-06-16 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 16-June-2026-10 | Frontend: 1)Alt-text review workflow enhancements with sheet-based editing, approval management, and Google Sheets synchronization capabilities 2)User experience improvements for Alt Text processing through redesigned layouts and reusable sheet viewing components 3)Platform log viewer refinements with enhanced error insights and improved log navigation 4)Client-side monitoring and authentication experience improvements through global error capture and login error handling enhancements | Medium | 2026-06-16 | 2026-06-16 | Rackesh Kumaran | Completed | Production |  | 4 | 4
vajraglobal.com | Seo Automation Tool | 16-June-2026-11 | Backend: 1) Alt-text workflow enhancements with Google Sheets write-back, production sheet filtering, and automated synchronization processes 2) Platform logging improvements with enriched error context and database-level diagnostic information 3) Authentication security enhancements through account lockout mechanisms and detailed lockout response handling 4) Error handling and configuration updates to support improved system reliability and operational visibility | Medium | 2026-06-16 | 2026-06-16 | Rackesh Kumaran | Completed | Production |  | 5 | 5.5
farnborough.com |  | 17-June-2026-1 | Move to Live and Cross test vennue site Live after version update | Medium | 2026-06-17 | 2026-06-17 | Parthiban | Completed | Production |  | 5 | 3.5
farnboroughairshow.com | FIA Maintenance 04 2026 | 17-June-2026-2 | Cross test FIA site Live after version update | Medium |  |  | Parthiban | Pipeline / To Do | Local
farnborough.com | FIA Maintenance June 2026 | 17-June-2026-3 | Fix the NULL issue in Landing page | Medium | 2026-06-17 | 2026-06-17 | Parthiban | Completed | Staging |  | 2 | 1.5
farnborough.com | FIA Maintenance June 2026 | 17-June-2026-4 | Fix the Log error in Venue Moved to staging | Medium | 2026-06-17 | 2026-06-17 | Parthiban | Completed | Staging |  | 2 | 1
farnboroughairshow.com | FIA Maintenance 04 2026 | 17-June-2026-5 | FIA-Move to staging | Medium | 2026-06-17 | 2026-06-17 | Parthiban | Completed | Staging |  | 0.5 | 0.5
farnboroughairshow.com | FIA Maintenance 04 2026 | 17-June-2026-6 | Cross test the FIA in staging after version update | Medium | 2026-06-17 | 2026-06-17 | Parthiban | Completed | Staging |  | 2 | 1
farnboroughinternationalstudios.com | studio Maintenance 04 2026 | 17-June-2026-7 | Studio Site Umbraco version from 13.13.1 to 13.14.0 and site cross test | Medium | 2026-06-17 | 2026-06-18 | Parthiban | Completed | Production |  | 2 | 1.5
farnborough.com | FIA Maintenance 04 2026 | 17-June-2026-7 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-17 | 2026-06-17 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 17-June-2026-8 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-17 | 2026-06-17 | Rackesh Kumaran | Completed | Production |  | 0.5 | 0.5
farnboroughinternationalstudios.com | FIA Maintenance 04 2026 | 17-June-2026-9 | Testing the full sites and learn how to version update | Medium | 2026-06-17 | 2026-06-17 | Rackesh Kumaran | Completed | Staging |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 17-June-2026-10 | Frontend : 1) Alt-text review workflow enhancements with pagination, bulk approval functionality, and optimized approval processing 2) Review status tracking improvements with approval metrics, status validation, and workflow progress visibility 3) Platform logs and member management enhancements through improved filtering, account status visibility, and UI consistency 4) Dashboard and page layout refinements to improve usability and navigation experience | Medium | 2026-06-17 | 2026-06-17 | Rackesh Kumaran | Completed | Production |  | 4 | 4
vajraglobal.com | Seo Automation Tool | 17-June-2026-11 | Backend : 1) Alt-text workflow enhancements with bulk update APIs, Google Sheets synchronization, and approval validation controls 2) Authentication security improvements through account lockout management and detailed lockout response handling 3) Platform logging enhancements with retention management, automated cleanup, and enriched diagnostic information 4) Member and organization management improvements through account status tracking and API enhancements | Medium | 2026-06-17 | 2026-06-17 | Rackesh Kumaran | Completed | Production |  | 5 | 5
vajraglobal.com | Build Vajra Global overview dashboard |  | Prometheus, Grafana, Blackbox, Alertmanager running on Server 2 | Medium | 2026-06-16 | 2026-06-16 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Config files created |  | prometheus.yml, alert.rules.yml, alertmanager.yml, docker-compose.yml | Medium | 2026-06-16 | 2026-06-16 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Fix Alertmanager crash |  | Debug alertmanager container restart loop — check logs with: docker logs alertmanager | Medium | 2026-06-16 | 2026-06-16 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Log into Grafana |  | Open http://157.245.111.29:3002 — login: admin / vajraGlobal@2024 | Medium | 2026-06-16 | 2026-06-16 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Add Prometheus data source |  | Connections → Data Sources → Add → Prometheus → URL: http://prometheus:9090 → Save & Test | Medium | 2026-06-16 | 2026-06-16 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Import Node Exporter dashboard |  | Dashboards → Import → ID: 1860 → Load → Select Prometheus source → Import | Medium | 2026-06-16 | 2026-06-16 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Import Blackbox dashboard |  | Dashboards → Import → ID: 7587 → Load → Select Prometheus source → Import | Medium | 2026-06-16 | 2026-06-16 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Install Node Exporter — Server 1 (Staging) |  | SSH 139.59.71.225 → download node_exporter v1.8.1 → install as systemd service | Medium | 2026-06-17 | 2026-06-17 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Install Node Exporter — Server 3 (CM) |  | SSH 159.65.158.118 → download node_exporter v1.8.1 → install as systemd service | Medium | 2026-06-17 | 2026-06-17 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Install Node Exporter — Server 4 (Intranet) |  | SSH 64.227.179.180 → download node_exporter v1.8.1 → install as systemd service | Medium | 2026-06-17 | 2026-06-17 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Verify all 4 servers in Prometheus |  | Open http://157.245.111.29:9090/targets — all 4 should show State=UP | Medium | 2026-06-18 | 2026-06-18 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Verify metrics on Grafana dashboard |  | Check Node Exporter Full dashboard shows CPU, RAM, disk, network for all 4 servers | Medium | 2026-06-18 | 2026-06-18 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Verify URL uptime panels |  | Check Blackbox dashboard shows all 8 URLs — green/red status per endpoint | Medium | 2026-06-18 | 2026-06-18 | Moswin | Completed |  |  |  | 0
vajraglobal.com | Build Vajra Global overview dashboard |  | New dashboard → add stat panels for each server's CPU, RAM, disk + URL status row | Medium | 2026-06-19 | 2026-06-19 | Moswin |  |  |  |  | 0
vajraglobal.com | Fix Alertmanager & verify email config |  | Resolve alertmanager crash → send test alert → confirm email arrives at moswin@vajraglobal.com | Medium | 2026-06-19 | 2026-06-19 | Moswin |  |  |  |  | 0
vajraglobal.com | Test disk alert (Server 2) |  | Server 2 disk at 60% — lower threshold temporarily to 55% to trigger test alert | Medium | 2026-06-22 | 2026-06-22 | Moswin |  |  |  |  | 0
vajraglobal.com | Test endpoint down alert |  | Temporarily block a URL in blackbox config → confirm alert email fires within 2 min | Medium | 2026-06-22 | 2026-06-22 | Moswin |  |  |  |  | 0
vajraglobal.com | Restore thresholds & document |  | Reset alert thresholds to production values. Document: what each alert means + who to call | Medium | 2026-06-23 | 2026-06-23 | Moswin |  |  |  |  | 0
vajraglobal.com | Restrict port 9090 & 3002 |  | DigitalOcean firewall → limit port 3002 and 9090 to your office IP only (not all IPv4) | Medium | Wed 24 Jun | Wed 24 Jun | Moswin |  |  |  |  | 0
vajraglobal.com | Change Grafana default password |  | Grafana → Profile → Change password from vajraGlobal@2024 to a stronger password | Medium | Wed 24 Jun | Wed 24 Jun | Moswin |  |  |  |  | 0
vajraglobal.com | Final check & sign-off |  | All 4 servers showing metrics. All 8 URLs monitored. At least 1 test alert received. | Medium | Wed 24 Jun | Wed 24 Jun | Moswin |  |  |  |  | 0
farnborough.com | FIA Maintenance 04 2026 | 18-June-2026-1 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-18 | 2026-06-18 | Rackesh Kumaran |  |  |  | 0.5 | 0.5
www.dgda.gov.sa | DGDA Maintenance June 2026 | 18-June-2026-2 | Daily Monitoring and Update in sheet for all Websites | Medium | 2026-06-18 | 2026-06-18 | Rackesh Kumaran |  |  |  | 0.5 | 0.5
vajraglobal.com | Seo Automation Tool | 18-June-2026-3 | Frontend : 1) Authentication and security workflow enhancements with forced password change, password policy validation, and improved user onboarding experience 2) Member management and presence tracking improvements with activity visibility and account status enhancements 3) Pagination usability improvements through direct page navigation and optimized page handling 4) UI and table layout refinements for better responsiveness, accessibility, and dark-mode compatibility | Medium | 2026-06-18 | 2026-06-18 | Rackesh Kumaran | Completed | Production |  | 4 | 4
vajraglobal.com | Seo Automation Tool | 18-June-2026-4 | Backend : Security Phase C implementation with advanced authentication hardening, password policy enforcement, and refresh token security controls Session management enhancements including token revocation, reuse detection, and forced password change workflows Authentication API improvements with validation controls, rate limiting, and comprehensive security testing Member oversight and organization management enhancements through presence tracking, activity monitoring, and administrative controls | Medium | 2026-06-18 | 2026-06-18 | Rackesh Kumaran | Completed | Production |  | 5 | 5.5
farnboroughairshow.com | FIA Maintenance 04 2026 | 18-June-2026-5 | FIA-Move and Cross Test the entire site Fix and check the CSP errors Test all the forms | Medium | 2026-06-18 | 2026-06-18 | Parthiban | Completed |  |  | 5 | 4
farnboroughinternationalstudios.com | Studio Maintenance 04 2026 | 18-June-2026-6 | Studio Site Umbraco version from 13.13.1 to 13.14.0 and site cross test Test all the forms | Medium | 2026-06-18 | 2026-06-18 | Parthiban | Completed |  |  | 3 | 3
farnboroughairshow.com | FIA Maintenance 04 2026 | 18-June-2026-7 | FIA-Update query in table and Move the files | Medium | 2026-06-18 | 2026-06-18 | Parthiban | Completed |  |  | 0.5 | 0.5
www.dgda.gov.sa | EMS Project | 18-June-2026-8 | Cross Test the DGDA EMS | Medium | 2026-06-18 | 2026-06-18 | Parthiban | Completed |  |  | 1 | 1.5
0
0
0
0
0
0
0
0

## Leave Tracker
Employee Name | Leave Type | From Date | To Date | Actual Leave | Which Actual Days | Which Total Days | Total Days | Half Day / Full Day | Status | Comp Off Date | Reason for Leave | Any Deliver On This Week | Emergency Leave | Applied Date | Leave Status | Approved By | Approval Date | Rejection Reason
Moswin | Casual Leave | 2026-05-15 | 2026-05-15 | 1 | Friday | Friday, Saturday, Sunday | 3 | Full Day | Completed |  |  | No |  | 2026-05-07 | Approved | Sunder | 2026-05-07
Abhicheke | Casual Leave | 2026-05-18 | 2026-05-22 | 5 | Monday, Tuesday, Wednesday, Thursday, Friday | Saturday, Sunday, Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday | 9 | Full Day | Completed |  |  | No |  | 2026-04-24 | Approved | Sowndar | 2026-04-09
Rackesh Kumaran | Sick Leave | 2026-05-19 | 2026-05-19 | 0.5 | Second Half - Tuesday | Second Half - Tuesday | 0.5 | Second Half | Completed |  | Food Poison | No |  | 2026-05-19 | Approved | Sowndar | 2026-05-19
Rackesh Kumaran | Sick Leave | 2026-05-20 | 2026-05-20 | 1 | Wednesday | Wednesday | 1 | Full Day | Completed |  | Food Poison | No |  | 2026-05-20 | Approved | Sowndar | 2026-05-20
Rackesh Kumaran | Sick Leave | 2026-05-21 | 2026-05-21 | 1 | Thursday | Thursday | 1 | Full Day | Completed |  | Food Poison | No |  | 2026-05-21 | Approved | Sowndar | 2026-05-21
Rackesh Kumaran | Sick Leave | 2026-05-22 | 2026-05-22 | 1 | Friday | Friday, Saturday, Sunday | 3 | Full Day | Completed |  | Food Poison | No |  | 2026-05-21 | Approved | Sowndar | 2026-05-21
Rackesh Kumaran | Sick Leave | 2026-05-25 | 2026-05-29 | 5 | Monday, Tuesday, Wednesday, Thursday, Friday | Saturday, Sunday, Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday | 9 | Full Day | Completed |  | Food Poison | No |  | 2026-05-21 | Approved | Sowndar | 2026-05-21
Abhicheke | Casual Leave | 2026-05-28 | 2026-05-29 | 2 | Thursday, Friday | Thursday, Friday, Saturday, Sunday | 4 | Full Day | Completed |  | Going to Temple | No |  | 2026-04-24 | Approved | Sowndar | 2026-04-09
Moswin | Casual Leave | 2026-05-29 | 2026-05-29 | 0.5 | Second Half - Friday | Saturday, Sunday, Second Half - Friday, Saturday, Sunday | 2.5 | Second Half | Completed |  | - | No |  | 2026-05-14 | Approved | Sowndar | 2026-05-29
Parthiban | Casual Leave | 2026-06-01 | 2026-06-01 | 1 | Monday | Saturday, Sunday, Monday | 3 | Full Day | Completed |  | Going to Native | No |  | 2026-05-14 | Approved | Sowndar | 2026-05-20
Moswin | Casual Leave | 2026-06-02 | 2026-06-02 | 0.5 | Second Half - Tuesday | Second Half - Tuesday | 0.5 | Second Half | Completed |  | Going to Native | No |  | 2026-06-02 | Approved | Sowndar | 2026-06-02
Moswin | Casual Leave | 2026-06-03 | 2026-06-03 | 1 | Wednesday | Wednesday | 1 | Full Day | Completed |  | Going to Native | No |  | 2026-06-02 | Approved | Sowndar | 2026-06-02
Parthiban | Casual Leave | 2026-06-08 | 2026-06-08 | 1 | Monday | Saturday, Sunday, Monday | 3 | Full Day | Completed |  | Medical apointment for mother | No |  | 2026-06-04 | Approved | Sowndar | 2026-06-04
Formulas:
Actual Leave = IF([Half Day / Full Day]="First Half",0.5, IF([Half Day / Full Day]="Second Half",0.5, NETWORKDAYS([From Date],[To Date])))
Status = IF([Approved By]="Pending","Waiting Approval", IF([Approved By]="Rejected","Rejected", IF([Approved By]="Cancelled","Cancelled", IF(TODAY()<[From Date],"Upcoming", IF(AND(TODAY()>=[From Date],TODAY()<=[Approval Date]),"In Progress", IF(TODAY()>[Approval Date],"Completed",""))))))
Status = IF([Approved By]="Pending","Waiting Approval", IF([Approved By]="Rejected","Rejected", IF([Approved By]="Cancelled","Cancelled", IF(TODAY()<[From Date],"Upcoming", IF(AND(TODAY()>=[From Date],TODAY()<=[To Date]),"In Progress", IF(TODAY()>[To Date],"Completed",""))))))

## Internal Tracker 2026
Project Name | Website Url | Task | Priority | Assign | S Date | E Date | As Per WO | Status | Env | Efforts | Actual Effors | Informed | Support Needed / Blocker | Dependency Detail | Page Url | Mail Subject | Internal Mail Subject | Functionality | My Understanding
Vajra Global | vajraglobal.com | Meeting with Sundar on Next Week | Low | Sowndar | 2026-03-24 | 2026-03-24 | 2026-03-24 | Completed |  | No Subtasks |  |  | I have set the meeting with Sundar on 24 March
Vajra Global |  | Rakesh Traing | Low | Sowndar |  |  |  | Completed |  | No Subtasks |  |  | Training has done. We start giving the basic task. We gradually increase the work on upcoming days
Vajra Global | vajraglobal.com | Request for Additional Static IP for Chennai Office | Low | Sowndar | 2026-03-19 | 2026-04-01 |  | Completed |  | No Subtasks
Vajra Global | vajraglobal.com | Upcoming Leave Notification For Sai | Low | Sowndar |  | 2026-03-18 |  | Completed |  | No Subtasks |  |  | Sai will be unavailable from May 22 to June 07, 2026, due to his wedding. We will require an alternative resource to manage the project during his absence As we disscussed over the meeting Regan will take care of Fanborought and I will coordinate with Adfactor team |  |  |  | [NEW TASK] [Vajra] Sai Vacation Holiday
Vajra Global | vajraglobal.com | Upcoming Leave Notification For abhicheke | Low | Sowndar |  | 2026-03-18 |  | In Progress |  | No Subtasks |  |  | Abhishek Wedding Leave (Staggered Schedule): Based on project requirements, the leave has been restructured into a staggered format to maintain momentum: 11 May & 12 May: Leave 18 May – 24 May: Leave 25 May – 27 May: Working / Check-in Window (To address urgent blockers) 28 May & 29 May: Leave |  |  |  | [NEW TASK] [Vajra] Abi Vacation Holiday
Vajra Global | vajraglobal.com | Umbraco sites Pitch | Low | Sowndar | 2026-01-06 |  |  | In Progress |  | No Subtasks | [6 empty] | New Outreach Project: Targeting Legacy Umbraco 7,8,9 & 10 Sites
Vajra Global | vajraglobal.com | CI/CD Automation For all Website | Low | Moswin |  |  |  | In Progress |  | No Subtasks | [6 empty] | Important mainly because it was sent directly to you
Vajra Global | vajraglobal.com | Updated Updated SEO Automation BRD BRD | Low | Moswin |  |  |  | In Progress |  | No Subtasks | [6 empty] | Click to teach Vajra Global Consulting Services LLP Mail this conversation is not important
Vajra Global | vajraglobal.com | Server Inventory | Low | Moswin | 2026-02-23 | 2026-04-15 | 2026-04-08 | In Progress |  | No Subtasks
Vajra Global | vajraglobal.com | Internal links | Low | Moswin | 2026-04-08 | 2026-04-17 | 2026-04-17 | In Progress |  | ⚠ Missing Effort
Vajra Global | vajraglobal.com | DevOps as a Service (DaaS) | Low | Moswin | 2026-04-07 | 2026-04-13 | 2026-04-13 | In Progress |  | ⚠ Missing Effort |  |  |  |  | Vajra_DevOps_as_a_Service.xlsx
⚠ Missing Effort
⚠ Missing Effort
⚠ Missing Effort
⚠ Missing Effort
⚠ Missing Effort
⚠ Missing Effort
⚠ Missing Effort
⚠ Missing Effort
⚠ Missing Effort

## Team Capacity
Member | Project | Type | Activity | Task | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Monthly Overall Utilization | Monthly Available
Sowndar | Internal Communcation | Non - Billable | PM | Communication |  | 10 | 5 | 5 | 5 | 2 | 117 | 108
| Client Communication | Non - Billable | Dev | Communication |  | 3 | 3 | 3 | 3 | 3
| EM | Billable | PM/Dev | Dev/Communication |  | 15 | 15 | 15 | 15 | 15
| FIA | Billable | Dev | Exhibitor API
[5 empty] | Weekly Utilization | 28 | 23 | 23 | 23 | 20
[5 empty] | Weekly Available | 17 | 22 | 22 | 22 | 25
Member | Project | Type | Activity | Task | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Monthly Overall Utilization | Monthly Available
Abhicheke | DGDA | Billable | Dev | National Design System design apply for all Pages feedback changes | Waiting for Client Input | 25 | 0 | 0 | 0 | 0 | 195 | 30
| Work Adfactors | Billable | Live | Work Adfactors Staging and Live Restore cross test | Not Started | 0 | 0 | 20 | 5 | 5
| DGDA | Billable | Dev | Quamatic Integration | Waiting for Client Input | 0 | 0 | 5 | 5 | 5
| DGDA | Billable | Dev | Emergency services form | Waiting for Client Input | 10 | 15 | 0 | 5 | 0
| DGDA | Billable | Dev | Whatsapp integration | Waiting for Client Input | 0 | 20 | 0 | 15 | 0
| Farnborough Airshow | Billable | Live | Event Task and Landing Page and forms | Waiting for Client Input | 0 | 0 | 10 | 10 | 20
| Internal Communication | Non - Billable | - | Task Discussion,Team Call | In Progress | 5 | 5 | 0 | 5 | 5
[5 empty] | Weekly Utilization | 40 | 40 | 35 | 45 | 35
[5 empty] | Weekly Available | 5 | 5 | 10 | 0 | 10
Member | Project | Type | Activity | Task | Status | Week 1 | Week 2 | 5 | Week 4 | Week 5 | Monthly Overall Utilization | Monthly Available
| Adfactors | Billable | Live | Home page and brand kit changes | In Progress | 12 | 0 | 0 | 5 | 0
Parthiban | Adfactors | Billable | Live | Enchance Admin dashboard | Not Started | 0 | 0 |  | 0 | 0 | 120 | 105
| Adfactors | Billable | Live | Case Study-New Templete | Not Started | 0 | 13 | 0 | 0 | 0
| Adfactors | Billable | Live,staging | Adfactors Chnages June | Not Started | 0 | 5 | 0 | 20 | 0
| Work Adfactors | Billable | Live | Work Adfactors Staging and Live Restore and test all pages | Not Started | 0 | 0 | 25 | 5 | 10
| Adfactors | Billable | Live,staging | Add Mention tag and get notfication for the Corresponding User after system generated post | Not Started | 0 | 0 | 0 | 0 | 5
| Internal Communication | Non - Billable | - | Task Discussion,Team Call | In Progress | 5 | 5 | 5 | 5 | 5
[5 empty] | Weekly Utilization | 17 | 23 | 25 | 35 | 20
[5 empty] | Weekly Available | 28 | 22 | 20 | 10 | 25
Member | Project | Type | Activity | Task | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Monthly Overall Utilization | Monthly Available
Rackesh | DGDA | Billable | live | Site cross testing & Form Testing | In Progress | 5 | 5 | 5 | 5 | 5 | 195 | 30
| Adfactors | Billable | live | Site cross testing & Form Testing | In Progress | 5 | 5 | 5 | 5 | 5
| SEO Automation Tool | Non - Billable | Dev | Make the frontend and backend setup and working in the login and signin/up functionality | In Progress | 20 | 20 | 20 | 20 | 20
| n8n automation | Non - Billable | local | Learning and implementation to automate the process | In Progress | 2 | 2 | 2 | 2 | 2
| Internal Communication | Non - Billable | - | Task Discussion,Team Call | In Progress | 5 | 5 | 5 | 5 | 5
| AEM | Non - Billable | live | Learning and implementation | In Progress | 2 | 2 | 2 | 2 | 2
| adfactors | Billable | live | phase 2 changes | In Progress | 0 | 0 | 0 | 0 | 0
[5 empty] | Weekly Utilization | 39 | 39 | 39 | 39 | 39
[5 empty] | Weekly Available | 6 | 6 | 6 | 6 | 6
Member | Project | Type | Activity | Task | Status | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Monthly Overall Utilization | Monthly Available
Moswin | SEO Automation | Non - Billable | Dev | Roadmap planning + N8n UI Build | In Progress | 10 | 10 | 10 | 0 | 0 | 207 | 18
| SEO Automation | Non - Billable | Live | Competitor analysis | In Progress | 35 | 5 | 0 | 0 | 0
| SEO Automation | Non - Billable | Live | Backllink Monitoring | Not Started | 0 | 25 | 5 | 0 | 0
| Vajra Product Applications Monitoring. | Non - Billable | Live | Monitoring set up with external tools for all our Internal projects. | Not Started | 0 | 0 | 25 | 5 | 0
| DGDA Monitoing | Billable | Live | DGDA Monitoing | In Progress | 2 | 2 | 2 | 2 | 2
| Maintain and backup Client cloud cluster data base. | Non - Billable | Live | https://clients.cloudclusters.io/ understanding and set up backup. | Not Started | 0 | 0 | 2 | 20 | 0
| SEO Automation | Non - Billable | Live | Indexing Status | Not Started | 0 | 0 | 0 | 15 | 10
| SEO Automation | Non - Billable | Live | Keyword Research | Not Started | 0 | 0 | 0 | 0 | 20
[5 empty] | Weekly Utilization | 47 | 42 | 44 | 42 | 32
[5 empty] | Weekly Available | -2 | 3 | 1 | 3 | 13

## Internal Tracker Sub 2026
Project Name | Main Task Name | Ticket Id | Task | Priority | S Date | E Date | Assigned to | Status | Env | As Per WO | Efforts | Actual Efforts | Informed | Support Needed / Blocker | Dependency Detail | Page Url | Mail Subject | Internal Mail Subject
www.vajraglobal.com/ | Umbraco sites Pitch |  | Targeting Legacy Umbraco 7,8,9 & 10 Sites | Low | 2026-01-06 | 2026-01-06 | Sowndar | Completed | Production |  | 0 | 0
www.vajraglobal.com/ | Umbraco sites Pitch |  | Targeting Legacy Umbraco 7,8,9 & 10 Sites | Low | 2026-02-12 | 2026-02-12 | Sowndar | Completed | Production |  | 0 | 0
| Updated Updated SEO Automation BRD BRD |  | Updated Updated SEO Automation BRD BRD | [7 empty] | 0 | 0
vajraglobal.com | Review High CPU Usage |  | Server Inventory | Low | 2026-03-20 | 2026-03-20 | Moswin | In Progress | Production |  | 0 | 0
| Server Inventory |  | Migration of MarketingOps frontent and backend, DB to the new server is done. Frontend and backend health is working. There are some application connection issues in there. Will work with Boopesh to chck on that today. | Medium | 2026-03-13 | 2026-03-13 | Moswin | Completed | Production |  | 6 | 0
| Updated SEO Automation BRD |  | Competitor analysis started working as discussed. but the project api which we are using wasnt able to fetch the output that we required. So need to find an alternate method. | Low | 2026-03-16 | 2026-03-16 | Moswin | Completed | Production |  | 3 | 0
| Updated SEO Automation BRD | 19-Mar-2026-1 | Alt text workflow phase 1 completed and shared with valli and team for validation. | Low | 2026-03-19 | 2026-03-19 | Moswin | Completed | Production |  | 9 | 0
| Updated SEO Automation BRD | 19-Mar-2026-2 | 2 improvements on 19-Mar-2026-1 completed | Low | 2026-03-23 | 2026-03-23 | Moswin | Completed | Production |  | 6 | 0 |  | Following our review, we've made two improvements: Alt Text Quality — The generated alt texts were too generic. We've refined the prompt by providing context from the article title, page context, and the image itself and after reviewing the latest outputs, the quality now meets our expectations. Image Filtering — A number of images being pulled were standalone assets not attached to any articles. We've updated the workflow to skip these entirely, so only relevant article images are processed.
| Server Inventory |  | Snapshot of the server taken, and decommisioned the server. Server and projects were monitored for the last 5 days. | Medium | 2026-03-23 | 2026-03-23 | Moswin | Completed | Production |  | 2 | 0 |  | Everything looks stable and normal. We have taken a backup snapshot of the server and decommissioned it. The snapshot will be retained for the next 5 days as a safety net before deletion. Additionally, I believe we have an opportunity to reduce one more server by consolidating and redistributing some projects. I will discuss this with Sunder Sir and come back with a plan tomorrow.
| AstonBrooke local environment set up. |  | For Aston Brooke set up the private key files in Kushall's laptop and have provided the updated commands to move the backend project into the server. | Medium | 2026-03-20 | 2026-03-20 | Moswin | Completed | Production |  | 1 | 0
| AstonBrooke local environment set up. |  | FTP set up done for AB in Kushall's laptop for Filezilla | Medium | 2026-03-24 | 2026-03-24 | Moswin | Completed | Production |  | 2 | 0
| Kreab billing invoice |  | Kreab billing cycle invoice fetch from AWS and sent to accounts team. MFA was with Ram so had to get it from him and further have changed it my device for future purposes | Medium | 2026-03-24 | 2026-03-24 | Moswin | Completed | Production |  | 2 | 0
| Server Inventory |  | Backup plan and cost sheet has been prepared ( | Medium | 2026-03-24 | 2026-03-24 | Moswin | Completed | Production |  | 2 | 0
https://automation.vajraglobal.com/ | Updated SEO Automation BRD |  | Alt text Phase 2 - Pause mechanism planned and how we can get validation and update only the ones that are approved have been finalized with Valli. Initiall set up has also been started | Medium | 2026-03-24 | 2026-03-24 | Moswin | Completed | Production |  | 2 | 0
https://automation.vajraglobal.com/ | Updated SEO Automation BRD |  | Have completed Alt text end to end. ( 7 hours) Phase 1 : from collecting missing alt texts information with the details. Phase 2 : generating alt texts and confirming approval from the SEO team. Phase 3 : Inject only the approved alt texts in the site. Pending : Need to plan with valli for creating a button to initiate the workflow externally. |  | 2026-03-25 | 2026-03-25 | Moswin | Completed | Production |  | 7 | 0
https://msmehealthengine.fametn.com/ | MSME |  | Working with Bboopesh on MSME for creation of super admin user, docker issues, setting up in a way that another repo can also move the backend to the same server |  | 2026-03-25 | 2026-03-25 | Moswin | Completed | Production |  | 2 | 0
https://msmehealthengine.fametn.com/ | MSME |  | MSME super admin user issues resolved and moved the code to staging. |  | 2026-03-26 | 2026-03-26 | Moswin | Completed | Production |  | 3 | 0
https://automation.vajraglobal.com/ | Updated SEO Automation BRD |  | ALT text - Need to plan with valli for creating a button to initiate the workflow externally. Button trigger for both the workflows through webhooks created new issues. All resolved and now everything is ready. |  | 2026-03-26 | 2026-03-26 | Moswin | Completed | Production |  | 5 | 0
vajraglobal.com | Server Inventory |  | 1C2GB-N8n.monitoringTools.ContentPubWDS-LIVE server clean up activity done brining down the space from 42 GB to 29 GB saving cost for backing up and potentially move project too in there. |  | 2026-03-26 | 2026-03-26 | Moswin | Completed | Production |  | 2 | 0
vajraglobal.com | Server Inventory |  | 2C4GB-Intranet.Kreab.thoughtleadership-STAGING storage brought down from 43 to 26 GB by doing some housekeeping activities and clearing old images, and logs. |  | 2026-03-27 | 2026-03-27 | Moswin | Completed | Production |  | 3 | 0
vajraglobal.com | Server Inventory |  | backups set up for all servers. Plan and cost estimation sheet is also done Server Inventory - Vajra |  | 2026-03-27 | 2026-03-27 | Moswin | Completed | Production |  | 2 | 0
vajraglobal.com | Server Inventory |  | Alerts and monitoring for all servers is also set up in Digital ocean |  | 2026-03-27 | 2026-03-27 | Moswin | Completed | Production |  | 2 | 0
https://astonbrooke.co.uk/ | Aston Brooke |  | Aston Brooke nginix set up call with Kushall |  | 2026-03-30 | 2026-03-30 | Moswin | Completed | Production |  | 2 | 0
https://automation.vajraglobal.com/ | Updated SEO Automation BRD |  | Tracking code and robots.txt failed due to too many requests in Excel. Have set up service accounts for them and it's working now. |  | 2026-03-30 | 2026-03-30 | Moswin | Completed | Production |  | 2 | 0
https://msmehealthengine.fametn.com/ | MSME |  | msme backend changes moved to staging - worked with Bboopesh |  | 2026-03-30 | 2026-03-30 | Moswin | Completed | Production |  | 2 | 0
https://automation.vajraglobal.com/ | Updated SEO Automation BRD |  | Alt text have set up so that credentials are taken in dynamically and used in the workflows as per the project |  | 2026-03-30 | 2026-03-30 | Moswin | Completed | Production |  | 4 | 0
https://automation.vajraglobal.com/ | Updated SEO Automation BRD |  | Alt text demo and follow up email |  | 2026-03-31 | 2026-03-31 | Moswin | Completed | Production |  | 2 | 0
https://automation.vajraglobal.com/ | Updated SEO Automation BRD |  | Prepare plan sheet for Alt text tool |  | 2026-03-31 | 2026-03-31 | Moswin | Completed | Production |  | 2 | 0
vajraglobal.com | Server Inventory |  | 1C2GB-ContentOps.MarketingOps.InterlarcBakcend-LIVE disk space reduced from 24 to 11 GB by doing some house keeping activities. |  | 2026-03-31 | 2026-03-31 | Moswin | Completed | Production |  | 2 | 0
https://automation.vajraglobal.com/ | Updated SEO Automation BRD |  | Enable a pop up notification when alt text generation is complete. |  | 2026-03-31 | 2026-04-01 | Moswin | Completed | Production |  | 3 | 0
vajraglobal.com | Server Inventory |  | Discuss with Bboopesh and Sunder and provide a plan with sir for the migration and risks involved with ETA |  | 2026-04-01 | 2026-04-01 | Moswin | Completed | Production |  | 3 | 0
vajraglobal.com | Learning |  | Claude Code - learn to utilize it for keyword research , competitior analysis or anyother upcoming automations. |  | 2026-04-01 | 2026-04-02 | Moswin | Completed | Production |  | 4 | 0
vajraglobal.com | Server Inventory |  | move marketingOPS-backend project to Intranet staging server |  | 2026-04-02 | 2026-04-02 | Moswin | Completed | Production |  | 6 | 0
vajraglobal.com | Updated SEO Automation BRD |  | set up mail node and get review from valli |  | 2026-04-02 | 2026-04-02 | Moswin | Completed | Production |  | 1 | 0
vajraglobal.com | Server Inventory |  | Migrate contentops-backend application to 1C2GB-N8n.monitoringTools.ContentPubWDS-LIVE |  | 2026-04-06 | 2026-04-06 | Moswin | Completed | Production |  | 6 | 0
https://msmehealthengine.fametn.com/ | MSME |  | Set up Pritunl and server VPN access for staging backend, live backend and data base server machines with commands |  | 2026-04-06 | 2026-04-06 | Moswin | Completed | Production |  | 1 | 0
vajraglobal.com | Updated SEO Automation BRD |  | Respond to sir mail with 4 week plan for SEO Prepare plan sheet for competitor analysis with claude code Prepare plan sheet for keyword research analysis with claude code. |  | 2026-04-06 | 2026-04-07 | Moswin | Completed | Production |  | 6 | 0
vajraglobal.com | Server Inventory |  | Migrate intelarc-api backend application to 2C4GB-Intranet.Kreab.thoughtleadership-STAGING |  | 2026-04-07 | 2026-04-07 | Moswin | Completed | Production |  | 6 | 0
vajraglobal.com | DevOps as a Service (DaaS) |  | Prepare sales pitch required details to Sriram sir for DevOps as a Service(DaaS) https://docs.google.com/spreadsheets/d/1VcZ3dgg0Ass8GliDR3zhezHmsi_LzdkC/edit?usp=sharing&ouid=108220845174973423951&rtpof=true&sd=true |  | 2026-04-07 | 2026-04-08 | Moswin | Completed | Production |  | 3 | 0
vajraglobal.com | Updated SEO Automation BRD |  | Internal Links - Have set up credentials and fetching all pages with pagination steps are done. |  | 2026-04-08 | 2026-04-08 | Moswin | Completed | Production
vajraglobal.com | Internal links |  | Internal links |  | 2026-04-09 | 2026-04-17 | Moswin | In Progress | Local |  | 90 |  |  | 50 % completed.
vajraglobal.com | Internal links |  | Workflow architecture plan |  | 2026-04-08 | 2026-04-08 | Moswin | Completed | Local |  | 3
vajraglobal.com | Internal links |  | Google Sheet approval schema |  | 2026-04-08 | 2026-04-08 | Moswin | Completed | Local |  | 3
vajraglobal.com | Internal links |  | N8N WP credentials setup |  | 2026-04-08 | 2026-04-08 | Moswin | Completed | Local |  | 3
vajraglobal.com | Internal links |  | Phase 1 — Crawl workflow |  | 2026-04-09 | 2026-04-09 | Moswin | Completed | Local |  | 3
vajraglobal.com | Internal links |  | Phase 1 — OpenAI suggestion engine |  | 2026-04-09 | 2026-04-09 | Moswin | Completed | Local |  | 3
vajraglobal.com | Internal links |  | Phase 1 — dry run on 5 posts |  | 2026-04-09 | 2026-04-09 | Moswin | Completed | Local |  | 3
vajraglobal.com | Internal links |  | Phase 1 - Improvements. Generate source, target, anchor text, paragraph context, insertion text for the eligible high confidence interlinks. |  | 2026-04-10 | 2026-04-10 | Moswin | Completed | Local |  | 5
www.vajraglobal.com/ | Server Inventory |  | Route traffic of 3 applications to their respective updated server machines. |  | 2026-04-08 | 2026-04-10 | Moswin | Completed | Production |  | 2 | 5
vajraglobal.com | Internal links |  | Phase 1 - Fixes pending. Remove duplicates, EMPTY / INVALID ITEMS with low confidence, improve ANCHOR TEXT QUALITY, handle SYMMETRICAL LINKS |  | 2026-04-10 | 2026-04-13 | Moswin | Completed | Local |  | 8 | 12 |  | Outputs for all pages received as expected,
vajraglobal.com | Internal links |  | Generated values of keywords topic id title url slug excerpt content_short content_full source_url target_url anchor_text insertion_text row_type reason confidence decision edited_anchor edited_insertion status fetched and updated in sheet properly with the multiple suggestion logic. |  | 2026-04-14 | 2026-04-14 | Moswin | Completed | Local |  | 6 | 6 |  | Completed. added new coloumn for the suggestions so the seo team can singularly select only those to approve.
vajraglobal.com | Internal links |  | Read final sheet, prepare inject content, extract post content , prepare and inject only if approved , update in sheet the status. |  | 2026-04-15 | 2026-04-15 | Moswin | Completed | Local |  | 6 | 6 |  | Completed with this too. some inputs mismatatched which led to some issues. that took some time to troubleshoot.. Pending: Get approval from Naresh and do a test run in staging wordpress sites.
vajraglobal.com | DevOps as a Service (DaaS) |  | Research Upwork and LinkedIn, find similar profiles and share with Sriram Sir with details of what all we can do like that. |  | 2026-04-15 | 2026-04-17 | Moswin | Completed | Local |  | 2 | 2 |  | Comment: Upwork_DevOps_research.xlsx Created a profile in upwork and research the kind of jobs we can do. and found some other freelancers by loggin in hiring mode. and fetched some people who do something like this full time and have good rating. LinkedIn will do tomorrow.
https://msmehealthengine.fametn.com/ | MSME |  | N8n workflow to fetch and provide invalid(non-deliverable) emails out of the list. |  | 2026-04-17 | 2026-04-17 | Moswin | Completed | Production |  | 6 | 6
https://msmehealthengine.fametn.com/ | MSME |  | 1. Plan how we can set up filters on top of AWS SES to find bounce back mails. 2. Send client with steps needed to be done. |  | 2026-04-20 | 2026-04-20 | Moswin | Completed | Local |  | 5 | 5
vajraglobal.com | Server Inventory |  | Nginx set up, SSL cert set up, IP pointing done. One application has issues, have shared it with the dev team. |  |  |  | Moswin | Completed |  |  | 4 | 4 |  | With the dev team for troubleshooting issues in backend.
vajraglobal.com | Updated SEO Automation BRD |  | 1. Prepare new data and keep it ready for Demo with Valli 2. Collect data on time saved information. 3. Complete demo call |  | 2026-04-21 | 2026-04-21 | Moswin | Completed | Local |  | 6 | 6
vajraglobal.com | DevOps Vajra Voyage |  | "System Stability post Go-Live ≥ 98%" this means all servers should be up and running. if something goes wrong we need a plan to recover and be back up and running without any data lose. I need to detail plan for this. Also for all applications should be running and that also needs to be tracked regularly. if it goes down, how to bring them up and running. We need document for all applications |  | 2026-04-17 | 2026-04-22 | Moswin | Completed | Local |  | 8 | 8 |  | https://docs.google.com/document/d/1KHg8muxaUMm2emsl9NOzYrZwD9Nzd7dR/edit?usp=sharing&ouid=108220845174973423951&rtpof=true&sd=true
https://msmehealthengine.fametn.com/ | MSME |  | Discussion call with Kiruba, Thamil and Bboopesh on the bounce back mail alternatives. Corrections has been done and moved to live for testing. Pritunl issue in Bboopesh laptop, cant find the rootcause. Running it temporarily in my laptop |  | 2026-04-21 | 2026-04-21 | Moswin | Completed | Staging |  | 3 | 3
https://msmehealthengine.fametn.com/ | MSME |  | Mail otp expiry is 2 mins in code. But is 10 mins by default. Figure out a way to reduce to 2 mins using aws. |  | 2026-04-24 | 2026-04-24 | Moswin | Completed | Production
vajraglobal.com | Server Inventory |  | Delete Droplet |  | 2026-04-24 | 2026-04-24 | Moswin | Completed | Production
vajraglobal.com | Internal links |  | Ui buttons for generation and Inject procedure. |  | 2026-04-24 | 2026-04-24 | Moswin | Completed | Production
vajraglobal.com | Server Inventory |  | For all our applications set up uptime monitoring for health endpoint api. |  | 2026-04-27 | 2026-04-29 | Moswin | Completed | Production |  | 4 |  |  |  | need health enpoints from the dev team. or ask them to set up end points then.
vajraglobal.com | Server Inventory |  | Analyse best monitoring tool we can set up for the error logs define thresholds and set up proper mailing system for increased error from specific applications and provide details to Sunder Sir |  | 2026-04-27 | 2026-04-27 | Moswin | Completed | Production |  |  |  |  | Grafana + Loki + Promtail | need dev team to set up logs. send mail to the team.
vajraglobal.com | Updated SEO Automation BRD |  | Prepare FRD for SEO Automation |  | 2026-04-28 | 2026-04-29 | Moswin | Completed |  |  | 4
vajraglobal.com | Updated SEO Automation BRD |  | Discussion with Kiruba for UI set for SEO Automation. |  | 2026-04-28 | 2026-04-28 | Moswin | Completed |  |  | 3 | 3
vajraglobal.com | Updated SEO Automation BRD |  | Preparation and Discussion with Valli and Balaji for UI set up for SEO Automation. |  | 2026-04-29 | 2026-04-29 | Moswin | Completed |  |  | 2
vajraglobal.com | Server Inventory |  | Client CloudClusters understanding and backup set up. |  | 2026-04-28 | 2026-04-29 | Moswin | Completed |  |  | 6 |  |  |  | Have responded to G sir and Sunder Sir queries. Need approval from sir for the cost, post that will enable db backups.
vajraglobal.com | Updated SEO Automation BRD |  | demo video send for alt text for context for balaji |  | 2026-04-30 | 2026-05-30 | Moswin | Completed
vajraglobal.com | Goal towards 99.99% availability |  | tech team applications uptime monitoring set up for their end points |  | 2026-04-30 | 2026-04-30 | Moswin | Completed | Production
vajraglobal.com | Goal towards 99.99% availability |  | Mail send for error logs set up and mail to Sriram sir with all the documents and data required. |  | 2026-04-30 | 2026-04-30 | Moswin | Completed | Production
vajraglobal.com | ?? |  | Hi Moswin, can you read on this topic and explain to me. no time pressure. take you own time. but we need to understand this in detail. https://www.linkedin.com/posts/leadgenmanthan_claude-code-can-now-run-any-cli-for-you-activity-7453738322599763968--WZH |  | 2026-05-04 | 2026-05-05 | Moswin | Completed | Production |  | 6 | 8 |  |  | Completed on my end, Sir told he will get back when he is available.
vajraglobal.com | Updated SEO Automation BRD |  | Prepare Road map / demo / discussion with Valli on the same. |  | 2026-05-04 | 2026-05-04 | Moswin | Completed | Production
vajraglobal.com | DevOps as a Service (DaaS) |  | Devops as a service sales team discussion this week with Sriram Sir |  | 2026-05-05 | 2026-05-06 | Moswin | Completed | Production
vajraglobal.com | CI/CD |  | Testing for all CICD workflows in Hellowiz and corrections for the same |  | 2026-05-11 | 2026-05-11 | Moswin | Completed | Production
vajraglobal.com | Updated SEO Automation BRD |  | Alt text generation for Vachi HR - Staging |  | 2026-05-11 | 2026-05-13 | Moswin | Completed | Production |  | 6 | 6
vajraglobal.com | Updated SEO Automation BRD |  | Alt text generation for Vachi HR - Live |  | 2026-05-14 | 2026-05-18 | Moswin | Completed | Production |  | 8 | 8
vajraglobal.com | DevOps as a Service (DaaS) |  | LinkedIn Optimization for devops visibility |  | 2026-05-13 | 2026-05-14 | Moswin | Completed | Production |  | 4 | 4 |  |  |  | https://www.linkedin.com/posts/moswin_aws-eks-kubernetes-activity-7462126509927927808--uMs?utm_source=share&utm_medium=member_desktop&rcm=ACoAACoz00YBMtL992VJP8rD2-2VhlT-0tzwdTs
https://msmehealthengine.fametn.com/ | MSME |  | MSME live moving and testing |  | 2026-05-14 | 2026-05-15 | Moswin | Completed | Production |  | 2 | 2
| Thought leadership developement |  | Thought leadership project set up and run |  | 2026-05-18 | 2026-05-20 | Moswin | Completed | Production |  | 12 | 12
| Thought leadership developement |  | 1. Gradle version 2. Missing packages install 3. Missing dependencies install |  | 2026-05-21 | 2026-05-21 | Moswin | Completed | Production |  | 6 | 6
| Thought leadership developement |  | Identify firebase and include Device SHA code |  | 2026-05-22 | 2026-05-22 | Moswin | On Hold / Blocked | Local |  | 3
vajraglobal.com | Goal towards 99.99% availability |  | Internal monitoring and alert set up with error logs planning and tool identification |  | 2026-05-15 | 2026-05-15 | Moswin | Completed |  |  | 2 | 2
vajraglobal.com | neo4j implementation + deployment |  | Learn + understand neo4j |  | 2026-05-21 | 2026-05-27 | Moswin | Completed | Local |  | 15 | 8
vajraglobal.com | Backlink call with Padma |  |  |  | 2026-05-22 | 2026-05-22 | Moswin | Completed | Local |  | 1 | 1
vajraglobal.com | Updated SEO Automation BRD |  | Vachi live Alt text insertion |  | 2026-05-21 | 2026-05-27 | Moswin | Completed | Production |  | 2 | 2
vajraglobal.com | CI/CD |  | Hello Wiz - WIzard Staging + Production CICD Pipeline |  | 2026-05-06 | 2026-05-07 | Moswin | Under Review & Testing | Local |  | 0.5 |  |  | Have built and set up pipelines for each project. Will push into the repository as a maintainance activity on third week of June. | Dev team to test the workflow and client approval to go ahead with this implementation
vajraglobal.com | CI/CD |  | Hello Wiz - Admin Staging + Production CICD Pipeline |  | 2026-05-06 | 2026-05-07 | Moswin | Under Review & Testing | Local |  | 0.5 |  |  | Have built and set up pipelines for each project. Will push into the repository as a maintainance activity on third week of June. | Dev team to test the workflow and client approval to go ahead with this implementation
vajraglobal.com | CI/CD |  | Hello Wiz - Client Staging + Production CICD Pipeline |  | 2026-05-06 | 2026-05-07 | Moswin | Under Review & Testing | Local |  | 0.5 |  |  | Have built and set up pipelines for each project. Will push into the repository as a maintainance activity on third week of June. | Dev team to test the workflow and client approval to go ahead with this implementation
vajraglobal.com | CI/CD |  | Hello Wiz - Backend Staging + Production CICD Pipeline |  | 2026-05-06 | 2026-05-07 | Moswin | Under Review & Testing | Local |  | 0.5 |  |  | Have built and set up pipelines for each project. Will push into the repository as a maintainance activity on third week of June. | Dev team to test the workflow and client approval to go ahead with this implementation
automation.vajraglobal.com | Updated SEO Automation BRD |  | Backlink Monitoring |  | 2026-05-21 | 2026-05-28 | Moswin | In Progress | Local |  | 6 |  |  | Done with the requirement build and corrections. | Need full list of backlinks targets urls and project urls so we can set this up for those and follow that
vajraglobal.com | Updated SEO Automation BRD |  | Plan and document neo4j hosting options and cost and set up for clients documentation |  | 2026-05-28 | 2026-06-03 | Moswin | In Progress | Local |  | 8
vajraglobal.com | neo4j implementation + deployment |  | neo4j infra set up for clients plan with cloud self managed or server on prem hosting plan and cost split No due date |  | 2026-06-05 | 2026-06-05 | Moswin | Pipeline / To Do | Local |  | 5
vajraglobal.com | Updated SEO Automation BRD |  | Monitoring and alert set up in all servers as proposed |  | 2026-05-28 | 2026-06-03 | Moswin | Pipeline / To Do | Local |  | 8
vajraglobal.com | Updated SEO Automation BRD |  | Review + decision call and mail convo close with Padma and Valli |  | 2026-05-29 | 2026-05-29 |  | Completed
vajraglobal.com | Updated SEO Automation BRD |  | Make the changes in backlink. |  | 2026-05-29 | 2026-05-29 |  | In Progress
| Kreab developement |  | Set up frontend ,backend and understand code |  | 2026-05-29 | 2026-06-01 |  | Completed
vajraglobal.com |  |  | Share 30/60 days plan with G sir. |  | 2026-05-29 | 2026-05-29
vajraglobal.com |  |  | Backlink Monitoring- changes from Padma |  | 2026-06-02 | 2026-06-02 |  |  |  |  | 4
automation.vajraglobal.com | Updated SEO Automation BRD |  | Competitor Analysis |  | 2026-04-30 | 2026-05-08 | Moswin | Pipeline / To Do | Local
automation.vajraglobal.com | Updated SEO Automation BRD |  | Indexing Status |  |  | 2026-05-08 | Moswin | Pipeline / To Do | Local
automation.vajraglobal.com | Updated SEO Automation BRD |  | Keyword Research |  |  |  | Moswin | Pipeline / To Do | Local

## DGDA GitHub
S.No | From | To | Date | Available | Description
1 | Feat/Seo | Main | 20-08-2025 | Deleted | Move The Changes
2 | Main | feat/water-dispenser-latest | 28-08-2025 |  | Take a Backup
3 | feat/water-dispenser-latest | Main | 2025-02-09 | Deleted
4 | sapc4cintegration | feat/datareq | 2025-04-09 | Deleted | Due to conflict
5 | feat/datareq | Main | 2025-10-09
6 | Main | feat/dalstudent | 2025-11-09
7 | feat/dalstudent | Main |  | Deleted | Remove 'dgdaGeneralEnquiry','dgdaFeedback', 'dgdaComplaints', On C4C
8 | feat/dalstudent | Main | 2025-09-12 | Deleted | Move the water dispenser sponsors logo fix
9 | Main | Release | 2025-09-12 |  | C4C Water Pen Testing Changes
10 | feat/dalstudent | Main | 2025-09-17 | Deleted | Terraform Code Update
11 | feat/saudi-national-day | Main | 2025-09-18 | Deleted | Test if it is working or not
12 | feat/saudi-national-day | Main | 2025-09-19 | Deleted
13 | main | release/dgda | 2025-09-20
14 | main | release/dgda | 2025-09-21 |  | National Day Page move to Production
15 | feat/saudi-national-day | Main | 2025-09-22 | Deleted | National Day Page Fonts update
16 | Main | release/dgda | 2025-09-22 | Deleted | National Day Page Fonts update
17 | feat/al-masar-program | Main | 2025-10-01 |  | Al Masar Program Page Development and lint error fix
18 | feat/feat-school-fixed | Main | 2025-10-07 |  | School Visit form student condtion fix
19 | Main | release/dgda | 2025-10-08 |  | School Visit form student condtion fix
20 | feat/CTProgram | Main | 2025-10-13 |  | Curatorial Training Program Page
21 | feat/CTProgram | Main | 2025-10-16 |  | Form Language Fix
22 | Main | release/dgda | 2025-10-16 |  | Form Language Fix
23 | feat/CTProgram | Main | 2025-10-22 |  | video library Page code uncomment and move it to main
24 | Main | release/dgda | 2025-10-22 |  | video library Page code uncomment and move it to live
25 | feat/CTProgram | Main | 2025-10-29 |  | Royal Golf Club Hiring Opportunity form add to C4C Bab Samhan Hiring Opportunity Survey form add to C4C
26 | feat/CTProgram | Main | 2025-10-30 |  | School Visit Form Grade Validation Fix
27 | Main | release/dgda | 2025-10-30 |  | School Visit Form Grade Validation Fix
28 | feat/CTProgram | Main | 2025-11-07 |  | Move the Water Dispenser Form Intrest Type code to Staging
29 | Main | release/dgda | 2025-11-07 |  | Water Dispenser Move to Production
30 | feat/CTProgram | Main | 2025-11-10 |  | Water Dispenser CTA Target Fix move to staging
31 | Main | release/dgda | 2025-11-10 |  | Water Dispenser CTA Target Fix move to live
32 | feat/CTProgram | Main | 17-11-2025 |  | CT Program
33 | Main | release/dgda | 17-11-2025 |  | CT Program
34 | feat/CTProgram | Main | 18-11-2025 |  | Fix the Category
35 | Main | release/dgda | 18-11-2025 |  | Fix the Category
36 | feat/CTProgram | Main | 24-11-2025 |  | banner video responsive fix
37 | Main | release/dgda | 24-11-2025 |  | banner video responsive fix
38 | feat/CTProgram | Main | 28-11-2025 |  | Phone Number Validation after user remove the data Fix the validaion in coding
39 | feat/CTProgram | Main | 2025-01-12 |  | Date picker not working on single click fix on DGDA and remove the special chacter on the some of the form input id
40 | Main | release/dgda | 2025-01-12 |  | Date picker not working on single click fix on DGDA and remove the special chacter on the some of the form input id
41 | feat/CTProgram | Main | 2025-03-12 |  | Form Empty Value fix for mail template
42 | Main | release/dgda | 2025-03-12 |  | Form Empty Value fix for mail template
43 | feat/CTProgram | Main | 2025-05-12 |  | Dummy Push for variable update - Moswin
44 | Main | release/dgda | 2025-05-12 |  | Dummy Push for variable update - Moswin
45 | feat/CTProgram | Main | 2025-10-12 |  | Googe Tag Manager Tracking - Sowndar
46 | Main | release/dgda | 2025-05-12 |  | Dummy Push for variable update - Moswin
47 | feat/version-update | Main | 18-12-2025 |  | Version Upudate from 14.2.25 to 15.5.9
48 | Main | release/dgda | 23-12-2025 |  | Version Upudate from 14.2.25 to 15.5.9
49 | feat/version-update | Main | 26-12-2025 |  | UMA Forms Type Add
50 | feat/version-update | Main | 29-12-2025 |  | Register Number Logic
51 | Main | release/dgda | 29-12-2025 |  | Register Number Logic
52 | feat/version-update | Main | 2026-02-03 |  | Forms payload duplicate fix
53 | Main | release/dgda | 2026-03-04 |  | Forms payload duplicate fix
54 | feat/version-update | Main | 2026-02-09 |  | Leadership Components
55 | feat/version-update | Main | 2026-02-11 |  | Leadership Components Text Alignment
56 | feat/version-update | Main | 2026-02-12 |  | Leadership Components Text Alignment in Arabic
57 | feat/version-update | Main | 2026-02-13 |  | CTA and Header Tracking Code Update
58 | Main | release/dgda | 2026-02-24 |  | Leadership Components (HRH) Text Alignment fix in coding and CEO Message Design Moved to Production
59 | feat/finding-details | Main | 2026-06-11 |  | Move the Founding Details Single Page
60 | Main | release/dgda | 2026-06-12 |  | Move the Founding Details Single Page

## DGS GitHub
S.No | From | To | Date | Available | Description
1 | dev/DGS | Main | 19-11-2025 |  | Add the Target on the hedaer button
2 | Main | release/dgs | 19-11-2025 |  | Add the Target on the hedaer button
3 | dev/DGS | Main | 19-11-2025 |  | Header Item Align right
4 | Main | release/dgs | 19-11-2025 |  | Header Item Align right
5 | dev/DGS | Main | 27-11-2025 |  | OG Image - Moswin
6 | Main | release/dgs | 27-11-2025 |  | OG Image - Moswin
7 | dev/DGS | Main | 28-11-2025 |  | Phone Number Validation after user remove the data Fix the validaion in coding
8 | Main | release/dgs | 28-11-2025 |  | Phone Number Validation after user remove the data Fix the validaion in coding
9 | Main | Main | 2025-01-12 |  | Date picker not working on single click fix on DGS and remove the special chacter on the some of the form input id
10 | dev/DGS | release/dgs | 2025-01-12 |  | Date picker not working on single click fix on DGS and remove the special chacter on the some of the form input id
11 | dev/DGS | Main | 2025-01-12 |  | Recaptcha fix - Moswin
12 | Main | release/dgs | 2025-01-12 |  | Recaptcha fix - Moswin
13 | dev/DGS | Main | 2025-01-12 |  | Speaker Page categories issue Fix
14 | Main | release/dgs | 2025-01-12 |  | Speaker Page categories issue Fix
15 | dev/DGS | Main | 2025-03-12 |  | Form Empty Value fix for mail template
16 | Main | release/dgs | 2025-03-12 |  | Form Empty Value fix for mail template
17 | dev/DGS | Main | 2025-04-12 |  | Dummy Push for Variable Update - Moswin
18 | Main | release/dgs | 2025-04-12 |  | Dummy Push for Variable Update - Moswin
19 | dev/DGS | Main | 2025-05-12 |  | Dummy Push for variables update - Moswin
20 | Main | release/dgs | 2025-05-12 |  | Dummy Push for variables update - Moswin
21 | dev/DGS | Main | 2025-10-12 |  | Move the PDF Title Field
22 | Main | release/dgs | 2025-10-12 |  | Move the PDF Title Field
23 | dev/DGS | Main | 2025-12-18 |  | First Name and last name max character
24 | Main | release/dgs | 2025-12-18 |  | First Name and last name max character
25 | dev/DGS | Main | 2025-12-31 |  | DGS Video Page(Coming Soon) Instead of the home page, create a new page and update the video on that page.
25 | Main | release/dgs | 2025-12-31 |  | DGS Video Page(Coming Soon) Instead of the home page, create a new page and update the video on that page.

## DGDA Environment
| AWS Name | Link | Coding | Content | GitHub
1 | dgda-prod | https://www.dgda.gov.sa | Production | Production | release/dgda | prod | Delivery | PROD GitHub to AWS-SSM Sync env vars & secrets
2 | dgda-prod-preview | https://preview.dgda.gov.sa/en | Production | Staging | release/dgda | prod | Preview | PROD GitHub to AWS-SSM Sync env vars & secrets
3 | dgda-preprod-preview | https://preview-preprod.dgda.gov.sa/en | Staging | Staging | main | preprod | Preview | PREPROD GitHub to AWS-SSM Sync env vars & secrets
4 | dgda-preprod | https://preprod.dgda.gov.sa/ | Staging | Production | main | preprod | Delivery | PREPROD GitHub to AWS-SSM Sync env vars & secrets
5 | dgda-dev | link as branch name | Staging | Staging |  | preprod | Preview

## DGS Environment
# | AWS Name | Temp Url | Link | Coding | Content | GitHub
1 | dgs-prod | https://release-dgs.d1ae5b5egxa43d.amplifyapp.com/ | https://www.dgs.sa/ | Production | Production | release/dgs
2 | dgs-prod-preview | https://release-dgs.dl1b7xhxrjhbe.amplifyapp.com/ | https://preview.dgs.sa/ | Production | Staging | release/dgs
3 | dgs-preprod-preview | https://main.d3kmmfy327jwr7.amplifyapp.com/ | https://preview-preprod.dgs.sa/ | Staging | Staging | main | Error 1016
4 | dgs-preprod | https://main.d1lnkvi8pnbqc9.amplifyapp.com/en | https://preprod.dgs.sa/ | Staging | Production | main | Error 1016
5 | dgs-dev | https://dev-dgs.ddz0gzz9umix8.amplifyapp.com/ | link as branch name | Staging | Staging

## Dropdown
WebsiteName | Website Url | Status | Status Definistion | Env | Env Definition | Priority | Priority Definition | Leave Status | Half Day / Full Day | Employee Details | Leave Type
FIA | farnborough.com | Pipeline / To Do | Approved tasks that are queued for work but have not yet been started by a resource. | Local | Individual developer’s sandbox. Work here is isolated and does not affect any other team members. | Low | Minor enhancements, cosmetic tweaks, or "nice-to-have" items with no impact on current functionality. | Pending | First Half | Abhicheke | Casual Leave
FIA | farnboroughairshow.com | Requirements Not Clear | Task is paused because the scope, logic, or design instructions are insufficient to proceed. | Staging | The integration environment where all code is combined to test for bugs and system stability. | Medium | Standard tasks that provide value but are not time-sensitive. To be completed in the normal work cycle. | Approved | Second Half | Moswin | Sick Leave
FIA | farnboroughinternational.org | In Progress | Active development or configuration is currently underway by the assigned resource. | UAT | User Acceptance Testing. A stable environment where the client validates that the solution meets their needs. | High | Important features or significant bugs that affect user experience. Requires prioritization in the next 24-48 hours. | Rejected | Full Day | Parthiban | Earned Leave
FIA | aerospaceglobalforum.com | On Hold / Blocked | Work has stopped due to a technical dependency, internal bottleneck, or resource unavailability. | Production | The "Live" environment used by end-users. Any changes here are final and affect the actual business. | Urgent | Time-critical tasks or major functional defects that impede a deadline. Requires immediate team focus. | Cancelled |  | Rackesh Kumaran | Maternity Leave
FIA | events.farnboroughinternational.org | Waiting for Client Input | Work cannot proceed until the client provides required data, access, or clarification. |  |  | Critical / Blocker | System-wide failure or total work stoppage. Critical security risks or production outages requiring "all hands on deck." |  |  | Regan | Paternity Leave
FIA | farnboroughinternationalstudios.com | Under Review & Testing | Development is completed and the task is undergoing internal QA, validation, or peer review. | [6 empty] | Sunder | Comp Off
Adfactors PR Private Limited | intranet.adfactorspr.com | Changes Requested / Rework | Client or QA has requested modifications; task is sent back for further development or correction | [6 empty] | Sowndar
Adfactors PR Private Limited | work.adfactorspr.com | Ready for Execution | All approvals are completed; task is finalized and ready for production release.
Diriyah Gate Development Authority | www.dgda.gov.sa | Completed | The task is successfully deployed, verified in Production, and officially signed off.
Diriyah Gate Development Authority | www.dgs.sa | Closed / Cancelled | The task was created in error or decided against before significant work began.
Vajra Global | vajraglobal.com | Closed – Billable | Development was completed, but the client chose not to go live. Hours worked are subject to final invoicing.
MSME | https://msmehealthengine.fametn.com/ | Closed – Not Proceeding | The project or task has been terminated mid-way; no further work or deployment will occur.

## Agreed Hours
# | Website List | Website URL | CMS | Overall Allocated Hours/Month | Allocated Hours for Website Maintenance/Month | Allocated Hours for Development Support/Month
1 | Farnborough International Corporate | https://www.farnboroughinternational.org/ | Umbraco | 18 | 18 | -
2 | Farnborough International Exhibition & Conference Centre | https://www.farnborough.com/ | Umbraco | 30 | 18 | 12
3 | Farnborough International Airshow | https://www.farnboroughairshow.com/ | Umbraco | 35 | 18 | 17
4 | Farnborough International Studios | https://farnboroughinternationalstudios.com/ | Umbraco | 18 | 18 | -
5 | Farnborough International Aerospace Events | https://events.farnboroughinternational.org/ | Umbraco | 18 | 18 | -
6 | Aerospace Global Forum | https://www.aerospaceglobalforum.com/ | Umbraco | 18 | 18 | -
7 | Farnborough International Space Show |  | WordPress | 20 | 11 | 9
8 | Sustainable Skies World Summit |  | WordPress | 20 | 11 | 9
9 | International Symposium on Remote Sensing of Environment |  | WordPress | 11 | 11 | -
10 | Adfactor Intranet | https://intranet.adfactorspr.com/ | Umbraco | 110
11 | Adfactor Hubspot |  | Hubspot | 25

## Umbraco Update For all Website
WebSite Vesrion | Current Version | New Version | End-of-Life | Balance Day | Comment
farnborough.com | 8.18.15 | 13.12.0 | 2026-12-14 | 178 days remaining | New Site in Staging need to move it to live
farnboroughairshow.com | 13.9.1 | 13.12.0 | 2026-12-14 | 178 days remaining
aerospaceglobalforum.com | 10.8.7 | 13.12.0 | 2026-12-14 | 178 days remaining | Nail is ooo we need to waiting for billing
events.farnboroughinternational.org | 8.18.15 | 13.12.0 | 2026-12-14 | 178 days remaining
farnboroughinternationalstudios.com | 10.8.7 | 13.12.0 | 2026-12-14 | 178 days remaining
farnboroughinternational.org | 7.15.11 | 13.12.0 | 2026-12-14 | 178 days remaining
intranet.adfactorspr.com | 10.8.9 | 13.12.0 | 2026-12-14 | 178 days remaining
work.adfactorspr.com | 10.8.9 | 13.12.0 | 2026-12-14 | 178 days remaining
Formulas:
Balance Day = IF([End-of-Life]="", "", IF([End-of-Life] - TODAY() <= 0, "Update Required", [End-of-Life] - TODAY() & " days remaining"))

## Farnborough Server Path
| Site | Path | File Size | DB Name | Production / Staging | PDF Key
1 | farnboroughairshow.com | D:\inetpub\wwwroot\live\NewSite\2025\FIA2025 | 3.72 GB | Farnborough_Airshow_Production | Production
2 | farnborough.com | D:\inetpub\wwwroot\live\NewSite\2025\Venue2025 | 6.22 GB | Farnborough_Venue_Production | Production
3 | events.farnboroughinternational.org | D:\inetpub\wwwroot\live\NewSite\2023\FarnboroughInt | 2.69 GB | FarnboroughInt_Production | Production
4 | FarnboroughInternational.org | D:\inetpub\wwwroot\live\farnboroughinternational.org\http | 2.84 GB | FarnboroughInt_Production | Production
5 | www.farnboroughinternationalstudios.com | D:\inetpub\wwwroot\live\NewSite\2024\farnborughfilmstudios.com | 1.12 GB | farnboroughstudios_live | Production
6 | www.aerospaceglobalforum.com | D:\inetpub\wwwroot\live\NewSite\2024\AGF | 998 MB | AGF_Airshow_Production | Production
7 | http://intranet.adfactorspr.com/ | /VAJRA/Newintranet.adfactorspr.com |  | AdfIntranet03052024 | Production | 221cc1a570764cd09f244f8625b03e32
8 | https://work.adfactorspr.com/ | /VAJRA/work.adfactorspr.com/work.file |  | workadfactorspr | Production | 7789c40d42bb49aea84d2faa8b317300
9 | https://eventsstaging.farnboroughinternational.org/ | D:\inetpub\wwwroot\Staging\UAT\2023\FarnboroughInt | 2.14 GB | FarnboroughInt_Staging | Staging
10 | https://staging.farnborough.com/ | D:\inetpub\wwwroot\Staging\UAT\2025\Venue2025Update\Staging | 6.8 GB | Farnborough_Venue_Staging_2025 | Staging
11 | staging.farnboroughairshow.com | D:\inetpub\wwwroot\Staging\UAT\2024\FIA2025 | 3.45 GB | Farnborough_Airshow_Staging24 | Staging
12 | staging.farnboroughinternational.org | D:\inetpub\wwwroot\Staging\Farnborough_International\Farnborough_International | 2.21 GB | FarnboroughInt_Staging | Staging
13 | staging.farnborughfilmstudios.com | D:\inetpub\wwwroot\Staging\UAT\2025\staging.farnborughfilmstudios.com | 1.15 GB | farnboroughstudios_staging_2024 | Staging
14 | staging.aerospaceglobalforum.com | D:\inetpub\wwwroot\Staging\UAT\2024\AGF | 939 GB | AGF_Airshow_Staging | Staging
15 | https://intranetstaging.adfactorspr.com/ | /VAJRA/VAJRA/intranetstaging.adfactorspr.com |  | AdfactorStaging | Staging | 8db1e45b79c247679a2113931cf7536c
16 | https://workstaging.adfactorspr.com/ | /VAJRA/workstaging.adfactorspr.com |  | WorkAdfactorsprStaging | Staging | No Key for workstaging